## Read me
Acceptance and sign-off workbook (Example, as signed)
Acceptance and sign-off for one project: the results the sponsor will accept, how each is tested, who says it's met, and who signs. Four tabs: Read me, Finished, Criteria and Changes.
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as it stood when v2 was signed on 28 Sep 2026.
Where to start
Start on Finished, with the project's details from the Register and its deliverables from the charter. Then write the criteria on Criteria: for each deliverable, the results that show it's done.
Filling it in
1 | On Finished, copy Name, Sits under, Owner, Sponsor, Status and Planned finish from the Register. Type v1 in Version, and the day you made it in Dated.
2 | Under What the charter delivers, copy each Id, Deliverable and Accepted by from the project charter's What it delivers, word for word.
3 | Under Who builds it, name the people and teams who build the project. Under Gates, type the gate names from your gate map, in order.
4 | On Criteria, add one criterion per row: its ID, its gate, what's true when it's met, the deliverable it proves, the Test, the Pass line and the Owner who says it's met.
5 | Read Checks on Finished and fix every row that shows △. Then sign, in the order under At each signing.
6 | Before each gate date, mark each criterion Met with its Evidence and date, or Waived with a Reason and date. Then pick the Next gate on Finished.
TYPED AND WORKED OUT
Type in the white cells. Grey cells are worked out and locked, with no password. The hidden columns on Criteria hold the checks' working and the copy taken at signing.
WRITING A CRITERION
1 | A criterion is something true when it's met, not a task. Write "The new engine's invoice matches the old engine's", not "Compare the invoices".
2 | Test says what someone does, and on what. Pass line says the number or result that counts. A Criterion or Pass line with a word like fast or easy gets a ◇, so look at it again.
3 | The Owner says it's met, and can't be on the builders list. By default it's whoever accepts the deliverable it proves.
4 | Number criteria yourself, C-01, C-02 and so on, and never reuse a number. Sorting the tab doesn't change them.
5 | Once anyone has signed, never clear a criterion. If it's no longer wanted, mark it Waived with a Reason, so its ID stays used.
6 | Waived is a decision: someone lets the gate go ahead without the criterion. Reason says who, and why.
7 | Criteria holds 100 rows. The line at the top of Finished warns at 95.
SIGNING
1 | Signing on Finished says where the sheet stands. Draft: nobody has signed. Waiting to sign: some have. Signed: everyone has signed this version. Changed since signed: a criterion changed and Changes has no row for it.
2 | The project charter calls the same four states Charter status.
3 | Sponsor, Owner and Takes it over each sign with a name, a typed signature, the date and the version.
4 | Type First signed on once, on the day of the first signature, and never change it.
5 | While the Next gate comes before Readiness, Takes it over may read Open: and the role, such as Open: Support lead. Once Readiness is next, check 6 needs a name and a signature.
6 | No sponsor yet? Type Not yet named in About and leave the Sponsor row empty. Check 6 fails until a sponsor signs.
AT EACH SIGNING
1 | From v2 on, change the Version on Finished, such as v2 to v3, and the date in Dated.
2 | On Changes, write a row for each criterion you changed: the old wording and the new, why, who decided, and whether the sponsor agreed.
3 | Read check 5 until it's clear.
4 | Sign the version.
5 | Copy the signed text into the hidden columns on Criteria. Show them with the + above the column letters. Copy C6:C105 and paste it as values into Y6, then E6:E105 into Z6 and F6:F105 into AA6. Do this at the first signing too.
Check 5 compares the criteria with this copy. Paste before check 5 is clear and the copy takes in the change, so check 5 can't see it. The file can't stop that.
READING THE MARKS
△ | A check found something, and the words say what. Filter Row check on △ to list the rows.
○ Clear | The check found nothing.
◇ | A hint worth a look, such as a vague word. It isn't counted as a failure.
THE CHECKS
Finished runs seven checks on the whole sheet. Row check on Criteria and on Changes says what's wrong with each row. Checks 5 and 6 read clear until someone signs.
1 | A criterion no one can test: its Criterion, Test or Pass line is blank. Write the missing one.
2 | A criterion with no Owner, or a builder as Owner. Give it an Owner who didn't build it, usually whoever accepts the deliverable. It also fails when Who builds it is empty.
3 | A criterion off the gate list, or without its own ID. Pick a gate from the list, and give each criterion its own ID. It also fails a gate where every criterion is waived.
4 | A criterion marked Met or Waived without its record. Met needs Evidence and a date; Waived needs a Reason and a date. The check sees that Evidence is filled in, not that it's true.
5 | A change after signing that isn't written down. Once anyone has signed, a criterion whose Criterion, Test or Pass line differs from the copy taken at signing needs a Changes row in this Version. It also fails a Changes row that's incomplete or that the sponsor hasn't agreed.
6 | A signature missing, or for an earlier version. Once anyone has signed, Sponsor, Owner and Takes it over each need a name, a signature, a date and this Version, and First signed on needs a date.
7 | A deliverable no criterion tests. Each Id under What the charter delivers needs at least one criterion, and each criterion's Proves must be one of those Ids or Whole project.
YOUR LOGO
The FRQZ logo is at the top of every tab. To use your own, delete it and insert your logo in the same cell.
OTHER FILES
1 | Name, Sits under, Owner, Sponsor, Status and Planned finish come from the Register, the Ids and deliverables from the project charter, and the gate names from the gate map. Files connect by these names, never by formulas.
2 | The gate map holds the project's state at each gate, with one line for these criteria: Every acceptance criterion due at this gate is Met or waived. Keep the criteria here, and don't copy them there.
3 | An assistant can check the criteria for you. The brief is in frqz-acceptance-and-sign-off-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results.
ABOUT THIS EXAMPLE
Hollins Software is a made-up software company. Everyone in it is made up too.
This copy is the Example as it stood when v2 was signed, on 28 Sep 2026. Step 5 of the agent brief compares the Example with it.
It fails checks 1, 2, 3 and 6, on the same rows as the Example. Check 5 is clear, because nothing had changed since signing.
C-03 and C-07 are still Open here. They were met on 14 and 15 Oct.
No check reads today's date, so the results stay as they are.
To start your own, use the blank file. This one's hidden columns hold the Example's signed text.
Note on A1: To use your own logo, delete this one and insert yours here.

## Finished
Acceptance and sign-off (Example, as signed) | [10 empty] | Criteria in use
Met
Waived
Waived by a builder (hint)
ABOUT | [5 empty] | WHAT THE CHARTER DELIVERS |  |  |  |  | Signing has begun (1 or 0)
NAME | Billing Engine Rewrite |  |  |  |  | Deliverable | Id | Accepted by | Criteria for it |  | Dates typed as text in Sign-off or First signed on
SITS UNDER | Billing and Payments Program |  |  |  |  | Monthly invoice run on the new engine | D1 | Rhys (Finance Operations Lead) |  |  | Gates with every criterion waived
LEVEL | Project |  |  |  |  | Credit notes and refunds on the new engine | D2 | Rhys (Finance Operations Lead)
OWNER | Anders (Engineering Manager) |  |  |  |  | Connection to the customer records Data Migration Wave 2 fills, tested on a full copy | D3 | Rhys (Finance Operations Lead)
SPONSOR | Not yet named |  |  |  |  | Cutover of invoicing from the old engine, rehearsed twice, with rollback | D4 | Priya (CTO)
STATUS | Active |  |  |  |  | Handover to Finance Operations and Support, with runbook and training | D5 | Noor (Support Lead)
PLANNED FINISH | 2027-06-30
VERSION | v2
DATED | 2026-09-28
FIRST SIGNED ON | 2026-06-12
SIGNING
NEXT GATE | Build complete
CHECKS | [5 empty] | WHO BUILDS IT
A criterion no one can test | [5 empty] | Anders
A criterion with no Owner, or a builder as Owner | [5 empty] | Backend engineers
A criterion off the gate list, or without its own ID | [5 empty] | Build agent
A criterion marked Met or Waived without its record
A change after signing that isn't written down
A signature missing, or for an earlier version
A deliverable no criterion tests
SIGN-OFF | [5 empty] | GATES
Role | Name | Signature | What signing means | Date | Version signed | Gate | Criteria | Reads | Look | Criteria at this gate | Met at this gate | Waived at this gate | Row still to sign (1 or 0)
Sponsor |  |  | I agree this is what finished means for this project. |  |  | Start
Owner | Anders (Engineering Manager) | Anders | I will deliver to these criteria, and log any change to them on Changes. | 2026-09-28 | v2 | Plan baselined
Takes it over | Rhys (Finance Operations Lead) | Rhys | I have read what I will take over, and I will accept it against these criteria. | 2026-09-28 | v2 | Build complete
Takes it over | Noor (Support Lead) | Noor | I have read what I will take over, and I will accept it against these criteria. | 2026-06-12 | v1 | Readiness
Go/no-go
A signature covers the version it names. Change a criterion after signing, and the sheet needs a new version and new signatures. | [5 empty] | Handover accepted
A typed name records a signature. It doesn't prove who typed it. | [5 empty] | Close
REVIEW NOTES
This copy fails checks 1, 2, 3 and 6, as the Example does. Check 5 is clear: nothing had changed since v2 was signed.
Note on J1: To use your own logo, delete this one and insert yours here.
Note on B6: The project's name exactly as the Register writes it. Other files find this sheet by it.
Note on G6: What the project hands over, copied word for word from the charter's What it delivers.
Note on H6: The charter's Id: D1, D2 and so on. Criteria point to it in Proves, so never reuse one.
Note on I6: The one person who accepts this deliverable, as the charter names them. By default they are the Owner of its criteria.
Note on J6: Worked out: how many criteria prove this deliverable. Check 7 fails a deliverable with none.
Note on B7: The program it sits under, as the Register writes it.
Note on B8: Always Project: acceptance criteria belong to one project.
Note on B9: The Register's Owner, written the same way, such as Anders (Engineering Manager). The person accountable for delivering the project.
Note on B10: The Register's sponsor. If there isn't one yet, type Not yet named and leave the Sponsor row in Sign-off empty. Check 6 fails until a sponsor signs.
Note on B11: From the Register: Proposed, Active, Paused, Completed or Terminated.
Note on B12: From the Register. The end of the project, after the last wave, not the go-live.
Note on B13: v1, v2 and so on. Make the next version when a criterion changes after signing, or when the project is renamed on the Register.
Note on B14: The day this version was made.
Note on B15: The day of the first signature on v1. Type it once and never change it.
Note on B16: Worked out. Draft until someone signs, Waiting to sign until everyone has, Signed when everyone has signed this version, Changed since signed when a change isn't written down.
Note on B17: The next gate to be decided, picked from the list under Gates. Takes it over may read Open: until Readiness is next.
Note on A19: Seven checks on the whole sheet. Each says in a sentence what it found. Row check on Criteria and on Changes says which row.
Note on G20: The people and teams who build this, from the charter's Who: a first name or a team name, such as Anders or Backend engineers. Check 2 fails an Owner whose name contains one of them.
Note on A30: Sponsor, Owner and Takes it over sign. Add a second Takes it over, or anyone else who must agree, in the two rows below.
Note on B30: Their name as the Register or the charter writes it, such as Rhys (Finance Operations Lead).
Note on C30: Type your name to sign.
Note on D30: Fixed for the first three roles. On a row you add, write what that person agrees to.
Note on E30: The day they signed.
Note on F30: The version they signed, such as v2. Check 6 fails a signature for an earlier version.
Note on G30: The gate names from your gate map, in order. The Gate column on Criteria picks from them. The gate map holds the dates and who decides.
Note on H30: Worked out: how many criteria sit on this gate.
Note on I30: Worked out: how many of them are met, and how many waived.
Note on J30: A ◇ when a gate has no criteria, or more than half are waived. A △ when every criterion is waived, which fails check 3.

## Criteria
Criteria (Example, as signed)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as it stood when v2 was signed on 28 Sep 2026.
CRITERIA
ID | Gate | Criterion | Proves | Test | Pass line | Owner (says it's met) | Status | Evidence | Met or waived on | Reason | Row check | Row in use (1 or 0) | Fails check 1 (1 or 0) | Fails check 2 (1 or 0) | Fails check 3 (1 or 0) | Fails check 4 (1 or 0) | Fails check 5 (1 or 0) | Fails check 7 (1 or 0) | Vague word found (1 or 0) | Waived by a builder (1 or 0) |  |  | Criterion as signed (paste values) | Test as signed (paste values) | Pass line as signed (paste values)
C-01 | Plan baselined | Every plan item has an owner and a due date | Whole project | Count the plan items missing an owner or a due date | 0 items missing either | Tomasz (PMO Head) | Met | Tracker export, 12 Jun 2026 | 2026-06-12 | [13 empty] | Every plan item has an owner and a due date | Count the plan items missing an owner or a due date | 0 items missing either
C-02 | Plan baselined | Every report that reads the old engine's tax export works from the new engine | Whole project | Ask Finance which reports read the export, then run each one on the new engine | Every report Finance names runs | Hugo (Program Manager) | Waived |  | 2026-06-12 | Hugo (Program Manager): the US tax rules were carried over, and other countries' rules were left out of the first cutover, so it doesn't need the export. | [12 empty] | Every report that reads the old engine's tax export works from the new engine | Ask Finance which reports read the export, then run each one on the new engine | Every report Finance names runs
C-03 | Build complete | For each of 40 sample accounts, the new engine's invoice matches the old engine's | D1 | Run both engines on September's data for the 40 accounts | 40 of 40 match to the cent | Rhys (Finance Operations Lead) | Open | [15 empty] | For each of 40 sample accounts, the new engine's invoice matches the old engine's | Run both engines on September's data for the 40 accounts | 40 of 40 match to the cent
C-04 | Build complete | The new engine connects to the customer records Data Migration Wave 2 fills, with no invoice lost | D3 | Connect to a full copy of the records and count the invoices in both engines | Counts match, with 0 invoices missing | Rhys (Finance Operations Lead) | Open | [15 empty] | The new engine connects to the customer records Data Migration Wave 2 fills, with no invoice lost | Connect to a full copy of the records and count the invoices in both engines | Counts match, with 0 invoices missing
C-05 | Build complete | The month-end invoice run is fast enough | D1 |  | Fast enough for month end | Rhys (Finance Operations Lead) | Open | [15 empty] | The month-end invoice run is fast enough |  | Fast enough for month end
C-06 | Build complete | Open defects at the gate are within the limit | D1 | Count the open defects by severity | 0 severity 1, 0 severity 2, 5 or fewer severity 3 | Noor (Support Lead) | Open | [15 empty] | Open defects at the gate are within the limit | Count the open defects by severity | 0 severity 1, 0 severity 2, 5 or fewer severity 3
C-07 | Build complete | All 12 invoice cases Finance listed pass on the new engine | D1 | Run the 12 cases on the new engine | 12 of 12 pass | Anders (Engineering Manager) | Open | [15 empty] | All 12 invoice cases Finance listed pass on the new engine | Run the 12 cases on the new engine | 12 of 12 pass
C-12 | Go/no-go | Credit notes and refunds from the new engine match Finance's figures | D2 | Run 10 sample credit notes and refunds on both engines | 10 of 10 match to the cent | Rhys (Finance Operations Lead) | Open | [15 empty] | Credit notes and refunds from the new engine match Finance's figures | Run 10 sample credit notes and refunds on both engines | 10 of 10 match to the cent
C-08 | Go/no-go | Billing can be rolled back to the old engine after cutover | D4 | Time a rollback on the staging copy | Rollback finishes in 4 hours or less | Priya (CTO) | Open | [15 empty] | Billing can be rolled back to the old engine after cutover | Time a rollback on the staging copy | Rollback finishes in 4 hours or less
C-09 | Handover accepted | Every invoice in the first live run matches the finance ledger | D1 | Compare the run's totals with the ledger after the first live run | Totals match to the cent, with 0 unexplained differences | Rhys (Finance Operations Lead) | Open | [15 empty] | Every invoice in the first live run matches the finance ledger | Compare the run's totals with the ledger after the first live run | Totals match to the cent, with 0 unexplained differences
C-10 | Go/no-go | Support can answer billing questions from the runbook alone | D5 | Noor's team answers 10 sample billing questions | 10 of 10 answered without escalation | Noor (Support Lead) | Open | [15 empty] | Support can answer billing questions from the runbook alone | Noor's team answers 10 sample billing questions | 10 of 10 answered without escalation
C-11 | Go-live | Finance Operations runs a month-end invoice run on the new engine alone | D1 | Finance Operations runs it with no one from the build team | The run finishes with no engineering help | Rhys (Finance Operations Lead) | Open | [15 empty] | Finance Operations runs a month-end invoice run on the new engine alone | Finance Operations runs it with no one from the build team | The run finishes with no engineering help
[21 empty] | Vague words, typed | Ids it can prove
[21 empty] | fast | Whole project
easy
intuitive
user-friendly
smooth
good enough
acceptable
adequate
reasonable
appropriate
as expected
looks right
Note on L1: To use your own logo, delete this one and insert yours here.
Note on A5: Number criteria yourself: C-01, C-02 and so on. Never reuse a number, even for a criterion you waive. Sorting the tab doesn't change them.
Note on B5: The gate where it has to be met. Pick it from the gate list on Finished.
Note on C5: One sentence: what is true when it's met. A result, not a task, such as The new engine's invoice matches the old engine's.
Note on D5: The deliverable it proves: an Id from What the charter delivers on Finished, or Whole project.
Note on E5: What someone does to check it, and on what, such as Run both engines on September's data.
Note on F5: The number or result that counts as a pass, such as 40 of 40 match to the cent.
Note on G5: The one person who says it's met. By default, whoever accepts the deliverable it proves. Never someone on the builders list.
Note on H5: Open, Met or Waived. Blank reads as Open.
Note on I5: Where the result is kept: the report, the run log or the file, with its date.
Note on J5: The day it was met or waived.
Note on K5: Needed when Waived: who waived it, and why.
Note on L5: Worked out: the first thing wrong with this row. Filter on △ to list them.

## Changes
Changes (Example, as signed)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as it stood when v2 was signed on 28 Sep 2026.
CHANGES
Version | Criterion | Date | What changed | Why | Decided by | Sponsor agreed | Row check
v2 | C-04 | 2026-09-21 | Test was on a sample copy, now on a full copy | A sample copy misses invoices kept in the archive | Anders (Engineering Manager) | No sponsor named
Note on H1: To use your own logo, delete this one and insert yours here.
Note on A5: The version this change goes into, such as v3. Check 5 looks for a row in the sheet's current Version.
Note on B5: The criterion's ID, such as C-06.
Note on C5: The day the change was agreed.
Note on D5: The old wording, then the new, such as Severity 2 limit was 0, now 3 or fewer.
Note on E5: Why, in a line.
Note on F5: The one person who decided the change, as the Register writes them.
Note on G5: Yes, No, or No sponsor named. A Pass line made easier is the change a sponsor most needs to see.
Note on H5: Worked out: a △ when a column is blank, the ID isn't on Criteria, or the sponsor said no.