## Read me
Plan workbook
A project's plan in one file: the work broken into items, an estimate for each, the dates against the gates, and every change since the plan was baselined. Seven tabs: Read me, Baseline, Work breakdown, Estimates, Schedule, Changes and Checks.
START
Start from the signed project charter and the gate map. Fill the tabs in order, Baseline first. Changes starts on the day the plan is baselined.
1 | On Baseline, type the details from the Register and the charter, then copy the charter's deliverables and cost lines, its Owner's limit and its tolerances.
2 | On Work breakdown, list the items, numbered 1, 1.1, 1.2. Give each one Owner and one person who accepts it, and each leaf the deliverable it serves.
3 | On Estimates, give each leaf a method, a basis, a confidence, and Low, Likely and High. Leave Baselined and Forecast blank for now.
4 | On Schedule, list the gates from the gate map, the milestones, what you need from other teams and the events, in date order, each with its Baselined date.
5 | When Plan baselined is decided, type Baselined on, copy each Likely into Baselined and each Baselined date into Original, and set Version to v1.
6 | From then on, log each change on Changes before you make it. Type a Forecast when a date or a figure is expected to move.
7 | Read Checks, and fix every row whose Row check shows △.
TABS
Baseline | The project's details, the charter's deliverables and cost lines, and the readings: Date, Cost, Scope and Overall.
Work breakdown | Every item, numbered, with one Owner and one person who accepts it. An item with no parts is a leaf, and only a leaf serves a deliverable.
Estimates | One row per leaf: Low, Likely and High, the method, the basis and the confidence, then the Baselined figure and the Forecast.
Schedule | Gates, milestones, needs and events in date order by Original, with each one's Forecast, Owner, working days late and reading.
Changes | Every request and every approved change: what it does to scope, cost and date, who decided it, and whether the sponsor agreed.
Checks | The nine checks, the first row each one fails at, and what to do.
Sizes | Work breakdown holds 60 items, Estimates 40, Schedule 39 dates and Changes 50. Baseline holds 8 deliverables and 8 cost lines. A row typed below these is outside every check.
CHECKS
Checks runs nine checks on what's typed, counting from As of on Baseline. Each shows its result, the first row it fails at and what to do. The Row check on each tab says what is wrong with each row.
1 | Work nobody owns or asked for: an item with no number, name, Owner or Accepted by; a leaf with no estimate or deliverable, or an Accepted by that isn't the deliverable's; a parent with an estimate; a deliverable with no item.
2 | Money that doesn't add up: a cost line that differs from its item's figure at v1, lines or a v1 total that differ from the Share, or a forecast outside the range. Until Baselined on is typed, it reads the Likely figures; after it, the Baselined ones. A forecast over the Baselined cost shows in Cost and in check 7.
3 | An estimate without its basis: no item, a second row for the same item, or no method, basis or confidence, or Low, Likely and High not in order.
4 | Dates that don't hold together: a name used twice, no kind, a Baselined that isn't a date, a gate name not on Read me, an Original before the row above's (a Baselined, until Original is typed), a date after the Planned finish, Close off the Planned finish, or Ends before Baselined. An approved move changes Baselined only, so the row stays where it is.
5 | A date nobody answers for: a gate, milestone or need not yet done with no Owner.
6 | A date or figure that moved with no change: a Forecast later than or different from Baselined with no Raised change naming it, a Baselined date other than Original with no Approved one, or an estimate added after the baseline with neither.
7 | A move past the Owner's limit: a date later than the limit's working days, a forecast over the Baselined cost by more than the limit, or approved changes that add up past a limit without the Sponsor's agreement.
8 | A need that arrives after it is needed: a Need whose Forecast is after its Baselined date.
9 | A change that isn't finished: a change whose Row check shows △, such as one approved and not applied, or one Raised for more than 14 days.
A small team can read checks 1, 3, 6 and 9 each week and all nine before a gate.
Check 3 finds a blank Basis. Whether a basis is any good is for a person to judge.
Two of the gate map's criteria are read here: every item has an owner and an estimate, at Plan baselined (checks 1 and 3), and every change since the plan was baselined is decided, at Build complete (check 9).
RULES
Each item, date and change keeps its number or name for good. Clear a row to remove it. Don't insert or delete rows.
After the plan is baselined, a Baselined cell changes only through an approved change, and Original never changes.
Only a leaf is estimated. A parent's figure is its parts added up.
A Need's Baselined date is the day it's needed by, and its Forecast is the day it's promised. A late Need holds up the milestone in Needed for and doesn't colour Date.
An Event happens to the project, such as someone leaving. It needs no owner and isn't read.
Every figure, limit and range is in the Unit on Baseline, Money or Days. Working days count Monday to Friday.
MARKS
△ | A check found something, and the words say what. Filter a Row check on △ to list the rows.
○ Clear | The check found nothing.
Not done | The check had nothing to test yet, such as no estimates. It isn't the same as clear.
GATE NAMES
Gate rows on Schedule use a name from this list, which matches the gate map. Change the names here if your gate map uses others; the three cells below them are spare.
Start
Plan baselined
Build complete
Readiness
Go/no-go
Handover accepted
Close
READINGS
Date | The worst reading on Schedule. Green while every gate and milestone is on time, Amber when one is late by up to the Date tolerance, Red beyond it or when a Baselined date has passed and the row isn't done.
Cost | Forecast at completion against the Baselined cost. Green at or under it, Amber when over by up to the Cost tolerance, Red beyond.
Scope | Not read until Baselined on is typed. Red when an estimate was added after the baseline with no change, Amber while a Raised request changes scope, otherwise Green.
Overall | The worst of Date, Cost and Scope.
Owner's limit | What the charter lets the Owner do alone: move a date by up to the working days in C15, and add up to C16 to the baseline. It's printed with the readings and colours nothing.
The Status report reads Date, Cost and Scope by the same rules, and both read against the Baselined figures as they stand after approved changes.
CHANGES
Number a request CR-1, CR-2 and on. Once it's approved it keeps its number as CH: CR-5 becomes CH-5.
To approve one, change its No. from CR to CH, set Status to Approved with Decided on and Decided by, type the new Baselined figure or date on Estimates or Schedule, raise Version on Baseline, and set Applied to Yes. Original stays as it was, and the Schedule row stays where it is.
After an approved change, Date and Cost read against the new Baselined figures and go back to Green. Original, Moved in all and the change's line keep the trace.
Past the Owner's limit, the sponsor agrees: type their name in Sponsor agreed. With no sponsor named on Baseline, nothing past the limit clears.
Scope, Cost and Date each need an answer, and 0 and None are answers. Decide a request within 14 days of Raised on.
WORKING
Grey cells are worked out from what you type, and locked so they aren't typed over. There's no password.
The working is in hidden columns, each with a header: I to L on Work breakdown, L to R on Estimates, R to Y on Schedule, Q and R on Changes, and J and K on Baseline. Unhide them to read it.
YOUR LOGO
The FRQZ logo is in cell A1 on every tab. To use your own, delete it and insert your logo in A1, on each tab.
OTHER FILES
The deliverables and cost lines on Baseline are copied by hand from the project charter, and the Share and Planned finish from the Register. Change them there first, then here.
Gate dates, and who decides each gate, come from the gate map. X1 and X2 are copies of the program workbook's lines, which the RAID log points to; Note says when they were copied.
The Status report, the Decision log and the project close cite a change by its CR or CH number, so keep each number for good.
Anyone who opens this file sees every cell. To share it with someone outside the company, send them their rows, not the file.
An assistant can check the plan for you. The brief is in frqz-plan-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results. It never types a date, a figure or a change.

## Baseline
Baseline
DETAILS
| Name | [7 empty] | As of, as the checks use it
Sits under
| Owner | [7 empty] | Forecast more than the Owner's limit over Baselined cost (1 or 0)
Sponsor
Share of the envelope
Planned finish
Version
Dated
Baselined on
As of
Owner's limit, working days
Owner's limit, cost
Cost tolerance (percent)
Unit
Range low
Range high
Forecast given by
Forecast given on
Date tolerance (working days)
DELIVERABLES
| Id | Deliverable | Accepted by | [5 empty] | Items on Work breakdown serving it | Helper, worked out
COST LINES
| Line | Item | Charter amount | Baselined now | Moved by approved changes | At v1 | Spent to date | Match
Total
READINGS
Baselined cost
Forecast at completion
Spent to date
Date
Cost
Scope
Overall
Owner's limit
Note on C5: The project's name exactly as the Register writes it. Row 2 of every tab shows it.
Note on C6: The program it sits under, as the Register writes it. Leave it blank if it sits under none.
Note on C7: The project's Owner as the Register writes it, such as Anders (Engineering Manager). A question about a row with no owner goes to this person.
Note on C8: The sponsor's name, or Not yet named. A change past the Owner's limit clears only when this person has agreed it.
Note on C9: The project's share of the envelope, from the program charter and the Register, in the Unit in C18.
Note on C10: From the Register. Every date on Schedule falls on or before it, and Close falls on it.
Note on C11: v1 from the day the plan is baselined, v2 after the first approved change that moves a Baselined cell, and so on.
Note on C12: The day this copy was last changed.
Note on C13: The day Plan baselined was decided. Leave it blank until then; the checks on changes read Not done while it is.
Note on C14: Optional. The day the checks count from. Leave it blank to use today's date.
Note on C15: From the charter: how many working days the Owner may move a date without the sponsor. A whole number from 0 to 60. It colours nothing.
Note on C16: From the charter: how much the Owner may add to the baseline without the sponsor, in the Unit. It colours nothing.
Note on C17: How far the forecast may go over the Baselined cost before Cost reads Red, as a percent: 10 percent in the Example.
Note on C18: Money or Days. Every figure, limit and range in this file is in it.
Note on C19: Optional. The least the team thinks the whole project could cost, set at the baseline.
Note on C20: Optional. The most the team thinks it could cost. A forecast outside the range fails a check.
Note on C21: The one person who stands behind the forecast, such as Anders (Engineering Manager).
Note on C22: The day they gave it.
Note on C23: How many working days late a date may run before it reads Red: 5 in the Example.
Note on B25: From the charter's deliverables: D1, D2 and on. Never reuse an Id, even after its row goes. Work breakdown picks from these.
Note on C25: The deliverable, word for word as the charter has it.
Note on D25: The one person who accepts it, as the charter names them. Each item that serves it has the same Accepted by.
Note on B36: The charter's cost line, letter for letter.
Note on C36: The top item on Work breakdown that the line pays for, such as 1 or 4.
Note on D36: The line's amount in the charter.
Note on E36: Worked out: the Baselined figures of the item and its parts on Estimates, as they stand now.
Note on F36: Worked out: the cost of approved changes on Changes that name the item or one of its parts.
Note on G36: Worked out: Baselined now less the approved changes, which is what the plan held at v1. Until Baselined on is typed, the Likely figures of the item and its parts.
Note on H36: From the finance export for this line: what has been spent so far.
Note on I36: Worked out: whether the plan at v1 matches the charter's line.
Note on C48: Worked out: the Baselined figures on Estimates added up, after approved changes.
Note on C49: Worked out: the Forecasts on Estimates added up, with Baselined where Forecast is blank.
Note on C50: Worked out: Spent to date on the cost lines added up.
Note on C51: Worked out from the Reading column on Schedule: Red if any row is Red, then Amber, then Green. Not read with no dates.
Note on C52: Worked out: Green while the forecast is the Baselined cost or less, Amber while it's over by no more than the Cost tolerance, Red beyond.
Note on C53: Worked out: Red when an estimate was added after the baseline with no change, Amber while a Raised request changes scope, otherwise Green. Not read before Baselined on.
Note on C54: Worked out: the worst of Date, Cost and Scope.
Note on C55: From C15 and C16, so a reader sees what the Owner may decide alone. It colours nothing.

## Work breakdown
Work breakdown
ITEMS
No. | Item | Deliverable | Owner | Accepted by | Forecast | Row check | Parts below it | Rows on Estimates for it | Row in use (1 or 0) | Fails: work nobody owns or asked for (1 or 0)
Note on A5: 1, 2, 3 for the top items, then 1.1, 1.2 for the parts of 1, and so on. A part's number starts with its parent's and a dot. Each number once.
Note on B5: A thing delivered, such as Credit notes and refunds, not an activity. Up to 80 characters.
Note on C5: Leaf items only, the items with no parts: the deliverable it serves, picked from Deliverables on Baseline.
Note on D5: One person who answers for the item, written like Imani (Security Lead).
Note on E5: One person who accepts it. On a leaf, the person who accepts its deliverable on Baseline.
Note on F5: Worked out: the forecast for the item and all its parts, from Estimates.
Note on G5: Worked out: the first thing wrong with the row. Filter on △ to list them.

## Estimates
Estimates
LEAF ITEMS
Item | Name | Method | Basis | Low | Likely | High | Baselined | Forecast | Confidence | Row check | First thing wrong with the estimate itself | Row in use (1 or 0) | Fails: estimate without its basis (1 or 0) | Fails: moved with no change (1 or 0) | Figure as it stands now | Baselined figure (0 if blank) | Added after the baseline with no change (1 or 0)
Total
Note on A5: The item's No. on Work breakdown, picked from the list. One row per leaf item; a parent isn't estimated.
Note on B5: Worked out: the item's name from Work breakdown.
Note on C5: How the number was made: Bottom up, By analogy, Three-point or Fixed scope.
Note on D5: Where the number came from, such as a trial load of 200 invoices. Up to 120 characters.
Note on E5: The least it could take, in the Unit on Baseline.
Note on F5: What you expect it to take. Copied into Baselined on the day the plan is baselined.
Note on G5: The most it could take. Low, Likely and High may be equal.
Note on H5: Typed once, on the day the plan is baselined, as a copy of Likely. After that it changes only through an approved change on Changes.
Note on I5: What the project expects now, if it differs from Baselined. Blank means Baselined. A Forecast that differs needs a Raised change naming the item.
Note on J5: High, Medium or Low: how sure the team is of Likely.
Note on K5: Worked out: the first thing wrong with the row. Filter on △ to list them.

## Schedule
Schedule
DATES
# | Milestone | Kind | Baselined | Forecast | Done on | Ends | Owner | RAID Id | Needed for | Original | Note | Working days late | Reading | Moved in all | Row check | Row in use (1 or 0) | Forecast as the checks read it | Fails: dates that don't hold together (1 or 0) | Fails: nobody answers for it (1 or 0) | Fails: moved with no change (1 or 0) | Fails: past the Owner's limit (1 or 0) | Fails: arrives after it is needed (1 or 0) | Date the order check reads: Original, or Baselined until Original is typed
Formulas:
Working days late = IF(OR([Row in use (1 or 0)]=0,[Done on]<>"",NOT(ISNUMBER([Baselined])),NOT(ISNUMBER([Forecast as the checks read it]))),"",IF([Forecast as the checks read it]<=[Baselined],0,NETWORKDAYS([Baselined]+1,[Forecast as the checks read it])))
Moved in all = IF(OR([Row in use (1 or 0)]=0,NOT(ISNUMBER([Original]))),"",IF(ISNUMBER([Done on]),IF([Done on]<=[Original],0,NETWORKDAYS([Original]+1,[Done on])),IF(NOT(ISNUMBER([Forecast as the checks read it])),"",IF([Forecast as the checks read it]<=[Original],0,NETWORKDAYS([Original]+1,[Forecast as the checks read it])))))
Note on A5: Worked out: the row's place in Original order.
Note on B5: The milestone's full name, the same in every file. Gate rows use a name from Gate names on Read me. Each name once, up to 80 characters.
Note on C5: Gate: on the gate map. Milestone: a point in the plan. Need: something another team or project provides. Event: happens to the project and needs no owner.
Note on D5: The date the plan is held to. For a Need, the day it's needed by.
Note on E5: Blank means on its Baselined date. Type a date when it's expected to move. For a Need, the day the provider has promised.
Note on F5: The day it happened or was decided. Once it's typed, the row is no longer read.
Note on G5: Optional, for something over several days, such as the cutover weekend: the last day.
Note on H5: One person who answers for it. For a Gate, the gate map's Decides. Blank means nobody.
Note on I5: The line's Id on the RAID log or the program workbook, such as X1, when the date comes from one.
Note on J5: For a Need: the milestone it holds up, picked from column B.
Note on K5: Baselined as it stood on the day the plan was baselined. Typed once and never changed, so every move stays visible. Keep the rows in this date order, or in Baselined order until it's typed.
Note on L5: Anything a reader needs, such as where a copied date came from and when.
Note on M5: Worked out: working days from Baselined to Forecast, 0 if not later. Blank once Done on is typed.
Note on N5: Worked out: Green on time, Amber late by up to the Date tolerance, Red beyond it or past Baselined and not done. Needs and Events aren't read.
Note on O5: Worked out: working days from Original to Done on, or to Forecast while not done. It keeps the trace after a change.
Note on P5: Worked out: the first thing wrong with the row. Filter on △ to list them.

## Changes
Changes
CHANGE LOG
No. | Raised on | Decided on | Change | Item or milestone | Scope | Cost | Date | Status | Decided by | Sponsor agreed | Applied | Why | Row check | Fails: past the Owner's limit with no sponsor (1 or 0) | Fails: a change that isn't finished (1 or 0)
Note on A5: CR-1, CR-2 and on while it's a request. Once it's approved, the same number becomes CH: CR-5 becomes CH-5. Each number once.
Note on B5: The day the change was asked for.
Note on C5: The day it was decided. Blank while it's Raised.
Note on D5: What changes, the old then the new, such as Build complete, Baselined Fri 6 Nov 2026, now Fri 13 Nov 2026. Up to 160 characters.
Note on E5: The item's No. on Work breakdown or the milestone's name on Schedule, exactly. Blank when it names neither.
Note on F5: What it does to scope: None, More, Less or Changed.
Note on G5: The cost it adds, in the Unit on Baseline. 0 is an answer.
Note on H5: The working days it moves the date. 0 is an answer.
Note on I5: Raised, Approved, Rejected, Returned or Withdrawn.
Note on J5: The one person who decided it, written like Anders (Engineering Manager).
Note on K5: The sponsor's name once they agree it, or No sponsor named. Past the Owner's limit, only the Sponsor on Baseline clears it.
Note on L5: Yes once the new Baselined cells and Version are typed. Nothing to apply when it moves no Baselined cell.
Note on M5: Why, in a line.
Note on N5: Worked out: the first thing wrong with the change. Filter on △ to list them.

## Checks
Checks
# | Check | Result | First at | What to do
1 | Work nobody owns or asked for |  |  | Give every item a number, a name, an Owner and Accepted by. Give every leaf an estimate and a deliverable, and every deliverable an item.
2 | Money that doesn't add up |  |  | Make each cost line equal its item's figure at v1, and the lines and the v1 total equal the Share. If the forecast is outside the range, ask who gave it.
3 | An estimate without its basis |  |  | Write in Basis where the number came from: a count, a past project, a quote.
4 | Dates that don't hold together |  |  | Keep the rows in date order by Original (by Baselined until Original is typed), on or before the Planned finish, with Close on it. Give each Gate row a name from Read me.
5 | A date nobody answers for |  |  | Name one person in Owner for each gate, milestone and need not yet done.
6 | A date or figure that moved with no change |  |  | Raise a change on Changes that names the item or milestone in column E, or put the figure back.
7 | A move past the Owner's limit |  |  | Raise a change and get the sponsor's agreement. With no sponsor named, ask the Owner who decides it.
8 | A need that arrives after it is needed |  |  | Ask the need's Owner when it will arrive. If it can't arrive in time, raise a change for the milestone it holds up.
9 | A change that isn't finished |  |  | Give each decided change a date and a decider, apply each approved one, and decide each request within 14 days.
Note on D6: The first row that fails: an item's No., a milestone's name or a change's No. Its Row check says why.