## Read me
Decision log (Example)
One log of the decisions on a project: what was decided, on what day, by which one person or body, and why. Five tabs: Read me, Summary, Log, Other files and People.
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 22 Oct 2026. Clear the white cells to start your own.
Where to start
Start on People: the people and bodies who decide, then who decides each gate. Then log each decision on the day it's made. A small team can keep to Log and People.
Filling it in
1 | On People, add each person who decides something on this project, with their role, and each body, with its members and the one person who signs for it.
2 | Under Gates on People, pick who decides each gate, copied from the gate map. Leave a gate blank where the map's is blank.
3 | On Summary, type the project's Name and Sits under as the Register has them, pick its Owner, and type the day you're reviewing on in As of.
4 | On Log, add each decision in the next empty row on the day it's made: the Next Id from Summary, the Date, the decision in a sentence, who decided it, and why.
5 | Pick the Gate when a gate was decided. Type the other files' Ids in Record elsewhere, and set Kept in when the program keeps the record.
6 | Read the seven checks on Summary, and fix every row whose Row check shows △.
7 | When a decision is overturned, add a new row and type the old row's Id in Replaces.
DECISIONS
A row is one decision that happened, dated the day it happened. A question still waiting for an answer goes in the status report until someone decides it.
A signing is a decision when it commits money or accepts work. A status changing, such as a criterion going from Open to Met, isn't one.
Two decisions made the same day by the same person can share a row.
Once the person who decided has seen a row, leave it as it is. When the decision is overturned, the new row's Replaces names it, and the old row shows Replaced by.
DECIDERS
Decided by is one person, or one body, picked from People. A body is a board that decides together, with its members and the one person who signs for it. Never type a team as a body; name the person who decided.
People writes each name the way the Register writes an Owner, Anders (Engineering Manager), from Name and Role. Log picks names from there, so type each one once.
A gate decision is made by the one person the gate map names for that gate. Copy each gate's Decides from the gate map onto People.
Change a gate's Decides only for a gate not yet decided. Check 4 reads the name as it is now, so a change fails the rows already logged for that gate.
Owning a criterion, reviewing a gate or editing a file doesn't make someone the decider.
RECORDS IN OTHER FILES
Record elsewhere holds the Ids other files give the same decision, separated by commas: CH-1 in the change log, C-02 in acceptance and sign-off, M-04 in the program workbook, RACI v1.
When the program charter or the program workbook keeps a decision, such as the Investment decision or a Program board decision, it still gets a row here. Set Kept in to that file and name the record.
Other files is optional, and hidden in the blank file. Unhide it to use check 7: type a line for each change, waiver or gate decision another file shows, in that file's words, and it finds its row on Log by Id or gate name.
READING THE MARKS
△ | A check found something, and the words say what. Filter Row check on Log on △ to list the rows.
○ Clear | The check found nothing.
Not done | Nothing is logged yet, so the check has nothing to test.
Not used | Other files is empty, so check 7 has nothing to read. It isn't a failure, and the line at the top of Summary doesn't count it.
CHECKS
Summary runs seven checks on the rows on Log, in the order below. Each result names the first row that fails, and Row check on Log lists everything wrong with each row.
1 | A decision without one named decider: Decided by isn't exactly one name from People column D, or it names a body with no members or nobody who signs for it.
2 | A decision with no reason or evidence: Why or evidence is blank, under three words, or opens with Above, See above, As above, Same as above, As agreed, TBD or N/A.
3 | A decision with no date or a date after As of: Date is blank, isn't a date, or falls after As of on Summary.
4 | A gate decision not made by that gate's decider: Gate is picked and Decided by isn't the name People gives for it, or People gives nobody. A Decision that opens with a gate's name and a colon, such as Readiness: Go, needs its Gate picked.
5 | A Replaces that names no earlier decision: Replaces holds this row's own Id, an Id that isn't on Log, or a row dated after this one.
6 | A decision kept in another file with no record named: Kept in is Program charter or Program workbook, and Record elsewhere is blank.
7 | A change another file shows that has no decision here: a line on Other files whose Id or name is in no row's Record elsewhere or Gate.
LIMITS
Log holds 150 rows, People 20 names, and Other files 40 lines.
Check 2 counts words. It can't tell a reason from a status: Waiting on the other signatures passes.
The file reads only what you type into it. It never opens another file, so check 7 finds only what someone typed on Other files.
Checks 5 and 6 stay clear until someone uses Replaces or Kept in.
A row doesn't say who typed it or when.
THE WORKING
Grey cells are worked out from what you type, and locked so they aren't typed over. There's no password.
The working is in hidden columns: T to AD on Log, each with a header, F on Other files, and K on Summary, labelled in J. Unhide them to read it.
Rows can't be inserted, deleted or sorted, so every row stays counted. Type each decision in the next empty row, in date order.
YOUR LOGO
The FRQZ logo is at the top of each tab. To use your own, delete it and insert your logo in the same place.
RELATED FILES
The status report, the cutover workbook and the project close cite rows by their DL- Id, so keep each Id for good.
A decision the status report says is needed becomes a row here on the day it's made. The cutover workbook cites the Readiness, Go/no-go and Handover accepted rows.
Anyone who opens this file sees every row. To share it with someone outside the company, send them their rows, not the file.
An assistant can check the log for you. The brief is in frqz-decision-log-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results. It never types a decider, a date or a reason.
ABOUT THIS EXAMPLE
Hollins Software is a made-up software company. Everyone in it is made up too.
This is the decision log for Billing Engine Rewrite, as of 22 Oct 2026, with the twelve decisions made from 5 Mar to 22 Oct 2026. It fails three of the seven checks on purpose. The other four are clear.
Check 1 | DL-08, the signing of acceptance criteria v2 with CH-3, has two names in Decided by, Anders and Rhys, so no one person is named as deciding it.
Check 2 | DL-10, on who owns how invoices move to the new engine (CH-4), gives Above as its reason.
Check 7 | C-06's Pass line was loosened on 15 Oct 2026, from 0 severity 2 defects to 3 or fewer. Other files lists the change from acceptance and sign-off, and no row here records it.
The Program board decides DL-09 and DL-12, with Hugo signing for it, so both pass check 1.
Handover accepted has nobody in Decides on People, because nobody has agreed who decides it. No row uses that gate yet, so no check fails on it.
DL-03's reviewer is Anders, who also decided the gate. That is the gate map's planted failure. This log records it and doesn't check reviewers.
As of on Summary is 22 Oct 2026, so the results stay as they are. Clear it and the checks count from today.

## Summary
Summary (Example) |  |  |  | Decisions logged
Decisions replaced
As of, as the checks use it
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 22 Oct 2026. Clear the white cells to start your own. |  |  |  | Kept in another file
PROJECT |  |  |  | Other files lines with no row on Log
NAME | Billing Engine Rewrite |  |  | Other files lines typed
SITS UNDER | Billing and Payments Program
OWNER | Anders (Engineering Manager)
AS OF | 2026-10-22
COUNTS
DECISIONS LOGGED
KEPT IN ANOTHER FILE
LATEST DECISION
NEXT ID
CHECKS
Check | Result | First at | What to do
A decision without one named decider |  |  | Ask who decided it and type one name. For a body, give its members and who signs for it on People.
A decision with no reason or evidence |  |  | Ask the person who decided it for the reason, and type it.
A decision with no date or a date after As of |  |  | Type the day it was decided. A decision still to come isn't a row yet.
A gate decision not made by that gate's decider |  |  | Pick the gate in Gate. Then make Decided by the name People gives for that gate, copied from the gate map.
A Replaces that names no earlier decision |  |  | Fix the Id in Replaces so it names an earlier row.
A decision kept in another file with no record named |  |  | Name the record in Record elsewhere, such as M-04 or Program charter edition 1.
A change another file shows that has no decision here |  |  | Log the decision as a row, or take the line off Other files if it wasn't a decision.
Note on A12: Rows on Log with anything typed in columns A to I.
Note on B13: Rows that a later row overturns through Replaces.
Note on A14: Rows whose Kept in is Program charter or Program workbook. That file keeps the record.
Note on A15: The latest Date on Log.
Note on A16: The Id for the next row: the highest number used, plus one. Never reuse an Id.
Note on C19: The Id of the first row that fails. For the last check, the first line on Other files with no row.

## Log
Log (Example)
Id | Date | Decision | Decided by | Why or evidence | Gate | Record elsewhere | Kept in | Replaces | Replaced by | Row check | Row in use (1 or 0) | Replaced by a later row (1 or 0) | Kept in another file (1 or 0) | Ids and gate, for matching Other files | Fails check 1 (1 or 0) | Fails check 2 (1 or 0) | Fails check 3 (1 or 0) | Fails check 4 (0; 1 wrong decider, 2 nobody set, 3 gate not picked) | Fails check 5 (1 or 0) | Fails check 6 (1 or 0) | Id number
DL-01 | 2026-03-05 | Program Investment decision, tranche 1: Billing Engine Rewrite's share of the envelope is 780,000. | Priya (CTO) | Evidence looked at for the Investment decision, in the program charter, edition 1. |  | Program charter edition 1 | Program charter
DL-02 | 2026-03-12 | Start: Go. | Priya (CTO) | Business case review by Tomasz (PMO Head), 9 Mar 2026, passed. | Start
DL-03 | 2026-06-12 | Plan baselined: Go. | Anders (Engineering Manager) | Plan and estimate review, 9 Jun 2026, passed; reviewer Anders. | Plan baselined
DL-04 | 2026-06-12 | C-02, the old engine's tax export check, is waived. | Hugo (Program Manager) | The US tax rules were carried over and other countries' rules are left out of the first cutover, so the export isn't needed. |  | C-02
DL-05 | 2026-06-12 | At the first cutover the new engine carries the US tax rules and leaves out other countries' rules. | Anders (Engineering Manager) | Invoice Tax Rules wasn't accepted yet. M-04 wrote the split down again on 8 Oct 2026.
DL-06 | 2026-09-09 | The RACI is agreed (version 1). | Anders (Engineering Manager) | First agreed 9 Sep 2026, confirmed 10 and 11 Sep. |  | RACI v1
DL-07 | 2026-09-21 | Changes beyond the Owner's limit go to the sponsor, not Hugo (CH-1). C-04's test moves to a full copy of the customer records (CH-2). | Anders (Engineering Manager) | Changes beyond the limit are the sponsor's call, and with no sponsor named nobody can approve one yet (CH-1). CH-2 adds testing at no cost, absorbed in item 2, and moves no date. |  | CH-1, CH-2
DL-08 | 2026-09-28 | Acceptance criteria v2 is signed, and the invoice layout gains the fields Partner Portal Launch needs (CH-3). | Anders (Engineering Manager); Rhys (Finance Operations Lead) signs v2 | Mei (Product Manager) needs the fields by January 2027 for Partner Portal Launch. No cost, absorbed in item 1.1. |  | Acceptance criteria v2, CH-3
DL-09 | 2026-10-08 | M-04: the tax rules split in DL-05 is written down now that Invoice Tax Rules is accepted. | Program board | The split was already in the baseline. The program workbook holds the record. |  | M-04 | Program workbook
DL-10 | 2026-10-14 | Engineering owns how invoices move to the new engine, not Hugo (CH-4). | Anders (Engineering Manager) | Above |  | CH-4
DL-11 | 2026-10-22 | Project charter v1 is signed by the Owner. | Anders (Engineering Manager) | Waiting on the other signatures. |  | Project charter v1
DL-12 | 2026-10-22 | Customers outside the US and on annual contracts get the second-wave notice before 1 Feb 2027. | Program board | Program board notes of 22 Oct 2026, line 10. |  | Program board notes 22 Oct
Note on J3: Worked out: the row that overturns this one, if any.
Note on K3: Worked out: everything wrong on this row. Filter on △ to list them.

## Other files
Other files (Example)
CHANGES IN OTHER FILES
Where | Id or name | Date | What | Row on Log | No row on Log (1 or 0)
Change log | CH-1 | 2026-09-21 | Changes beyond the Owner's limit go to the sponsor
Change log | CH-2 | 2026-09-21 | C-04's test on a full copy
Change log | CH-3 | 2026-09-28 | Invoice fields for Partner Portal Launch
Change log | CH-4 | 2026-10-14 | Engineering owns how invoices move
Gate map | Start | 2026-03-12 | Decided Go
Gate map | Plan baselined | 2026-06-12 | Decided Go
Acceptance and sign-off | C-02 | 2026-06-12 | Tax export check waived
Acceptance and sign-off | Acceptance criteria v2 | 2026-09-28 | Signed by Anders and Rhys
Program workbook | M-04 | 2026-10-08 | Tax rules split written down
Program board notes | Program board notes 22 Oct | 2026-10-22 | Second-wave notice before 1 Feb
Acceptance and sign-off | C-06 | 2026-10-15 | Pass line loosened: severity 2 from 0 to 3 or fewer
Note on E5: Worked out: the row on Log whose Record elsewhere or Gate holds this Id or name.

## People
People (Example)
DECIDERS
# | Name | Role | As written | Kind | Members | Signs for | Row check | Placeholders the second check refuses
| Priya | CTO |  | Person |  |  |  | above
| Anders | Engineering Manager |  | Person |  |  |  | see above
| Hugo | Program Manager |  | Person |  |  |  | as above
| Rhys | Finance Operations Lead |  | Person |  |  |  | tbd
| Program board |  |  | Body | Hugo (Program Manager), Anders (Engineering Manager), Rhys (Finance Operations Lead) | Hugo (Program Manager) |  | n/a
as agreed
same as above
GATES
| Gate | Decides
| Start | Priya (CTO)
| Plan baselined | Anders (Engineering Manager)
| Build complete | Anders (Engineering Manager)
| Readiness | Anders (Engineering Manager)
| Go/no-go | Priya (CTO)
Handover accepted
| Close | Priya (CTO)
Note on D5: Worked out: Name with Role in brackets, the way the Register writes an Owner. Log picks names from here.
Note on H5: Shows △ when a name is used twice, Kind is blank, or a body lacks members or a signer.
Note on B29: The gate map's seven gates, locked so the names match it.
Note on C29: The one person who decides each gate, as the gate map has it. Blank where the map's is blank. Change it only for a gate not yet decided.