Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of Fri 28 May 2027. The last page says which review questions it fails on purpose.

# Handover and ownership

Billing Engine Rewrite

| Name | Billing Engine Rewrite |
| --- | --- |
| Sits under | Billing and Payments Program |
| Owner | Anders (Engineering Manager) |
| System | The new billing engine, live from Sun 13 Dec 2026 |
| Takes it over | Rhys (Finance Operations Lead) Noor (Support Lead) |
| Decides | Rhys (Finance Operations Lead) |
| Named by | Priya (CTO), Thu 19 Nov 2026 |
| Handover accepted | Fri 28 May 2027 |
| Planned finish | Wed 30 Jun 2027 |
| Version | v1 |
| Dated | Fri 28 May 2027 |
| Status | Signed |
| Kept after close by | Rhys (Finance Operations Lead) |
| Current copy | Finance Operations folder / Billing engine / Handover and ownership |

# 1. Ownership

| Work | Owned by | Backup | Escalate to | From |
| --- | --- | --- | --- | --- |
| Monthly invoice run | Rhys (Finance Operations Lead) | None named | Anders (Engineering Manager) | Wed 3 Feb 2027 |
| Month close and ledger export | Rhys (Finance Operations Lead) | None named | Anders (Engineering Manager) | Fri 8 Jan 2027 |
| Tax rule list | Rhys (Finance Operations Lead) | None named | Anders (Engineering Manager) | Thu 4 Feb 2027 |
| First two lines of billing questions | Noor (Support Lead) | None named | Anders (Engineering Manager) | Mon 26 Apr 2027 |
| Fixing billing defects, in Engineering's normal backlog | Anders (Engineering Manager) | None named | Priya (CTO) | Mon 26 Apr 2027 |
| Watching the old engine, read-only, to the end of its licence | Rhys (Finance Operations Lead) | None named | Anders (Engineering Manager) | Mon 14 Dec 2026 |

# 2. Materials

| Item | Where it is | Kept by |
| --- | --- | --- |
| Runbook v3 | Support wiki / Billing / Runbook v3 | Noor (Support Lead) |
| Rollback steps | Support wiki / Billing / Rollback steps | Noor (Support Lead) |
| 12-case and 40-account test packs | Engineering repository / billing-engine / test-packs | Anders (Engineering Manager) |
| Ledger export specification | Finance Operations folder / Billing engine / Ledger export | Rhys (Finance Operations Lead) |
| Training slides |  | Noor (Support Lead) |
| Build agent instructions and access list | Engineering repository / billing-engine / build-agent | Anders (Engineering Manager) |

# 3. Outside contacts

| Question about | Outside party | Our contact |
| --- | --- | --- |
| The connection to the Payments processor | Payments processor (vendor) | Anders (Engineering Manager) |
| The Partner Portal's use of the new invoice fields | Partner Portal Launch, Mei (Product Manager) | Anders (Engineering Manager) |
| The old engine's hosting contract | The old engine's hosting provider | Rhys (Finance Operations Lead) |

# 4. People

| Person | Role in the project | Last day on the project | Passed on to |
| --- | --- | --- | --- |
| Esi (Finance Operations Analyst) | Reconciled the opening balances and prepared December's close | Fri 18 Dec 2026 | Rhys (Finance Operations Lead) |
| Backend engineer 1 | Build and cutover steps | Mon 18 Jan 2027 | Anders (Engineering Manager) |
| Backend engineer 2 | Build and cutover steps | Mon 18 Jan 2027 | Anders (Engineering Manager) |
| Backend engineer 3 | Build and cutover steps | Mon 18 Jan 2027 | Anders (Engineering Manager) |
| Build agent | Built and tested the engine for Anders | Mon 18 Jan 2027 | Anders (Engineering Manager) |
| Anders (Engineering Manager) | Owner | Mon 28 Jun 2027 |  |
| Rhys (Finance Operations Lead) | Takes it over; accepted the billing deliverables | Mon 28 Jun 2027 |  |
| Noor (Support Lead) | Takes it over for support; accepts D5 | Mon 28 Jun 2027 |  |

# 5. Open items

| Item | Owner | Due | Kept in |
| --- | --- | --- | --- |
| The new engine's running cost, 140,000 a year, is in no budget line | Rhys (Finance Operations Lead) |  | RAID log R3 |
| 150 customers still to move: 20 in May, 130 in June | Anders (Engineering Manager) | Mon 28 Jun 2027 | Cutover workbook, Rollout |
| Switch off the old engine's licence and hosting | Finance Operations | Fri 31 Dec 2027 | Project charter, Not doing |
| Objective 3's reading on the quarter to 30 Sep 2027 | Hugo (Program Manager) | Thu 30 Sep 2027 | Program workbook, Benefits |
| First read of Cheaper to run billing | Rhys (Finance Operations Lead) | Fri 30 Jul 2027 | Program workbook, Benefits |
| No backup named for any owner in Ownership | Anders (Engineering Manager) | Fri 4 Jun 2027 | This handover, Ownership |

# 6. Acceptance

| Criterion | Owner (says it's met) | Status | Evidence | Met on |
| --- | --- | --- | --- | --- |
| Finance Operations has closed a month on the new engine | Rhys (Finance Operations Lead) | Met | Finance Operations folder / Billing engine / Month close: December closed Fri 8 Jan 2027, and January to April since, five closes | Fri 8 Jan 2027 |
| Support has handled billing tickets for four weeks without the build team | Noor (Support Lead) | Met | Support ticket report, Mon 26 Apr to Fri 21 May 2027, 20 working days: 212 tickets, 9 sent to Engineering and fixed in the normal backlog | Fri 21 May 2027 |
| The runbooks are in the support team's wiki | Noor (Support Lead) | Met | Support wiki / Billing / Runbook v3 | Fri 14 May 2027 |
| Every invoice in the first live run matches the finance ledger | Rhys (Finance Operations Lead) | Met | Finance Operations folder / Billing engine / Month close: December run against the ledger, totals match to the cent, 0 unexplained differences (C-09) | Fri 8 Jan 2027 |

# 7. Versions

A change to Ownership, Acceptance, Sign-off, Takes it over or Decides makes the next version, v2, and everyone in Sign-off signs again. A corrected place, contact, Due or typo is v1.1: write it here with Re-signed No.

| Version | Date | What changed | Decided by | Re-signed |
| --- | --- | --- | --- | --- |
| v1 | Fri 28 May 2027 | First issued and signed | Anders (Engineering Manager) | Yes |

# 8. Sign-off

| Role | Name | What signing means | Signature | Date | Version signed |
| --- | --- | --- | --- | --- | --- |
| Owner | Anders (Engineering Manager) | I hand this over as written. | Anders | Fri 28 May 2027 | v1 |
| Takes it over | Rhys (Finance Operations Lead) | I've read what I'm taking over, and I accept it. | Rhys | Fri 28 May 2027 | v1 |
| Takes it over | Noor (Support Lead) | I've read what I'm taking over, and I accept it. I also accept D5. | Noor | Fri 28 May 2027 | v1 |
| Decides Handover accepted | Rhys (Finance Operations Lead), also signs as Takes it over | I decide that the handover is accepted. | Rhys | Fri 28 May 2027 | v1 |

A signature applies to the version beside it. Status is Signed only when every section is filled in and every row here has a name, a signature, a date and the current version. None named in Backup counts as filled in, and so does a blank Passed on to for someone still on the project after Handover accepted.

# Review questions

Before anyone signs, someone who didn't write this handover asks these eight questions: the person taking the work over, or the portfolio manager. Until everyone has signed, Who signed reads Not yet. Anything else that isn't a yes goes back to the Owner before signing.

| # | Question | Yes when |
| --- | --- | --- |
| 1 | Same names. Do the names match the Register, the charter and the gate map? | Name, Sits under and Owner are the Register's, letter for letter, and Planned finish is its date. Takes it over names the charter's people. Decides and Handover accepted are the gate map's. Every criterion in Acceptance is the gate map's or the acceptance file's, word for word, and none that falls at Handover accepted is missing. |
| 2 | One owner each. Is every owner one named person? | Each Owned by, Escalate to, Kept by, Our contact and Open items Owner is one Name (Role) with nothing after it. Each Backup is one other person, or None named with a row in Open items. No team owns anything. |
| 3 | Where things are. Could someone new find everything the project leaves? | Every Materials row has a Where it is that is a link or a folder path of two parts or more, and a Kept by who owns a row in Ownership. The runbook, the rollback steps, each training item the charter promised and any agent's instructions have a row. |
| 4 | Evidence for acceptance. Does every criterion say where to see it's true? | Every Acceptance row has Evidence and a Met on, and no Met on is after Handover accepted. A criterion that names a period has Evidence that covers it, counted in working days, Monday to Friday: four weeks is 20. Whether the evidence proves the criterion is for the person signing. |
| 5 | What's left open. Does every open item have an owner and a day? | Each Open items row has one Owner, and a Due that is a weekday after Handover accepted or Date TBD (gated on …) naming what it waits for. Every RAID line still open has a row, and so do any customers still to move. |
| 6 | Who's leaving. Has everyone who's leaving passed on what they know? | Everyone in the charter's team or on the RACI whose last booked day is on or before Handover accepted has a Passed on to: one person still on the project. Everyone in the charter's team has a row in People, and every Last day is a weekday. |
| 7 | Who signed. Is it complete, and has everyone signed this version? | Sign-off has a row for the Owner, each person in Takes it over and the person in Decides, each with a name, a signature, a date and the current version, and every section is filled in. While Status is Draft or Waiting to sign, the answer is Not yet. Once Status is Signed, anything missing is a no. |
| 8 | The dates agree. Do the dates agree with each other? | Handover accepted is on or before the Planned finish. Every From in Ownership is on or before Handover accepted. Each Sign-off date falls on or after the latest Met on and on or before Handover accepted. Every printed weekday matches its date. |

# About this Example

Hollins Software is a made-up software company. Everyone in it is made up too.

This is the handover for Billing Engine Rewrite on Fri 28 May 2027, the day Handover accepted is decided. The new engine has been live since Sun 13 Dec 2026, and 150 customers are still to move.

It fails questions 2, 3, 5 and 7 on purpose, and passes 1, 4, 6 and 8.

| 2 One owner each | Open items row 3, switching off the old engine's licence and hosting, has a team as its Owner: Finance Operations. |
| --- | --- |
| 3 Where things are | Training slides, in Materials, has no Where it is. Noor signed I also accept D5 over that blank. |
| 5 What's left open | Open items row 1, the new engine's running cost, has no Due, though it waits on Finance Operations' FY28 budget request, which isn't written yet. |
| 7 Who signed | Status is Signed while Materials row 5 and Open items row 1 are blank. |

Rhys (Finance Operations Lead) decides Handover accepted and also takes the billing work over. The person taking the work over is usually the one who accepts it, so the assistant asks about it and doesn't fail it.

No owner in Ownership has a backup. Open items row 6 has Anders finding them by Fri 4 Jun 2027, so question 2 passes on that.

Backend engineer 1, 2 and 3 stand for three named people. A real handover names them.

## Before you start

A handover says who keeps each piece of the work going after the project, where everything they need is kept, and what is still open. It's signed on the day Handover accepted is decided, by the Owner, each person who takes the work over and the person who decides the gate.

Name, Sits under and Owner are copied from the project's row on the Register, letter for letter, and Planned finish is its date, written with the weekday. Takes it over is copied from the project charter. Decides and Handover accepted are copied from the gate map. Acceptance copies each criterion that falls at Handover accepted word for word, from the gate map and from the acceptance and sign-off file.

Write every person as Name (Role), one person to a cell. A team never owns anything: name the one person who answers for it.

Once it's signed, keep this file as it was signed. Changes go into the copy named in Current copy, and Versions says when a change needs signing again.

Before anyone signs, someone who didn't write the handover asks the eight review questions after Sign-off: the person taking the work over, or the portfolio manager.

An assistant can check it for you. The brief is in frqz-handover-agent-brief.txt, beside this file.

To use your own logo, right-click the FRQZ logo at the top right and choose Change Picture. In Google Docs, choose Replace image.