## Read me
Portfolio workbook · Full (Example)
A record of every program and project in one portfolio, kept by hand, with the requests waiting to start and who is free. Nine tabs: Read me, Portfolio, Register, Funding, Steering, Checks, Board, Intake and Capacity.
Example. Hollins Software and everyone in it are made up. Clear the white cells to start your own.
Where to start
Start with the Register and the Board. Add Intake when requests start to queue, and Capacity when people are double-booked. Leave those two empty until then; their checks stay clear.
Filling it in
1 | On Portfolio, type the portfolio's name, director, manager and status. If a steering group meets, pick how often, and add a First review date if it hasn't met yet.
2 | On Register, add a row for every program and every project, with Sits under, Status and Owner. On projects, pick an Approach in the last column, after Check.
3 | Type Planned finish, Latest forecast and Forecast spend, and Budget on programs and on projects directly under Portfolio. On Funding, type the envelope, its currency and where it came from.
4 | Read Health and Check on Register, and the Checks tab for every result. Write a Variance note on every Amber or Red row, ending with your name.
5 | Before each steering meeting, type Last checked on every row whose owner has just checked it, and Owner's view on every Amber or Red row. Then read the Board and write its two commentary lines. The director signs it once the steering group has seen it.
6 | When requests start to queue: on Intake, agree the criteria and weights and type the date. Add each request as it arrives and score it. Read Recommended rank and the two Fits columns, then type the decision, who made it, when, and why.
7 | When people start to be double-booked, list them on Capacity with any time away, and book their days on each current row, one line per run of weeks. Read Who is free before you take on new work.
8 | After each steering meeting, add it under Meetings on Steering. Then log its decisions, each with one accountable person and who recorded it, and any actions with an owner and a due date.
YOUR LOGO
The FRQZ logo is in cell A1 on every tab. To use your own, delete it and insert your logo in A1, on each tab.
NAMES
Type each person's name the same way every time, with a role in brackets if you like: Priya (CTO). Names are matched exactly as typed, so Priya and Priya (CTO) count as two people.
READING THE MARKS
■ Red | Late, or over budget, by more than your limit. The limits are on the Checks tab, and you can change them.
◧ Amber | Late, or over budget, within your limit.
□ On track | A date or a budget was read, and nothing is late or over.
Not read | Nothing to judge from yet. A project with a Planned finish and no Latest forecast reads Not read; if the date hasn't moved, type it again as the forecast. A Sprint project always reads Not read.
Not counted | Proposed, Completed or Terminated. Left out of every count.
△ | A check found something, and the words say what. Filter the Check column on △ to list them all.
○ Clear | The check found nothing.
HOW HEALTH IS WORKED OUT
Dates: a project is Red once its Planned finish has passed while it's still Active or Paused. Otherwise a Latest forecast past the plan by more than your limit is Red, and a smaller slip is Amber.
Money: spend over Budget by more than your limit is Red, and a smaller overrun is Amber. A program's spend is its projects' Forecast spend added up.
Health is the worse of the two. A program with no Latest forecast uses the latest among its projects. Its colour never hides theirs: Projects inside counts its Red and Amber projects beside it.
GREY COLUMNS
Grey cells are worked out from what you type. Don't type over them: a typed value replaces the formula.
Owner's current rows counts the Active and Paused rows that carry each owner's name, so you can see who's spread thin. It sets no limit.
THE BOARD
The Board is worked out from the Register, like Health. You type only its two commentary lines, the Kept in cell and the signature.
The first time, type Last checked on every row you've checked. As soon as one row has a date, every current row without a recent one counts as not checked.
Last checked: the day the owner last read this row's dates, forecast spend and note and said they still stand. Type it again at each check.
Owner's view: the owner's answer to whether the date and the cost will hold. It shows beside Health and never changes it.
To close a row, change its Status to Completed or Terminated. Don't delete it: the Board lists what left since the last review, and a deleted row can't be listed.
Its only settings are the two numbers on its second page. 35 days is where they start; change it to suit.
An assistant can prepare the Board for you. The brief is in frqz-portfolio-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results.
INTAKE AND SCORING
Score: the weighted criteria, 20 to 100. Recommended rank: the order the scores suggest for the queue. Fits: whether what's left covers this request and every one ranked above it.
The score leaves out cost and effort. The two Fits columns test them against the money left and the free person-days, in rank order.
An accepted request is shown to fit when it fits the money and the people, or when Gives way names an Active project that slows or stops for it. It needs a cost and an effort either way.
Agree the criteria and weights before anyone scores, and type the date. The check can show only that a date was typed and that no decision is dated before it.
Fits the money tests against money not yet given to any program. For work inside a program, ask that program's owner.
Free person-days is typed. Capacity's figure for the next 13 weeks shows beside it. That figure counts anyone whose project has no booking as free, so it's the most you could have.
Give the Register row the same name as the request. To rename a project or an objective, use Find and Replace on every tab.
An accepted request has 14 days to get its Register row before the check flags it. Change the number on the tab to suit.
Record intake decisions here, and the steering group's other decisions on Steering.
Intake runs five checks of its own. Their count is on the Checks tab, as Intake checks.
An assistant can prepare the intake queue for you. The brief is in frqz-intake-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results.
CAPACITY
Capacity shows who is free in each of 13 weeks, starting from First week. Move First week forward as the weeks pass. Bookings and Time away keep their own dates.
Everything on Capacity is in days a week. A person with 4 usual days and 3 booked has 1 free.
People lists whoever does the work. A first name is enough; it doesn't have to match Owner on the Register.
Each Bookings line is one person on one Register row, from a first Monday to a last, at the same days a week. When the pace changes, end the line and start another. Book each day once, on the program or on one of its projects.
Book days on a Proposed row to see who would go over if it were approved: the last column of Who is free shows it. The line counts against nobody until the row is Active.
Everyone and Outside team are kept for two uses. On Time away, Everyone takes the days off every person, as for a public holiday. On Bookings, Outside team means a vendor or contractor staffs the row: it uses nobody's days, and the row counts as staffed.
Free days, at most, is a ceiling. A person whose project has no booking yet looks free, and so does a week nobody has booked.
Someone booked for all their days shows as over in any week they're away. Split the line and book fewer days that week, or leave the finding.
Time away holds dates and days, never a reason. Anyone who opens the file can read it.
Clear a line to remove it. Don't insert or delete rows on Capacity: each table sits at fixed rows. If two Register rows share a name, bookings go to the first.
Capacity runs four checks of its own, at the top of the tab. The Checks tab shows how many fail, apart from its twelve.
An assistant can read Capacity for you. The brief is in frqz-capacity-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results.
THE STARTER WORKBOOK
A small team that wants fewer tabs can use the Starter workbook. Its Register columns A to L and Intake columns A to R match this one, so rows paste across.
To bring rows in from the Starter, paste Register columns A to L, then AJ to AK, as two pastes. One paste of A to AK would clear Approach.
ABOUT THIS EXAMPLE
Hollins Software is a made-up software company. Everyone in it is made up too.
Four checks fail on purpose. Billing and Payments Program has no sponsor. Support Tooling Replacement sits under a program that isn't on the sheet, and Internal Wiki Cleanup is paused, so still current, outside the portfolio. The budgets add up to 30,000 USD more than the envelope. And the 15 Oct 2026 decision was recorded by the manager, where decisions are the director's to record.
Support Tooling Replacement is a Sprint project, so its Health reads Not read. The other eight checks are clear. The dates are in 2026 and 2027, so the marks will change as time passes.
The Board fails one check on purpose: Data Migration Wave 2 is Red and its owner says it will hold. Its other two checks are clear until the dates pass. The forecast check starts failing on 31 Oct 2026 and the Last checked one on 17 Nov 2026.
Intake fails two checks on purpose. Audit Evidence Portal and Support Chat Upgrade were accepted though neither fits the money, and nothing running gives way for them.
Audit Evidence Portal names Internal Wiki Cleanup, which is paused. Support Chat Upgrade names nothing.
Audit Evidence Portal still has no Register row three weeks after it was accepted, and Invoice Tax Rules is on the Register without its objective.
The budgets already pass the envelope by 30,000, so no request fits the money until something stops. Free person-days is Capacity's figure for the same 13 weeks, 239.
The other three checks are clear. On 30 Oct 2026 Support Chat Upgrade also fails the Register check, when its 14 days run out. The count stays at two.
Capacity fails three of its four checks on purpose. Imani is booked for 6 days in the week of 26 Oct and has 5. One Bookings line names Rai, who isn't on People: it's a typo for Raj. Billing Engine Rewrite is Active with nobody booked, so Anders looks free in every week.
Lena's 2 days a week on Invoice Tax Rules are pencilled in; if that row were approved, Lena would be over in 6 weeks. Lena's booking drops to 4 days in the two holiday weeks. Priya, Tomasz, Dara and Hugo aren't on People, so they can't be booked.
The 13 weeks run from 19 Oct 2026 to 17 Jan 2027. No check reads today's date, so the results stay as they are; from 18 Jan 2027 the note beside First week says the weeks have passed.

## Portfolio
Portfolio (Example)
One portfolio per workbook. Type in the white cells; the grey ones are worked out.
Example. Hollins Software and everyone in it are made up. Clear the white cells to start your own.
THE PORTFOLIO
PORTFOLIO NAME | Product and Platform | What you call the work this workbook covers. Required.
DIRECTOR | Priya (CTO) | The person accountable for the portfolio's direction and benefits. A name, with a role in brackets if you like. Required.
MANAGER | Tomasz (PMO Head) | The person who runs it day to day and keeps the register. Can be the director. Required.
STATUS | Active | Where the portfolio is in its life. Blank counts as Active. Reviews are checked only while it's Active.
REVIEW CADENCE | Quarterly | How often the steering group reviews the portfolio. Leave blank if there isn't one.
FIRST REVIEW | 2026-01-15 | The date of the first review, while no meeting is logged on Steering. Optional.
LAST REVIEW |  | Worked out: the latest meeting date on Steering.
NEXT REVIEW |  | Worked out: Last review plus the cadence, or First review until a meeting is logged.
PEOPLE CHECK |  | Shows △ when the director or the manager isn't named.
REVIEW CHECK |  | Shows △ when the next review has passed, or a cadence is set with no review date.
COUNTS BY HEALTH |  | Programs and projects directly under Portfolio, one count each. A program's own projects are counted beside it on Register.
■ Red
◧ Amber
□ On track
Not read
CURRENT ROWS OUTSIDE THE PORTFOLIO |  | Active or Paused rows with Sits under set to Outside the portfolio. Left out of the counts above.
CHECKS |  | Every result is on the Checks tab.
OBJECTIVES
Objective | Owner | Measure and target | Target date | Linked rows
Cut the time to bring on a new customer | Priya (CTO) | Days from signed order to first live use: 21 | 2027-06-30
Pass the annual audit with no major findings | Imani (Security Lead) | Major findings at audit: 0 | 2027-02-26
Move all billing to the new engine before renewals | Hugo (Program Manager) | Share of invoices from the new engine: 100% | 2027-09-30

## Register
Register (Example)
Example. Hollins Software and everyone in it are made up. Clear the white cells to start your own.
Name | Level | Sits under | Status | Owner | Sponsor | Objective | Planned finish | Latest forecast | Forecast spend | Budget | Variance note | Health | Projects inside | Owner's current rows | Check | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Approach | Helper, worked out | Helper, worked out | Helper, worked out | Last checked | Owner's view | Current and in the portfolio (1 or 0) | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper
Customer Platform Modernisation | Program | Portfolio | Active | Dara (Program Manager) | Priya (CTO) | Cut the time to bring on a new customer | 2027-04-30 |  |  | 1100000 | [6 empty] | Portfolio | [17 empty] | 2026-10-19 | Will hold
Data Migration Wave 2 | Project | Customer Platform Modernisation | Active | Kofi (Delivery Lead) |  | Cut the time to bring on a new customer | 2027-02-26 | 2027-03-12 | 520000 |  | Schema fix agreed with the vendor; the new date holds only if it lands by 5 Nov. Kofi | [5 empty] | Outside the portfolio | [13 empty] | Waterfall |  |  |  | 2026-10-20 | Will hold
Billing and Payments Program | Program | Portfolio | Active | Hugo (Program Manager) |  | Move all billing to the new engine before renewals | 2027-06-30 |  |  | 900000 | [24 empty] | 2026-10-15 | Will hold
Billing Engine Rewrite | Project | Billing and Payments Program | Active | Anders (Engineering Manager) |  | Move all billing to the new engine before renewals | 2027-06-30 | 2027-06-30 | 780000 | [21 empty] | Waterfall |  |  |  | 2026-10-15 | At risk
Invoice Tax Rules | Project | Billing and Payments Program | Proposed | Hugo (Program Manager) | [26 empty] | Waterfall
Security and Compliance Program | Program | Portfolio | Active | Imani (Security Lead) | Priya (CTO) | Pass the annual audit with no major findings | 2027-01-29 |  |  | 350000 | [24 empty] | 2026-10-19 | Will hold
Penetration Test Remediation | Project | Security and Compliance Program | Active | Imani (Security Lead) |  | Pass the annual audit with no major findings | 2026-10-09 | 2026-10-30 | 40000 |  | Two criticals closed; the third needs a vendor patch. Imani | [19 empty] | Waterfall |  |  |  | 2026-10-21 | Will not hold
Laptop Encryption Rollout | Project | Security and Compliance Program | Active | Imani (Security Lead) |  |  | 2026-12-11 | 2026-12-16 | 120000 |  | Last two offices wait on courier delivery. Imani | [19 empty] | Waterfall |  |  |  | 2026-10-14 | At risk
Partner Portal Launch | Project | Portfolio | Active | Mei (Product Manager) |  |  | 2027-04-30 | 2027-04-30 | 85000 | 80000 | Contract testers cost more than planned; still within 10 percent. Mei | [19 empty] | Waterfall |  |  |  | 2026-10-12 | At risk
Support Tooling Replacement | Project | Support Ops Program | Active | Noor (Support Lead) |  |  | 2027-02-12 | 2027-02-12 | 70000 | [21 empty] | Sprint |  |  |  | 2026-10-08
Internal Wiki Cleanup | Project | Outside the portfolio | Paused | Noor (Support Lead) | [26 empty] | Waterfall |  |  |  | 2026-07-03
Vendor Risk Assessment | Project | Security and Compliance Program | Completed | Imani (Security Lead) |  |  | 2026-09-18 |  | 55000 | [21 empty] | Waterfall |  |  |  | 2026-10-21
Legacy Reporting Retirement | Project | Customer Platform Modernisation | Terminated | Kofi (Delivery Lead) |  |  |  |  | 40000 | [21 empty] | Waterfall |  |  |  | 2026-10-19
Formulas:
Helper, worked out = IF(OR([Helper, worked out]=0,[Planned finish]="",[Approach]="Sprint"),0,IF(AND([Level]="Project",[Planned finish]<TODAY()),3,IF([Helper, worked out]="",0,IF([Helper, worked out]<=[Planned finish],1,IF(NETWORKDAYS([Planned finish],[Helper, worked out])-1>IF([Level]="Program",Checks!$B7,Checks!$B6),3,2)))))
Board helper = IF(AND([Current and in the portfolio (1 or 0)]=1,[Last checked]<>""),MAX(0,TODAY()-[Last checked]),"")
Board helper = IF(OR([Current and in the portfolio (1 or 0)]=0,COUNT(AJ6:AJ305)=0),0,IF([Last checked]="",1,IF(TODAY()-[Last checked]>Board!$B40,1,0)))
Note on M5: Worked out. Don't type here.
Note on N5: Worked out. Don't type here.
Note on O5: Worked out. Don't type here.

## Funding
Funding (Example)
Example. Hollins Software and everyone in it are made up. Clear the white cells to start your own.
ENVELOPE
ENVELOPE | 2400000 | The total the portfolio may spend. Optional; leave it blank and the envelope check doesn't run.
CURRENCY | USD | The currency of every figure in this workbook. Pick one, or type another code.
SOURCE | FY27 plan, approved 30 Sep 2026 | Where the figure came from, such as a plan or a board decision, with its date.
SET BY | Priya (CTO) | Who set the figure, or last changed it.
BUDGETS GIVEN OUT |  | Every Budget on a row directly under Portfolio, Proposed rows left out. When a row closes, lower its Budget to what was spent.
LEFT IN THE ENVELOPE |  | The envelope minus budgets given out. Negative means over.
FORECAST SPEND, ALL PROJECTS |  | Forecast spend added up across this portfolio's projects, Proposed left out.
PROJECTS WITH NO FORECAST SPEND |  | Projects in that total with Forecast spend blank. While there are any, the figure above reads low.
ENVELOPE CHECK |  | Shows △ when budgets given out pass the envelope.
BUDGETS, WORKED OUT FROM THE REGISTER
Name | Budget | Level | Status | Forecast spend | Against budget
Note on E17: A program's figure is its projects' Forecast spend added up.
Note on F17: Forecast spend minus Budget. Negative means under.

## Steering
Steering log (Example)
Example. Hollins Software and everyone in it are made up. Clear the white cells to start your own.
Decisions |  |  |  |  | Meetings |  | Actions
Date | Decision | Accountable | Check | Recorded by | Meeting date | Attended | Meeting date | Action | Owner | Due
2026-04-16 | Fund Customer Platform Modernisation at 1,100,000 for the year | Priya (CTO) |  | Priya (CTO) | 2026-04-16 | Priya, Tomasz, Dara, Hugo, Imani | 2026-10-15 | Name a sponsor for Billing and Payments Program | Priya (CTO) | 2026-11-13
2026-07-16 | Pause Internal Wiki Cleanup until next year's planning | Priya (CTO) |  | Priya (CTO) | 2026-07-16 | Priya, Tomasz, Dara, Hugo, Imani, Anders | 2026-10-15 | Move Support Tooling Replacement under a real program or drop it | Tomasz (PMO Head) | 2026-11-13
2026-10-15 | Keep the Penetration Test Remediation plan date at 9 Oct and report against it | Imani (Security Lead) |  | Tomasz (PMO Head) | 2026-10-15 | Priya, Tomasz, Dara, Hugo, Imani

## Checks
Checks (Example)
Example. Hollins Software and everyone in it are made up. Clear the white cells to start your own.
LIMITS FOR RED
DAYS LATE BEFORE RED, PROJECTS | 5 | Working days a project may run past its Planned finish before it reads Red. Starts at 5; change it to suit.
DAYS LATE BEFORE RED, PROGRAMS | 10 | Working days a program may run past its Planned finish before it reads Red. Starts at 10.
OVER BUDGET BEFORE RED | 10% | How far spend may run over Budget before a row reads Red. A smaller overrun reads Amber. Starts at 10%.
ALL CHECKS
Check | Result | Where to look
A row with no owner |  | Register, Check column
A program with no sponsor |  | Register, Check column
Sits under, or a current row outside the portfolio |  | Register, Check column
Director or manager not named |  | Portfolio, People check
Budgets over the envelope |  | Funding, Envelope check
Budget on a row not directly under Portfolio |  | Register, Check column
Review overdue, or no review date |  | Portfolio, Review check
An objective with no owner |  | Portfolio, Objectives
An Amber or Red row with no variance note |  | Register, Check column
A decision without one accountable person |  | Steering, Decisions
A decision not recorded by the director |  | Steering, Decisions
A name used twice |  | Register, Check column
Board checks |  | Board, Board checks
Intake checks |  | Intake, Checks
Capacity checks |  | Capacity, Capacity checks

## Board
Board (Example)
Example. Hollins Software and everyone in it are made up. Clear the white cells to start your own.
1 Where it stands. Worked out from the Register's dates and money.
Health | Programs and direct projects | All current rows | Of those, not checked | Budget, programs and direct projects
■ Red
◧ Amber
□ On track
Not read
Total
Left in the envelope
2 Commentary, written by the director. Causes come from the owners' variance notes.
Since last review | Data Migration Wave 2 is Red. The schema fix is agreed with the vendor, and the new date holds only if it lands by 5 Nov. Since 15 Oct, Vendor Risk Assessment has been completed and Legacy Reporting Retirement terminated.
For the group to decide | Is the schema fix due by 5 Nov firm enough to keep Data Migration Wave 2 at 12 Mar 2027? Its owner says it will hold; the dates put it 10 working days late.
Name | Owner | Health | Owner's view | What the numbers show | Variance note
4 Before you trust the figures
Owner's view milder than the numbers
Left since the last review
Not on this page | Benefits, risks and progress against the objectives aren't recorded in this workbook. No figure on this page stands in for them. |  |  |  | Kept in: the risk register, held by the CTO's office.
Board checks
Signed by |  |  | On
Settings and detail
Not checked after (days) | 35
Look ahead (days) | 90
Board checks
Rows not checked
A forecast date has passed
Owner's view milder than the numbers
Objectives and the rows serving them. The workbook holds no reading of the measures, so no progress is shown.
Objective | Owner | Rows serving it | Red or Amber among them | Measure and target | Target date
Rows that left since the last review. A row shows here only if its Last checked date is after that review.
Name | How it left | Last checked | Budget | Forecast spend

## Intake
Intake and scoring (Example)
Example. Hollins Software and everyone in it are made up. Clear the white cells to start your own.
Scoring criteria. Agree them, and their weights, before anyone scores a request.
Criterion | Weight | What a 1 and a 5 mean | [40 empty] | Helper, worked out
Fit to objective | 30% | 1: serves an objective only loosely. 5: moves an objective's measure directly.
Value to customers | 30% | 1: no customer would notice. 5: a named customer or contract depends on it.
Urgency | 20% | 1: can wait a year. 5: a date we don't control falls inside the next quarter.
Needed by other work | 20% | 1: nothing depends on it. 5: running work can't finish without it.
TOTAL WEIGHT
AGREED BY | Priya (CTO)
AGREED ON | 2026-02-02
What's left for new work
LEFT IN THE ENVELOPE
FREE PERSON-DAYS | 239 | next 13 weeks
COST OF THE QUEUE
PERSON-DAYS IN THE QUEUE
DAYS TO GET ON THE REGISTER | 14
Checks
A decision dated before the criteria were agreed, or no date
A scored request with no objective from Portfolio
An accepted request not shown to fit
An accepted request that doesn't match the Register
A decision without who, when or why
Intake checks
Rows below the table
Requests. The queue is every scored request that hasn't started on the Register and isn't deferred or declined.
Request | Requested by | Received | Objective | Proposed owner | Estimated cost | Effort, person-days | Wanted start |  |  |  |  | Decision | Decided by | Decided on | Reason | Gives way | Register name | Score | Recommended rank | Fits the money | Fits the people | Days open | Check | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Running cost: this request and every one ranked above it | Running person-days: this request and every one ranked above it | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out
Data Migration Wave 2 | Dara (Program Manager) | 2026-01-12 | Cut the time to bring on a new customer | Kofi (Delivery Lead) | 480000 | 600 |  | 5 | 4 | 4 | 3 | Accept | Priya (CTO) | 2026-02-05
Penetration Test Remediation | Imani (Security Lead) | 2026-05-18 | Pass the annual audit with no major findings | Imani (Security Lead) | 40000 | 90 |  | 4 | 5 | 5 | 4 | Accept | Priya (CTO) | 2026-06-02
Invoice Tax Rules | Hugo (Program Manager) | 2026-09-14 | Move all billing to the new engine before renewals | Hugo (Program Manager) | 120000 | 160 | 2027-02-01 | 4 | 4 | 3 | 3 | Accept | Priya (CTO) | 2026-10-08 | Billing can't move to the new engine without the tax rules. | Partner Portal Launch
Single Sign-On for the Partner Portal | Mei (Product Manager) | 2026-10-02 | Cut the time to bring on a new customer | Mei (Product Manager) | 60000 | 80 | 2027-01-04 | 3 | 4 | 4 | 4
Usage-Based Billing Pilot | Hugo (Program Manager) | 2026-10-12 | Move all billing to the new engine before renewals | Hugo (Program Manager) | 200000 | 300 | 2027-03-01 | 4 | 5 | 2 | 2
Audit Evidence Portal | Imani (Security Lead) | 2026-09-21 | Pass the annual audit with no major findings | Imani (Security Lead) | 90000 | 120 | 2027-01-04 | 5 | 3 | 4 | 3 | Accept | Priya (CTO) | 2026-09-30 |  | Internal Wiki Cleanup
Support Chat Upgrade | Noor (Support Lead) | 2026-09-28 | Cut the time to bring on a new customer | Noor (Support Lead) | 45000 | 60 |  | 3 | 3 | 3 | 3 | Accept | Priya (CTO) | 2026-10-15 | Support needs it before the 1 January renewals.
Guided Setup Wizard | Mei (Product Manager) | 2026-10-09 | Cut the time to bring on a new customer | Mei (Product Manager) | 70000 | 100 | 2027-03-01 | 3 | 3 | 2 | 3
Self-Hosted Install Option | Dara (Program Manager) | 2026-08-03 | Cut the time to bring on a new customer | Dara (Program Manager) | 400000 | 500 |  | 4 | 3 | 1 | 1 | Defer | Priya (CTO) | 2026-09-17 | Needs Data Migration Wave 2 finished first. Look again in January.
Custom Report Builder | Noor (Support Lead) | 2026-08-10 | Cut the time to bring on a new customer | Noor (Support Lead) | 150000 | 220 |  | 2 | 2 | 1 | 2 | Decline | Tomasz (PMO Head) | 2026-09-03 | No customer could be named who needs it.

## Capacity
Capacity (Example)
Example. Hollins Software and everyone in it are made up. Clear the white cells to start your own.
Settings | [53 empty] | Days booked on this Register row | Active project with nobody booked (1 or 0) | Days pencilled on this Register row |  | Names for the Time away list | Names for the Bookings list | Lines and rows the tab can't read
FIRST WEEK | 2026-10-19 | [56 empty] | Everyone | Outside team
USUAL DAYS A WEEK | 5
Capacity checks
Someone booked for too many days
A line or row the tab can't read
An Active project with nobody booked
A booking past the forecast date
Who is free. Days each person has left in each week, after time away and bookings on current rows. Below 0 means over.
Person | Weeks over | Usual days |  |  |  | If Proposed rows are approved | [7 empty] | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper |  |  |  | Capacity helper
Free days, at most
Days over, all people
People. The people who can be booked, and the days a week each one works.
Person | Usual days a week | Row check |  |  |  |  | Capacity helper
Kofi
Lena
Anders
Raj
Imani
Sade
Mei | 4
Noor | 4
Time away. Leave and holidays, as days away in each week from one Monday to another. No reasons.
Person | From | To | Days away a week | Row check |  |  | Capacity helper
Everyone | 2026-12-21 | 2026-12-28 | 1
Kofi | 2026-11-09 | 2026-11-09 | 5
Bookings. One line per person, Register row and run of weeks. A line on a Proposed row is pencilled in and counts against nobody.
Register row | Person | From | To | Days a week | Line check |  | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper
Data Migration Wave 2 | Kofi | 2026-10-19 | 2026-11-02 | 2
Data Migration Wave 2 | Kofi | 2026-11-16 | 2027-01-11 | 2
Data Migration Wave 2 | Lena | 2026-10-19 | 2026-12-14 | 5
Data Migration Wave 2 | Lena | 2026-12-21 | 2026-12-28 | 4
Data Migration Wave 2 | Lena | 2027-01-04 | 2027-01-11 | 5
Data Migration Wave 2 | Raj | 2026-10-19 | 2026-12-07 | 2
Penetration Test Remediation | Imani | 2026-10-19 | 2026-10-26 | 3
Laptop Encryption Rollout | Imani | 2026-10-19 | 2026-10-19 | 2
Laptop Encryption Rollout | Imani | 2026-10-26 | 2026-12-14 | 3
Penetration Test Remediation | Sade | 2026-10-19 | 2026-10-26 | 3
Laptop Encryption Rollout | Sade | 2026-10-26 | 2026-12-14 | 2
Partner Portal Launch | Mei | 2026-10-19 | 2027-01-11 | 3
Support Tooling Replacement | Noor | 2026-10-19 | 2027-01-11 | 3
Invoice Tax Rules | Lena | 2026-11-16 | 2026-12-21 | 2
Partner Portal Launch | Rai | 2026-10-19 | 2026-11-09 | 2