## Read me
Portfolio workbook · Starter
A record of every program and project in one portfolio, kept by hand, with the requests waiting to start and who is free. Seven tabs: Read me, Portfolio, Register, Steering, Board, Intake and Capacity.
Where to start
Start with the Register and the Board. Add Intake when requests start to queue, and Capacity when people are double-booked. Leave those two empty until then; their checks stay clear.
Filling it in
1 | On Portfolio, type the portfolio's name, its director and its manager. If a steering group meets, pick how often in Review cadence.
2 | On Register, add a row for every program and every project. In Sits under, pick the program each project belongs to, or Portfolio, or Outside the portfolio.
3 | Type Planned finish and Latest forecast. If a date hasn't moved, type it in both. Add Forecast spend on projects, and Budget on programs and on projects directly under Portfolio.
4 | Read the Health and Check columns. Fix every row that shows △, and write a Variance note on every Amber or Red row, ending with your name.
5 | Before each steering meeting, type Last checked on every row whose owner has just checked it, and Owner's view on every Amber or Red row. Then read the Board and write its two commentary lines. The director signs it once the steering group has seen it.
6 | When requests start to queue: on Intake, agree the criteria and weights and type the date. Add each request as it arrives and score it. Read Recommended rank and the two Fits columns, then type the decision, who made it, when, and why.
7 | When people start to be double-booked, list them on Capacity with any time away, and book their days on each current row, one line per run of weeks. Read Who is free before you take on new work.
8 | After each steering meeting, log each decision and its one accountable person on Steering, then type the meeting's date in Last review on Portfolio.
YOUR LOGO
The FRQZ logo is in cell A1 on every tab. To use your own, delete it and insert your logo in A1, on each tab.
NAMES
Type each person's name the same way every time, with a role in brackets if you like: Priya (CTO). Names are matched exactly as typed, so Priya and Priya (CTO) count as two people.
READING THE MARKS
■ Red | Late, or over budget, by more than your limit. The limits are on Portfolio, and you can change them.
◧ Amber | Late, or over budget, within your limit.
□ On track | A date or a budget was read, and nothing is late or over.
Not read | Nothing to judge from yet. A project with a Planned finish and no Latest forecast reads Not read; if the date hasn't moved, type it again as the forecast.
Not counted | Proposed, Completed or Terminated. Left out of every count.
△ | A check found something, and the words say what. Filter the Check column on △ to list them all.
○ Clear | The check found nothing.
HOW HEALTH IS WORKED OUT
Dates: a project is Red once its Planned finish has passed while it's still Active or Paused. Otherwise a Latest forecast past the plan by more than your limit is Red, and a smaller slip is Amber.
Money: spend over Budget by more than your limit is Red, and a smaller overrun is Amber. A program's spend is its projects' Forecast spend added up.
Health is the worse of the two. A program with no Latest forecast uses the latest among its projects. Its colour never hides theirs: Projects inside counts its Red and Amber projects beside it.
GREY COLUMNS
Grey cells are worked out from what you type. Don't type over them: a typed value replaces the formula.
Owner's current rows counts the Active and Paused rows that carry each owner's name, so you can see who's spread thin. It sets no limit.
THE BOARD
The Board is worked out from the Register, like Health. You type only its two commentary lines, the Kept in cell and the signature.
The first time, type Last checked on every row you've checked. As soon as one row has a date, every current row without a recent one counts as not checked.
Last checked: the day the owner last read this row's dates, forecast spend and note and said they still stand. Type it again at each check.
Owner's view: the owner's answer to whether the date and the cost will hold. It shows beside Health and never changes it.
To close a row, change its Status to Completed or Terminated. Don't delete it: the Board lists what left since the last review, and a deleted row can't be listed.
Its only settings are the two numbers on its second page. 35 days is where they start; change it to suit.
The Board runs three checks of its own, on its second page. They aren't among the seven on Portfolio. Portfolio does show the counts from Intake and Capacity, under its seven.
An assistant can prepare the Board for you. The brief is in frqz-portfolio-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results.
INTAKE AND SCORING
Score: the weighted criteria, 20 to 100. Recommended rank: the order the scores suggest for the queue. Fits: whether what's left covers this request and every one ranked above it.
The score leaves out cost and effort. The two Fits columns test them against the money left and the free person-days, in rank order.
An accepted request is shown to fit when it fits the money and the people, or when Gives way names an Active project that slows or stops for it. It needs a cost and an effort either way.
Agree the criteria and weights before anyone scores, and type the date. The check can show only that a date was typed and that no decision is dated before it.
Fits the money tests against money not yet given to any program. For work inside a program, ask that program's owner.
Free person-days is typed. Capacity's figure for the next 13 weeks shows beside it. That figure counts anyone whose project has no booking as free, so it's the most you could have.
Give the Register row the same name as the request. To rename a project or an objective, use Find and Replace on every tab.
An accepted request has 14 days to get its Register row before the check flags it.
Record intake decisions here, and the steering group's other decisions on Steering.
Intake runs four checks of its own. Their count shows on Portfolio, under the seven checks there.
An assistant can prepare the intake queue for you. The brief is in frqz-intake-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results.
CAPACITY
Capacity shows who is free in each of 13 weeks, starting from First week. Move First week forward as the weeks pass. Bookings and Time away keep their own dates.
Everything on Capacity is in days a week. A person with 4 usual days and 3 booked has 1 free.
People lists whoever does the work. A first name is enough; it doesn't have to match Owner on the Register.
Each Bookings line is one person on one Register row, from a first Monday to a last, at the same days a week. When the pace changes, end the line and start another. Book each day once, on the program or on one of its projects.
Book days on a Proposed row to see who would go over if it were approved: the last column of Who is free shows it. The line counts against nobody until the row is Active.
Everyone and Outside team are kept for two uses. On Time away, Everyone takes the days off every person, as for a public holiday. On Bookings, Outside team means a vendor or contractor staffs the row: it uses nobody's days, and the row counts as staffed.
Free days, at most, is a ceiling. A person whose project has no booking yet looks free, and so does a week nobody has booked.
Someone booked for all their days shows as over in any week they're away. Split the line and book fewer days that week, or leave the finding.
Time away holds dates and days, never a reason. Anyone who opens the file can read it.
Clear a line to remove it. Don't insert or delete rows on Capacity: each table sits at fixed rows. If two Register rows share a name, bookings go to the first.
Capacity runs four checks of its own, at the top of the tab. Portfolio shows how many fail, apart from its seven.
An assistant can read Capacity for you. The brief is in frqz-capacity-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results.
THE FULL WORKBOOK
The Full workbook adds a Funding tab, meetings and actions on Steering, and a Checks tab that runs twelve checks to this file's seven. Register A to L, the objectives, Steering A to C and Intake A to R match, so rows paste across.
To move your rows to the Full workbook, paste Register columns A to L, then AJ to AK, as two pastes. One paste of A to AK would clear the Full file's Approach column.
FOR A SMALL TEAM
Use projects only: Level Project and Sits under Portfolio on every row.
Fill in Status, Owner, Planned finish, Latest forecast and, on Amber or Red rows, a Variance note.
Leave Sponsor, Objective, Budget, Forecast spend, the envelope, the review cadence and the Steering tab empty. Nothing asks for them.
Three checks still run: a row with no owner, Sits under, and an Amber or Red row with no variance note.

## Portfolio
Portfolio
One portfolio per workbook. Type in the white cells; the grey ones are worked out.
THE PORTFOLIO
PORTFOLIO NAME |  | What you call the work this workbook covers. Required.
DIRECTOR |  | The person accountable for the portfolio's direction and benefits. A name, with a role in brackets if you like. Required.
MANAGER |  | The person who runs it day to day and keeps the register. Can be the director. Required.
REVIEW CADENCE |  | How often the steering group reviews the portfolio. Leave blank if there isn't one.
LAST REVIEW |  | The date of the latest steering meeting.
NEXT REVIEW |  | Worked out: Last review plus the cadence.
REVIEW CHECK |  | Shows △ when the next review has passed, or a cadence is set with no Last review.
LIMITS FOR RED
DAYS LATE BEFORE RED, PROJECTS |  | Working days a project may run past its Planned finish before it reads Red. Starts at 5; change it to suit.
DAYS LATE BEFORE RED, PROGRAMS |  | Working days a program may run past its Planned finish before it reads Red. Starts at 10.
OVER BUDGET BEFORE RED |  | How far spend may run over Budget before a row reads Red. A smaller overrun reads Amber. Starts at 10%.
ENVELOPE
ENVELOPE |  | The total the portfolio may spend. Optional; leave it blank and the envelope check doesn't run.
BUDGETS GIVEN OUT |  | Every Budget on a row directly under Portfolio, Proposed rows left out. When a row closes, lower its Budget to what was spent.
LEFT IN THE ENVELOPE |  | The envelope minus budgets given out. Negative means over.
FORECAST SPEND, ALL PROJECTS |  | Forecast spend added up across this portfolio's projects, Proposed left out.
PROJECTS WITH NO FORECAST SPEND |  | Projects in that total with Forecast spend blank. While there are any, the figure above reads low.
ENVELOPE CHECK |  | Shows △ when budgets given out pass the envelope.
COUNTS BY HEALTH |  | Programs and projects directly under Portfolio, one count each. A program's own projects are counted beside it on Register.
■ Red
◧ Amber
□ On track
Not read
CURRENT ROWS OUTSIDE THE PORTFOLIO |  | Active or Paused rows with Sits under set to Outside the portfolio. Left out of the counts above.
CHECKS
A ROW WITH NO OWNER
A PROGRAM WITH NO SPONSOR
SITS UNDER, OR A CURRENT ROW OUTSIDE THE PORTFOLIO
BUDGETS OVER THE ENVELOPE
REVIEW OVERDUE, OR NO REVIEW DATE
AN AMBER OR RED ROW WITH NO VARIANCE NOTE
A DECISION WITHOUT ONE ACCOUNTABLE PERSON
INTAKE CHECKS
CAPACITY CHECKS
OBJECTIVES
Objective | Owner | Measure and target | Target date

## Register
Register
Name | Level | Sits under | Status | Owner | Sponsor | Objective | Planned finish | Latest forecast | Forecast spend | Budget | Variance note | Health | Projects inside | Owner's current rows | Check | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Last checked | Owner's view | Current and in the portfolio (1 or 0) | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper | Board helper
Portfolio
Outside the portfolio
Formulas:
Helper, worked out = IF(OR([Helper, worked out]=0,[Planned finish]=""),0,IF(AND([Level]="Project",[Planned finish]<TODAY()),3,IF([Helper, worked out]="",0,IF([Helper, worked out]<=[Planned finish],1,IF(NETWORKDAYS([Planned finish],[Helper, worked out])-1>IF([Level]="Program",Portfolio!$B16,Portfolio!$B15),3,2)))))
Board helper = IF(AND([Current and in the portfolio (1 or 0)]=1,[Last checked]<>""),MAX(0,TODAY()-[Last checked]),"")
Board helper = IF(OR([Current and in the portfolio (1 or 0)]=0,COUNT(AJ6:AJ305)=0),0,IF([Last checked]="",1,IF(TODAY()-[Last checked]>Board!$B40,1,0)))
Note on M5: Worked out. Don't type here.
Note on N5: Worked out. Don't type here.
Note on O5: Worked out. Don't type here.

## Steering
Steering log
Date | Decision | Accountable | Check

## Board
Board
1 Where it stands. Worked out from the Register's dates and money.
Health | Programs and direct projects | All current rows | Of those, not checked | Budget, programs and direct projects
■ Red
◧ Amber
□ On track
Not read
Total
Left in the envelope
2 Commentary, written by the director. Causes come from the owners' variance notes.
Since last review
For the group to decide
Name | Owner | Health | Owner's view | What the numbers show | Variance note
4 Before you trust the figures
Owner's view milder than the numbers
Left since the last review
Not on this page | Benefits, risks and progress against the objectives aren't recorded in this workbook. No figure on this page stands in for them. |  |  |  | Kept in:
Board checks
Signed by |  |  | On
Settings and detail
Not checked after (days) | 35
Look ahead (days) | 90
Board checks
Rows not checked
A forecast date has passed
Owner's view milder than the numbers
Objectives and the rows serving them. The workbook holds no reading of the measures, so no progress is shown.
Objective | Owner | Rows serving it | Red or Amber among them | Measure and target | Target date
Rows that left since the last review. A row shows here only if its Last checked date is after that review.
Name | How it left | Last checked | Budget | Forecast spend

## Intake
Intake and scoring
Scoring criteria. Agree them, and their weights, before anyone scores a request.
Criterion | Weight | What a 1 and a 5 mean | [36 empty] | Helper, worked out
Fit to objective | 30% | 1: serves an objective only loosely. 5: moves an objective's measure directly.
Value to customers | 30% | 1: no customer would notice. 5: a named customer or contract depends on it.
Urgency | 20% | 1: can wait a year. 5: a date we don't control falls inside the next quarter.
Needed by other work | 20% | 1: nothing depends on it. 5: running work can't finish without it.
TOTAL WEIGHT
AGREED BY
AGREED ON
What's left for new work
LEFT IN THE ENVELOPE
FREE PERSON-DAYS
COST OF THE QUEUE
PERSON-DAYS IN THE QUEUE
DAYS TO GET ON THE REGISTER | 14
Checks
A decision dated before the criteria were agreed, or no date
A scored request with no objective from Portfolio
An accepted request not shown to fit
An accepted request that doesn't match the Register
A decision without who, when or why
Intake checks
Rows below the table
Requests. The queue is every scored request that hasn't started on the Register and isn't deferred or declined.
Request | Requested by | Received | Objective | Proposed owner | Estimated cost | Effort, person-days | Wanted start | Decision | Decided by | Decided on | Reason | Gives way | Register name | Score | Recommended rank | Fits the money | Fits the people | Days open | Check | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Running cost: this request and every one ranked above it | Running person-days: this request and every one ranked above it | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out | Helper, worked out

## Capacity
Capacity
Settings | [53 empty] | Days booked on this Register row | Active project with nobody booked (1 or 0) | Days pencilled on this Register row |  | Names for the Time away list | Names for the Bookings list | Lines and rows the tab can't read
FIRST WEEK | [57 empty] | Everyone | Outside team
USUAL DAYS A WEEK | 5
Capacity checks
Someone booked for too many days
A line or row the tab can't read
An Active project with nobody booked
A booking past the forecast date
Who is free. Days each person has left in each week, after time away and bookings on current rows. Below 0 means over.
Person | Weeks over | Usual days |  |  |  | If Proposed rows are approved | [7 empty] | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper |  |  |  | Capacity helper
Free days, at most
Days over, all people
People. The people who can be booked, and the days a week each one works.
Person | Usual days a week | Row check |  |  |  |  | Capacity helper
Time away. Leave and holidays, as days away in each week from one Monday to another. No reasons.
Person | From | To | Days away a week | Row check |  |  | Capacity helper
Bookings. One line per person, Register row and run of weeks. A line on a Proposed row is pencilled in and counts against nobody.
Register row | Person | From | To | Days a week | Line check |  | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper | Capacity helper