Example. Hollins Software and everyone in it are made up. Billing and Payments Program, as of 22 Oct 2026. To start your own, open the blank charter.

Program charter

Billing and Payments Program

How to fill it in, and the nine questions to ask before anyone signs, are on the last pages.

| Sits under | Portfolio |
| --- | --- |
| Level | Program |
| Objective | Move all billing to the new engine before renewals |
| Owner | Hugo (Program Manager) |
| Sponsor | Not yet named |
| Planned finish | 30 Jun 2027 |
| Budget (the envelope at signing) | 900,000 (US dollars) |
| Edition | 1 |
| Charter status | Signed |

# 1. What the program is for

By 30 Jun 2027, Finance Operations runs billing for every Hollins customer on the new billing engine, with tax worked out inside it.

Why a program: Billing Engine Rewrite builds the engine and moves the customers to it. Invoice Tax Rules gives it the tax rules for customers outside the US, and neither project moves every customer on its own.

# 2. Benefits

Table A: Benefits

| Benefit | Kind | Measure | Unit | Owner | Worth a year |
| --- | --- | --- | --- | --- | --- |
| Invoices from the new engine | Benefit | Share of invoices produced by the new engine, from the billing run report | Percent | Hugo (Program Manager) |  |
| Fewer invoice corrections | Benefit | Credit notes issued in a month to fix a billing error, from the finance ledger | Count | Rhys (Finance Operations Lead) |  |
| Cheaper to run billing | Benefit | Yearly cost of the old engine's licence and hosting, from the finance ledger | US dollars a year | Rhys (Finance Operations Lead) | 310,000 |

Table A, continued: Baselines and targets

| Benefit | Baseline | Baseline date | Target | Target date | First read |
| --- | --- | --- | --- | --- | --- |
| Invoices from the new engine | 0 | 1 Oct 2026 | 100 | 30 Sep 2027 | 29 Jan 2027 |
| Fewer invoice corrections | Not yet measured |  | 60 | 31 Dec 2027 | 30 Apr 2027 |
| Cheaper to run billing | 310,000 | 30 Sep 2026 | 0 | 31 Dec 2027 | 30 Jul 2027 |

First read is the first time the Owner reads the measure. After that, it's read each quarter until the target date, and the program workbook keeps the next date.

Table B: Costs that continue

| Cost | Per year | Who pays | Comes off | Note |
| --- | --- | --- | --- | --- |
| None |  |  |  |  |

# 3. Projects and money

Table C: Projects and their shares

| Project | Owner | Planned finish | Share of the envelope |
| --- | --- | --- | --- |
| Billing Engine Rewrite | Anders (Engineering Manager) | 30 Jun 2027 | 780,000 |
| Invoice Tax Rules | Hugo (Program Manager) | 1 Feb 2027 | 120,000 |
| Held back |  |  | 0 |
| Total of shares and held back |  |  | 900,000 |

Tolerances at signing

Cost: 10 percent over the envelope. Benefits: 15 percent short of the planned change. Outcome date: 10 working days late.

# 4. Decision points

Table D: Decision points

| Decision point | Date | Decides | Consulted | Evidence looked at |
| --- | --- | --- | --- | --- |
| Investment decision, Mar 2026 | 5 Mar 2026 | Priya (CTO) | Anders (Engineering Manager), Rhys (Finance Operations Lead) | Benefits: three, with owners; one baseline not yet measured. Budget 900,000; Billing Engine Rewrite's share set. Program manager Hugo (Program Manager); sponsor not yet named. Billing Engine Rewrite, Planned finish 30 Jun 2027. Dependencies: none yet written down. |
| Strategic review, Jan 2027 | 29 Jan 2027 | Not yet named | Anders (Engineering Manager), Rhys (Finance Operations Lead) | To look at: benefits read so far, any tolerance crossed, the dependencies, the outcome date. |
| Strategic review, Apr 2027 | 30 Apr 2027 | Not yet named | Anders (Engineering Manager), Rhys (Finance Operations Lead) | To look at: benefits read so far, any tolerance crossed, the dependencies, the outcome date. |
| Strategic review, at close | 30 Jun 2027 | Not yet named | Anders (Engineering Manager), Rhys (Finance Operations Lead) | To look at: benefits read so far, any tolerance crossed, the dependencies, the outcome date. |

# 5. Dependencies at signing

Table E: Dependencies

| Needs | Provided by | Needed by | Who answers |
| --- | --- | --- | --- |
| Tax rules for customers outside the US in the second wave | Invoice Tax Rules | 1 Feb 2027 | Hugo (Program Manager) |
| Customer accounts for the second wave, a milestone in Data Migration Wave 2 | Data Migration Wave 2 | 29 Jan 2027 | Kofi (Delivery Lead) |

The new engine carries the US tax rules itself. Customers outside the US and on annual contracts move in the second wave, from 1 Feb 2027, and need both of these.

# 6. Will not do

Change prices or plans.

Build the invoice screens partners see; Partner Portal Launch does that.

Move customer data to the new customer platform, which is Data Migration Wave 2's work.

# 7. Program board and benefits after close

| Program board | Hugo (Program Manager), Anders (Engineering Manager), Rhys (Finance Operations Lead) |
| --- | --- |
| Takes the benefits at close |  |

# 8. Changing this charter

To change anything in the header or in Tables A to E, write it in Table F first, with the old value, the new one and why. It makes the next edition, and everyone in section 9 signs again. A rename on the Register, or a typing mistake put right, is a row marked name only: same edition, no new signatures.

Table F: Changes

| Edition | Date | What changed | Why | Decided by |
| --- | --- | --- | --- | --- |
|  |  | No changes yet. |  |  |

# 9. Sign-off

Table G: Signatures

| Role | Name | What signing means | Signature | Date | Edition signed |
| --- | --- | --- | --- | --- | --- |
| Sponsor |  | I decide whether this program goes on, changes or stops, and I've read its benefits. |  |  |  |
| Program manager, and benefit owner for Invoices from the new engine | Hugo (Program Manager) | I'll run the program as this charter sets it out, and bring any change to section 8 first. I'll read my benefits' measures on the dates in Table A. | Signed | 22 Oct 2026 | 1 |
| Portfolio director | Priya (CTO) | I agree to this Budget coming out of the portfolio's envelope. | Signed | 22 Oct 2026 | 1 |
| Benefit owner for Fewer invoice corrections and Cheaper to run billing | Rhys (Finance Operations Lead) | I'll read my benefits' measures on the dates in Table A. |  |  |  |

A signature covers the edition written beside it. The charter is Signed only when every row is signed for the edition in the header. Change anything above, and everyone signs the next edition.

# Read me

This charter holds what was agreed when the program was signed: what it's for, the benefits it should bring, the projects and the money, who decides, and who signs. It changes only through section 8. What's true today, such as the forecast and the latest reads, goes in the program workbook.

## Filling it in

Copy from your portfolio register, letter for letter: the program's name and its Sits under, Level, Objective, Owner, Sponsor and Planned finish from its row, and each project under it into Table C (Project, Owner and Planned finish).

Write section 1 first, then the benefits in Table A, each with its measure, baseline and owner.

Fill the rest in order. Where you can't fill a cell yet, leave it blank or write Not yet named, and the review questions will find it. Delete each grey prompt once its section is filled.

Before anyone signs, ask the nine review questions on the next page, or give the charter to an assistant with the brief (see Other files).

Set Charter status to Waiting to sign and send it to everyone in Table G. When every row is signed for this edition, set it to Signed and keep a PDF of it.

To change it after that, follow section 8.

## Your logo

The FRQZ logo is at the top right of page 1. To use your own, right-click it and choose Change Picture. In Google Docs, choose Replace image.

## Names

Write each person the way the Register does, first name and role: Hugo (Program Manager). The program, its projects and its objective are copied letter for letter, so the program workbook and each project charter can find them by name.

## Words used here

Envelope: the money set aside for the whole program, the Budget in the header. Each project gets a share; what isn't shared out yet is Held back.

Benefit: a change the program should bring, counted in something you already measure. Disbenefit: a change it makes worse for someone, written the same way.

Worth a year: what a benefit counted in money is worth each year once it reaches its target. A cost that continues in Table B comes off it.

Investment decision: the decision to start the program and fund it. Strategic review: a planned look at whether it goes on, changes or stops. The last Strategic review is at close.

Tolerances: how far cost, benefits and the outcome date may move before the sponsor has to decide.

Edition: the count of signed charters, 1 and then 2 after the first signed change. A name only row in Table F keeps the edition.

Changed since signed: something above was changed after signing, and the next edition isn't signed yet.

## A program already running

You can sign a charter for a program that's already under way. Signing then confirms the program as it stands that day, and Table D keeps the Investment decision's own date.

A file can't tell you it was changed after signing. Before each Strategic review, compare it with the signed PDF: in Word, Review, then Compare; in Google Docs, Tools, then Compare documents. That's question 9.

## Other files

The program workbook starts from Tables A to E and says which edition it copied. Change the charter first, then the workbook.

Each project charter names the benefit it serves exactly as Table A writes it, and its share exactly as Table C has it.

An assistant can review the charter for you. The brief is in frqz-program-charter-agent-brief.txt, beside this file.

## About this Example

Hollins Software is a made-up software company. Everyone in it is made up too.

This is the charter for Billing and Payments Program, signed on 22 Oct 2026 for a program already running. Its Investment decision was made on 5 Mar 2026.

It fails four of the nine review questions on purpose. The review notes on the last page say where.

Question 3: Fewer invoice corrections has no baseline. It reads Not yet measured, with no date.

Question 4: All three benefits are read after the program closes on 30 Jun 2027, and nobody is named to take them at close. The first, Invoices from the new engine, is owned by Hugo, the program manager, whose role ends at close.

Question 5: Cheaper to run billing is worth 310,000 a year, and Table B says None with no reason. Finance puts the new engine's hosting and support at 140,000 a year, and no budget line holds it.

Question 8: The charter reads Signed, but the program has no sponsor, nobody is named to decide the three Strategic reviews, and the sponsor's row in Table G is empty. Rhys hasn't signed either.

# Before anyone signs: nine questions

A reviewer who didn't write the charter asks these: the program manager's peer, or the portfolio manager. Write what each one finds in the review notes, with where you found it.

| 1. A name that differs from the Register | Do the header's Name, Sits under, Objective and Owner, and each project and owner in Table C, match the Register letter for letter? Is every Register row that sits under this program in Table C? Copy the Register's spelling. If the Register is wrong, change it there first. A blank on the Register stays blank here. |
| --- | --- |
| 2. A benefit nobody outside the program would notice | Could each benefit come true while nobody outside the program team is better off? Ask the same of the objective's measure. If so, it counts something the program builds. Find what changes for the people who use it, and count that. |
| 3. A benefit that can't be measured yet | Does every benefit have a measure with its unit and report, a baseline with the day it was taken, a target, a target date and a first read? TBC, Not yet measured and a year alone count as missing. Take the baseline before anyone signs, or write down who takes it and by when. |
| 4. A benefit read after close, with nobody named to read it | For each benefit whose target date is after the Planned finish: is its owner someone who stays after close, and does Takes the benefits at close name someone, or say Not needed: and why? Ask the sponsor who takes the benefits at close. A benefit's owner can differ from the objective's owner; tell the portfolio manager who it is at handover. |
| 5. A benefit in money with no running cost set against it | Does every benefit with a Worth a year have a row in Table B that comes off it, or does Table B say None with a reason? Ask Finance what the new thing costs to run each year, and who pays. |
| 6. Shares that don't add up to the Budget | Do the shares and Held back add up to the Budget, and is the printed total right? Fix the shares, or change the Budget through section 8. |
| 7. A date out of order, or different from the Register | Is the Planned finish the Register's? Does each project finish on or before it? Do the decision points run in order, and does each first read come before its target date? Does each Needed by fall on or after its provider's Planned finish, unless Needs names a milestone? Find which date is wrong and fix it, on the Register first if it's there. A Proposed project with no Planned finish on the Register is noted, not failed. |
| 8. A signed charter with no one named to decide | Is the Sponsor named? Until the charter is signed, Not yet named is allowed. Does every decision point have one name in Decides? If Charter status reads Signed, has everyone in Table G signed this edition? Set Charter status back to Waiting to sign until they are. |
| 9. A change since signing that isn't in Table F | Compared with the last signed edition, has any value, date, share or name in the header or Tables A to E changed with no row in Table F? A name only row covers a rename. Write the row, and sign the next edition. On edition 1 there's nothing to compare. |

# Review notes

Read on 22 Oct 2026. The Example fails questions 3, 4, 5 and 8 on purpose, and passes 1, 2, 6 and 7. Question 9 needs an earlier signed edition.

| # | Question | Result | What was found, and where |
| --- | --- | --- | --- |
| 1 | A name that differs from the Register | ○ Passes | Every name matches the Register. Invoice Tax Rules is Proposed, so its Planned finish is blank on the Register; Table C has 1 Feb 2027. |
| 2 | A benefit nobody outside the program would notice | ○ Passes | All three benefits count something that changes once billing runs on the new engine: invoices, corrections and cost. |
| 3 | A benefit that can't be measured yet | △ Fails | Fewer invoice corrections has no baseline and no baseline date (Table A, row 2). |
| 4 | A benefit read after close, with nobody named to read it | △ Fails | All three benefits are read after the program closes on 30 Jun 2027, and nobody is named to take the benefits at close (section 7). Invoices from the new engine's owner is the program manager, Hugo, whose role ends at close (Table A, row 1). |
| 5 | A benefit in money with no running cost set against it | △ Fails | Cheaper to run billing is worth 310,000 a year, and Table B says None, with no reason in Note. Finance puts the new engine's hosting and support at 140,000 a year, in no budget line. |
| 6 | Shares that don't add up to the Budget | ○ Passes | 780,000 and 120,000, with 0 held back, make 900,000: the Budget, and the printed total. |
| 7 | A date out of order, or different from the Register | ○ Passes | The Planned finish is the Register's. Both projects finish by it, the decision points run in order, and every first read comes before its target date. The Data Migration Wave 2 row is needed by 29 Jan 2027, before that project's finish, and names its milestone. |
| 8 | A signed charter with no one named to decide | △ Fails | The charter reads Signed. The Sponsor is Not yet named (header), the three Strategic reviews have nobody in Decides (Table D), and the Sponsor's and Rhys's rows aren't signed (Table G). |
| 9 | A change since signing that isn't in Table F | Not done: no earlier signed edition | This is edition 1. |