Program charter

The program's name, letter for letter as the Register writes it

How to fill it in, and the nine questions to ask before anyone signs, are on the last pages.

| Sits under | As the Register writes it: Portfolio, or Outside the portfolio |
| --- | --- |
| Level | Program |
| Objective | One Portfolio objective, in the objectives list's exact words |
| Owner | The program manager: first name and role, such as Hugo (Program Manager) |
| Sponsor | The one person who decides whether the program goes on, changes or stops. Not yet named is allowed until the charter is signed |
| Planned finish | The outcome date, as on the Register, such as 30 Jun 2027 |
| Budget (the envelope at signing) | A number, then the currency once, in brackets: 900,000 (US dollars) |
| Edition | 1 for the first signed charter. Each signed change makes the next |
| Charter status | Draft, Waiting to sign, Signed or Changed since signed |

Copy the name and Sits under to Planned finish from the program's row on the Register, letter for letter. Every other figure in this charter is a plain number in the Budget's currency. A new Owner or Sponsor is a change to the charter: write it in section 8 first.

# 1. What the program is for

One sentence: by [date], [who] can [what]. Name the change people outside the program team will notice.

Why a program: Two lines: the projects, and the benefit none of them brings alone. If one project would do, run it as a project.

# 2. Benefits

One row per benefit, each a change in something you already count. A loss the program causes is a row too, with Kind Disbenefit. If a benefit is the Portfolio objective's measure, use the objective's words.

Table A: Benefits

Measure: what is counted, and the report it comes from. Baseline date: the day, month and year it was taken; TBC or a year alone isn't a date. If there's no baseline yet, write Not yet measured. Worth a year: only for a benefit counted in money.

| Benefit | Kind | Measure | Unit | Owner | Worth a year |
| --- | --- | --- | --- | --- | --- |

Table A, continued: Baselines and targets

| Benefit | Baseline | Baseline date | Target | Target date | First read |
| --- | --- | --- | --- | --- | --- |

First read is the first time the Owner reads the measure. After that, it's read each quarter until the target date, and the program workbook keeps the next date.

Table B: Costs that continue

What keeps costing money once the new thing is live, each year, and the benefit it comes off. If nothing does, write None in Cost and the reason in Note.

| Cost | Per year | Who pays | Comes off | Note |
| --- | --- | --- | --- | --- |

# 3. Projects and money

Copy each project's Name, Owner and Planned finish from the Register, letter for letter. Share of the envelope is the part of the Budget set aside for that project. Held back is what isn't shared out yet, and may be 0.

Table C: Projects and their shares

| Project | Owner | Planned finish | Share of the envelope |
| --- | --- | --- | --- |
| Held back |  |  |  |
| Total of shares and held back |  |  |  |

Tolerances at signing

How far each may move before the sponsor has to decide. The program workbook copies them; a change to one is a row in section 8.

Cost: [10] percent over the envelope. Benefits: [15] percent short of the planned change. Outcome date: [10] working days late.

# 4. Decision points

The Investment decision first, then each Strategic review in date order; the last is the one at close. One person decides each. The sponsor chairs every Strategic review.

Table D: Decision points

| Decision point | Date | Decides | Consulted | Evidence looked at |
| --- | --- | --- | --- | --- |
| Investment decision, [month year] |  |  |  | What was true on the day, one line each: Every benefit has an owner, a baseline and a first read. The Budget is set, and each project's share is listed. The sponsor and the program manager are named. Every project is listed with a Planned finish. Dependencies are written down. |
| Strategic review, at close |  |  |  |  |

# 5. Dependencies at signing

Only what would move the outcome date. Needed by falls on or after the provider's Planned finish, unless Needs names the milestone that comes sooner. If there's nothing, write None.

Table E: Dependencies

| Needs | Provided by | Needed by | Who answers |
| --- | --- | --- | --- |

# 6. Will not do

Three to six things someone might expect from this program and won't get. Where another project does it, name that project.

# 7. Program board and benefits after close

| Program board | Everyone who sits on it, by first name and role. |
| --- | --- |
| Takes the benefits at close | The person who reads the benefits after the program closes, by name and role, and from what date. If every benefit is read before close, write Not needed: and why. |

# 8. Changing this charter

To change anything in the header or in Tables A to E, write it in Table F first, with the old value, the new one and why. It makes the next edition, and everyone in section 9 signs again. A rename on the Register, or a typing mistake put right, is a row marked name only: same edition, no new signatures.

Table F: Changes

The old value, then the new: Planned finish was 30 Jun 2027, now 30 Jul 2027. Decided by: the one person who agreed it.

| Edition | Date | What changed | Why | Decided by |
| --- | --- | --- | --- | --- |

# 9. Sign-off

One row for the sponsor, the program manager and the portfolio director, and one for each benefit owner. Someone in two roles signs one row that names both. With no portfolio, write none, no portfolio, and why, in the portfolio director's row.

Table G: Signatures

| Role | Name | What signing means | Signature | Date | Edition signed |
| --- | --- | --- | --- | --- | --- |
| Sponsor |  | I decide whether this program goes on, changes or stops, and I've read its benefits. |  |  |  |
| Program manager |  | I'll run the program as this charter sets it out, and bring any change to section 8 first. |  |  |  |
| Portfolio director |  | I agree to this Budget coming out of the portfolio's envelope. |  |  |  |
| Benefit owner |  | I'll read my benefits' measures on the dates in Table A. |  |  |  |

A signature covers the edition written beside it. The charter is Signed only when every row is signed for the edition in the header. Change anything above, and everyone signs the next edition.

# Read me

This charter holds what was agreed when the program was signed: what it's for, the benefits it should bring, the projects and the money, who decides, and who signs. It changes only through section 8. What's true today, such as the forecast and the latest reads, goes in the program workbook.

## Filling it in

Copy from your portfolio register, letter for letter: the program's name and its Sits under, Level, Objective, Owner, Sponsor and Planned finish from its row, and each project under it into Table C (Project, Owner and Planned finish).

Write section 1 first, then the benefits in Table A, each with its measure, baseline and owner.

Fill the rest in order. Where you can't fill a cell yet, leave it blank or write Not yet named, and the review questions will find it. Delete each grey prompt once its section is filled.

Before anyone signs, ask the nine review questions on the next page, or give the charter to an assistant with the brief (see Other files).

Set Charter status to Waiting to sign and send it to everyone in Table G. When every row is signed for this edition, set it to Signed and keep a PDF of it.

To change it after that, follow section 8.

## Your logo

The FRQZ logo is at the top right of page 1. To use your own, right-click it and choose Change Picture. In Google Docs, choose Replace image.

## Names

Write each person the way the Register does, first name and role: Hugo (Program Manager). The program, its projects and its objective are copied letter for letter, so the program workbook and each project charter can find them by name.

## Words used here

Envelope: the money set aside for the whole program, the Budget in the header. Each project gets a share; what isn't shared out yet is Held back.

Benefit: a change the program should bring, counted in something you already measure. Disbenefit: a change it makes worse for someone, written the same way.

Worth a year: what a benefit counted in money is worth each year once it reaches its target. A cost that continues in Table B comes off it.

Investment decision: the decision to start the program and fund it. Strategic review: a planned look at whether it goes on, changes or stops. The last Strategic review is at close.

Tolerances: how far cost, benefits and the outcome date may move before the sponsor has to decide.

Edition: the count of signed charters, 1 and then 2 after the first signed change. A name only row in Table F keeps the edition.

Changed since signed: something above was changed after signing, and the next edition isn't signed yet.

## A program already running

You can sign a charter for a program that's already under way. Signing then confirms the program as it stands that day, and Table D keeps the Investment decision's own date.

A file can't tell you it was changed after signing. Before each Strategic review, compare it with the signed PDF: in Word, Review, then Compare; in Google Docs, Tools, then Compare documents. That's question 9.

## Other files

The program workbook starts from Tables A to E and says which edition it copied. Change the charter first, then the workbook.

Each project charter names the benefit it serves exactly as Table A writes it, and its share exactly as Table C has it.

An assistant can review the charter for you. The brief is in frqz-program-charter-agent-brief.txt, beside this file.

# Before anyone signs: nine questions

A reviewer who didn't write the charter asks these: the program manager's peer, or the portfolio manager. Write what each one finds in the review notes, with where you found it.

| 1. A name that differs from the Register | Do the header's Name, Sits under, Objective and Owner, and each project and owner in Table C, match the Register letter for letter? Is every Register row that sits under this program in Table C? Copy the Register's spelling. If the Register is wrong, change it there first. A blank on the Register stays blank here. |
| --- | --- |
| 2. A benefit nobody outside the program would notice | Could each benefit come true while nobody outside the program team is better off? Ask the same of the objective's measure. If so, it counts something the program builds. Find what changes for the people who use it, and count that. |
| 3. A benefit that can't be measured yet | Does every benefit have a measure with its unit and report, a baseline with the day it was taken, a target, a target date and a first read? TBC, Not yet measured and a year alone count as missing. Take the baseline before anyone signs, or write down who takes it and by when. |
| 4. A benefit read after close, with nobody named to read it | For each benefit whose target date is after the Planned finish: is its owner someone who stays after close, and does Takes the benefits at close name someone, or say Not needed: and why? Ask the sponsor who takes the benefits at close. A benefit's owner can differ from the objective's owner; tell the portfolio manager who it is at handover. |
| 5. A benefit in money with no running cost set against it | Does every benefit with a Worth a year have a row in Table B that comes off it, or does Table B say None with a reason? Ask Finance what the new thing costs to run each year, and who pays. |
| 6. Shares that don't add up to the Budget | Do the shares and Held back add up to the Budget, and is the printed total right? Fix the shares, or change the Budget through section 8. |
| 7. A date out of order, or different from the Register | Is the Planned finish the Register's? Does each project finish on or before it? Do the decision points run in order, and does each first read come before its target date? Does each Needed by fall on or after its provider's Planned finish, unless Needs names a milestone? Find which date is wrong and fix it, on the Register first if it's there. A Proposed project with no Planned finish on the Register is noted, not failed. |
| 8. A signed charter with no one named to decide | Is the Sponsor named? Until the charter is signed, Not yet named is allowed. Does every decision point have one name in Decides? If Charter status reads Signed, has everyone in Table G signed this edition? Set Charter status back to Waiting to sign until they are. |
| 9. A change since signing that isn't in Table F | Compared with the last signed edition, has any value, date, share or name in the header or Tables A to E changed with no row in Table F? A name only row covers a rename. Write the row, and sign the next edition. On edition 1 there's nothing to compare. |