## Read me
Program workbook
One program's benefits, costs, projects, dependencies and meetings, kept by hand, with a Dashboard that reads them all. Seven tabs: Read me, Dashboard, Benefits, Costs, Roadmap, Dependencies and Meetings.
Where to start
Start on Dashboard: copy the program from the Register and check the limits. Then copy the benefits from the signed program charter. The charter holds what was agreed; this workbook holds what is true now.
Filling it in
1 | On Dashboard, copy the program's Name, Sits under, Owner, Sponsor, Planned finish and Latest forecast from the Register, and type the charter's Edition. In Projects on the Register, count the Register rows under this program.
2 | Check the four limits beside it. The first two are your organisation's figures; the other two are this template's own. Change any of them to suit.
3 | On Benefits, add one row per benefit from the charter's Table A. Then type each read as it happens: Last read, its date, and the owner's Forecast.
4 | On Costs, add a line for each cost that continues once the program is live, and the benefit it comes off. A money benefit with no such cost still gets one line: Cost None, Per year 0, and the reason in Note.
5 | On Roadmap, add one row per project, spelled as the Register spells it, with its Status and dates. Add each decision point: Investment decision or Strategic review, then its month.
6 | On Dependencies, add what each project needs from outside itself, who provides it and by when. Ask, then type the State and the date promised.
7 | On Meetings, list each forum, then log every action and decision with one owner. When a Due date changes, add one to Times moved.
8 | Read the Dashboard, and fix every row that shows △.
YOUR LOGO
The FRQZ logo is in cell A1 on every tab. To use your own, delete it and insert your logo in A1, on each tab.
NAMES
Write each person the way the Register does, first name and role: Hugo (Program Manager). Owner, Chair and Who answers take one name each. Type a project exactly as the Register spells it, on Roadmap and Dependencies alike.
READING THE MARKS
■ Red | Late, or short of a benefit, by more than your limit. The limits are on Dashboard, and you can change them.
◧ Amber | Late, or short of a benefit, within your limit.
□ On track | A date or a forecast was read, and nothing is late or short.
Not read | Nothing to read yet: a date or a figure is missing, or typed as words.
Not asked | A dependency with no State. Nobody has asked the provider yet.
△ | A check found something, and the words say what. Filter Row check on △ to list the rows.
○ Clear | The check found nothing.
HOW IT COUNTS
1 | Only Active and Paused projects count toward the outcome date. A Proposed project shows on Roadmap and isn't counted until it's Active.
2 | The outcome date is the later of the Latest forecast on Dashboard and the latest counted forecast on Roadmap, so a typed date can't hide a late project.
3 | An Active project with no Latest forecast drops out of the outcome date, so check 5 can pass while check 4 fails. Roadmap's Row check flags it.
4 | Lateness is counted in working days, from the day after the date that was due. Weekends are the only days off; there's no holiday list.
5 | Overdue reviews, actions and forums show the date they were due. Every result counts from Counting from on Dashboard: As of if you typed one, otherwise today.
6 | Expected is what the provider says this week, and Promised is what they promised. The later of the two is the date it will arrive.
7 | The Dashboard lists the first eight benefits, and six dependencies worst first: past due, slipped, declined and not asked, then the rest. The tabs hold them all.
THE CHECKS
The Dashboard runs nine checks, at the bottom. Each says what's wrong in a sentence, and Row check on each tab says which row.
Check 1 | Fails a benefit with a blank from Measure to Next review, a review date that has passed, a First read passed with nothing read, a figure typed as words, or a name used twice.
Check 2 | Fails a money benefit with no line on Costs, a Worth a year that isn't baseline minus target, or a cost line that names no benefit or has no amount.
Check 3 | Fails when a benefit's Target date is after Planned finish and Takes the benefits at close is blank. A name passes, and so does Not needed: with a reason.
Check 4 | Fails when Roadmap's projects don't number Projects on the Register, or a Roadmap row shows △. A misspelt name still passes; the assistant's first step looks for it.
Check 5 | Fails when the outcome date is more working days late than your limit.
Check 6 | Fails a dependency nobody has asked about, one with no Who answers or no date, or one asked longer ago than your limit.
Check 7 | Fails a dependency that arrives after Needed by, is past due, or was declined.
Check 8 | Fails a forum with no Chair, May decide or Goes to, or one whose Next meeting differs from its decision point's date on Roadmap.
Check 9 | Fails an open action with no owner, two owners or no Due date, one that's overdue, or one moved as many times as your limit.
KEEPING IT TIDY
1 | Grey cells are worked out and locked, with no password. Filter freely. To sort, unprotect the sheet first and protect it again after. Don't insert rows.
2 | Meetings holds 300 actions, about a year of a fortnightly board. Move Done actions older than 90 days to a copy of this file.
3 | When the Register renames a project, rename it on Dashboard, Roadmap and Dependencies too. Roadmap and Dependencies have their names typed, so neither follows on its own.
4 | A change to a benefit, a cost or a decision date is a change to the program charter first, and a new Edition. Then copy it here.
OTHER FILES
1 | A dependency on another program's project is in that program's workbook too. Check that the two files agree on Promised and Expected.
2 | Program risks and issues go in a RAID log. The project RAID log file works for a program: name the program as its Register row.
3 | Each project file cites a benefit by its name on Benefits, and a dependency by its Needs, word for word.
4 | An assistant can check the workbook for you. The brief is in frqz-program-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results.

## Dashboard
Dashboard
Program |  |  |  | Limits |  |  |  | Helper, worked out
NAME |  |  |  | WORKING DAYS LATE BEFORE RED |  |  | 10
SITS UNDER |  |  |  | BENEFIT SHORTFALL BEFORE RED |  |  | 15%
OWNER |  |  |  | WORKING DAYS AN ASK MAY WAIT |  |  | 10
SPONSOR |  |  |  | MOVES THAT FLAG AN ACTION |  |  | 2
PLANNED FINISH |  |  |  | FIRST MONTH ON ROADMAP
LATEST FORECAST
CHARTER EDITION
TAKES THE BENEFITS AT CLOSE
PROJECTS ON THE REGISTER
AS OF
COUNTING FROM
Status
OUTCOME DATE
BENEFITS
DEPENDENCIES OPEN
ACTIONS OPEN
NEXT DECISION POINT
Benefits
Benefit | Owner | Target | Forecast | Reading | Review due | Net a year at target
Dependencies
Needs | Provided by | Needed by | Date it will arrive | Shown as | Who answers
Checks
1 A benefit that can't be read, or is overdue
2 A saving not shown net of what it costs to run
3 A benefit read after close, with nobody to take it
4 A roadmap that doesn't match the Register
5 An outcome date later than the limit allows
6 A dependency nobody has answered for
7 A dependency that won't arrive in time
8 A forum missing a chair, limits or a place to escalate
9 An action without one owner and a date, or stuck
CHECKS FAILING
Note on C11: Worked out: the later of the forecast typed beside it and the latest Active or Paused project on Roadmap. The outcome date uses this.
Note on B16: Worked out: As of if you typed one, otherwise today. Every overdue and late result counts from this date.

## Benefits
Benefits
Benefits
Benefit | Kind | Measure | Unit | Baseline | Baseline date | Target | Target date | Owner | First read | Next review | Last read | Last read date | Forecast | Worth a year | Progress | Reading | Review due | Net a year at target | Row check | Missing a measure, baseline, target, owner or date (1 or 0) | Read after close, nobody named (1 or 0) | Worth money, no line on Costs (1 or 0) | No review date, or passed (1 or 0) | Name used twice (1 or 0) | First read passed, nothing read (1 or 0) | Worth a year isn't baseline minus target (1 or 0) | A figure typed as words (1 or 0) | Fails check 1 (1 or 0) | Helper, worked out | Helper, worked out
Note on A6: A short name, used once. Project files cite the benefit by this name, so copy it from the charter's Table A exactly.
Note on B6: Benefit, or Disbenefit for a loss the program accepts.
Note on C6: What is counted, and from which report.
Note on D6: What the number counts in, such as percent or US dollars a year. For money, write dollars, USD, EUR or GBP, so the money check can find it.
Note on E6: The figure before the program, as a number. Leave it blank until it's measured: a blank is a finding.
Note on F6: The day the baseline was taken. A year or TBC isn't a date.
Note on G6: The figure the program promises, as a number.
Note on H6: When the target is reached. A date after the program's Planned finish needs a name in Takes the benefits at close on Dashboard.
Note on I6: One person who reads the measure, written like Rhys (Finance Operations Lead). They needn't be the objective's owner.
Note on J6: The first day the owner reads the measure.
Note on K6: The next day the owner reads it. Start with First read, and move it on after each read.
Note on L6: The figure at the last read, as a number.
Note on M6: The day of that read.
Note on N6: The figure the owner expects at the target date. A person's figure, never an agent's. Reading is worked out from it.
Note on O6: Money benefits only: what the change from baseline to target is worth in a year, as a number. Leave it blank for any other benefit.
Note on P6: Worked out: how far the last read has come from baseline to target.
Note on Q6: Worked out from Forecast. On track if it meets the target, Amber if it falls short within the limit on Dashboard, Red beyond it. Not read when a figure is missing or typed as words.
Note on R6: Worked out from Next review.
Note on S6: Worked out: Worth a year minus every line on Costs that comes off this benefit.
Note on T6: The first thing wrong with this row. Filter on △ to list them.

## Costs
Costs
Costs that continue
Cost | Comes off | Per year | Who pays | Note | Row check | Names no benefit on Benefits (1 or 0) | Per year missing, or 0 with no Note (1 or 0)
Note on A6: What keeps costing money once the program is live, such as hosting. If a benefit has no such cost, type None.
Note on B6: The benefit this cost comes off. Pick it from Benefits.
Note on C6: The cost for a year, as a number. 0 is allowed with a Note.
Note on D6: The team or budget that pays it.
Note on E6: Why, in a line. Required when Per year is 0.
Note on F6: The first thing wrong with this row. Filter on △ to list them.

## Roadmap
Roadmap
Projects and decision points
Item | Kind | Note | Status | Start | Planned finish | Latest forecast | Working days late | Row check | Forecast counted toward the outcome date | Decision point on or after Counting from | Helper, worked out | Helper, worked out | Helper, worked out
Note on A6: A project's name exactly as the Register writes it. Or a decision point: Investment decision or Strategic review, then a comma and a month or at close, such as Strategic review, Jan 2027.
Note on B6: Project or Decision point.
Note on C6: Worked out.
Note on D6: Projects only, copied from the Register. Only Active and Paused projects count toward the outcome date.
Note on E6: The day the project started, or will start.
Note on F6: From the Register. For a decision point, its date.
Note on G6: From the Register. If the date hasn't moved, type Planned finish again. Optional while a project is Proposed.
Note on H6: Worked out: working days from the day after Planned finish to Latest forecast. Weekends are the only days off.
Note on I6: The first thing wrong with this row. Filter on △ to list them.
Note on K6: 15 months, one column each, from the first month on Dashboard. ◆ marks a decision point, █ the plan from Start to Planned finish, ░ the slip to Latest forecast, ▶ a date past the last month.

## Dependencies
Dependencies
Dependencies
Needs | Needing project | Provided by | Outside this program? | Needed by | Asked on | Promised | State | Expected | Who answers | Reason | Date it will arrive | Working days after needed | Shown as | Row check | Name or date missing (1 or 0) | Asked longer than the limit (1 or 0) | Slipped, past due or declined (1 or 0) | Open, once per record (1 or 0) | Not asked (1 or 0) | Sort key, worst first | Helper, worked out
Formulas:
Working days after needed = IF(OR([Needs]="",NOT(ISNUMBER([Date it will arrive])),NOT(ISNUMBER([Needed by]))),"",IF([Date it will arrive]>[Needed by],NETWORKDAYS([Needed by]+1,[Date it will arrive]),""))
Asked longer than the limit (1 or 0) = IF([Needs]="",0,IF([State]<>"Asked",0,IF(NOT(ISNUMBER([Asked on])),1,IF(NETWORKDAYS([Asked on]+1,Dashboard!$B16)>Dashboard!$H8,1,0))))
Note on A6: What's needed, in a line. A project file cites it by these words exactly, so change them only on purpose.
Note on B6: The project on Roadmap that needs it.
Note on C6: Who provides it: a project's name exactly as the Register writes it, or a team's name.
Note on D6: Yes if the provider isn't in this program. Blank reads No. A dependency on another program's project is in that program's workbook too, so check the two agree.
Note on E6: The last day it can arrive without moving the project that needs it.
Note on F6: The day you asked the provider.
Note on G6: The date the provider promised.
Note on H6: Asked, Accepted, Declined, New date or Met. Leave it blank until you've asked: it shows as Not asked.
Note on I6: What the provider says this week, if it differs from Promised. Blank means Promised.
Note on J6: One person at the providing end, written like Kofi (Delivery Lead).
Note on K6: Why, for a decline or a new date.
Note on L6: Worked out: the later of Promised and Expected.
Note on M6: Worked out: working days from the day after Needed by to the date it will arrive.
Note on N6: Worked out: the State, or Not asked, Slipped or Past due.
Note on O6: The first thing wrong with this row. Filter on △ to list them.

## Meetings
Meetings
Forums
Forum | Chair | Cadence | Last met | Next meeting | May decide | Goes to | Decision point | Shown as | [8 empty] | No chair, limits or place to escalate (1 or 0) | Next decision point of this kind on Roadmap | Next meeting differs from Roadmap (1 or 0)
Actions and decisions
No. | Kind | Forum | Meeting date | What | Owner | Due | Status | Closed on | Times moved | Shown as | Row check | No one owner and a date (1 or 0) | Overdue (1 or 0) | Moved at the limit or more (1 or 0) | Fails check 9 (1 or 0) | Owner's name, before the role
Note on A6: The name of a group that meets, such as Program board. Forum and Program board are working names: use your own.
Note on B6: One person who chairs it, written like Hugo (Program Manager).
Note on C6: How often it meets.
Note on D6: The day it last met.
Note on E6: The day it meets next. If it holds a decision point, use the date on Roadmap.
Note on F6: What it may decide on its own, in words and numbers, such as a change of up to 10 working days.
Note on G6: Where anything beyond its limits goes, such as Strategic review.
Note on H6: Investment decision or Strategic review if this forum holds one, or None. Its Next meeting is compared with the next one on Roadmap.
Note on I6: Worked out from Next meeting.
Note on A19: A number for the row, used once, such as M-06. Other files and the assistant cite it.
Note on B19: Action for something to do, Decision for something decided.
Note on C19: Pick it from the forums above.
Note on D19: The meeting it came from.
Note on E19: What's to be done, or what was decided, in a line.
Note on F19: One name, written like Hugo (Program Manager): who does it, or who decided. Two names fail check 9.
Note on G19: When it's due. Required on an action.
Note on H19: Open, Done or Dropped for an action. Decided for a decision.
Note on I19: The day it was done, dropped or decided.
Note on J19: Add one each time Due changes. At the limit on Dashboard, an open action fails check 9.
Note on K19: Worked out from Status and Due.
Note on L19: The first thing wrong with this row. Filter on △ to list them.