Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of Wed 30 Jun 2027. The last page says which review questions it fails on purpose.

# Project close

Billing Engine Rewrite

| Name | Billing Engine Rewrite |
| --- | --- |
| Sits under | Billing and Payments Program |
| Owner | Anders (Engineering Manager) |
| Sponsor | Not yet named |
| Planned finish | Wed 30 Jun 2027 |
| Closed as | Completed |
| Closed on | Wed 30 Jun 2027 |
| Share of the envelope | 780,000 (US dollars) |
| Final cost | 770,400 |
| Forecast spend | 780,000 |
| Version | v1 |
| Status | Signed |
| Dated | Tue 29 Jun 2027 |

# 1. Result

| Purpose | By 30 Jun 2027, Finance Operations can bill every Hollins customer from the new engine. |
| --- | --- |
| Benefit it serves | Invoices from the new engine; Cheaper to run billing |
| Outcome | All 1,460 customers are billed from the new engine. The last moved on Mon 28 Jun 2027. |
| Told | Wed 30 Jun 2027, Anders (Engineering Manager) |
| Why it stopped | Doesn't apply: Closed as Completed. |

# 2. Deliverables

| Id | Deliverable | Accepted by | Accepted on | Delivered |
| --- | --- | --- | --- | --- |
| D1 | Monthly invoice run on the new engine | Rhys (Finance Operations Lead) | Fri 8 Jan 2027 | As promised |
| D2 | Credit notes and refunds on the new engine | Rhys (Finance Operations Lead) | Fri 8 Jan 2027 | As promised |
| D3 | Connection to the customer records Data Migration Wave 2 fills, tested on a full copy | Rhys (Finance Operations Lead) | Mon 14 Dec 2026 | As promised |
| D4 | Cutover of invoicing from the old engine, rehearsed twice, with rollback | Priya (CTO) | Fri 18 Dec 2026 | As promised. No rollback was needed. |
| D5 | Handover to Finance Operations and Support, with runbook and training | Noor (Support Lead) | Fri 28 May 2027 | As promised |

# 3. Acceptance

| Result | Count | Criteria | Evidence kept in |
| --- | --- | --- | --- |
| Met | 11 | C-01 and C-03 to C-12 | Test evidence |
| Waived | 1 | C-02 | Decision log DL-04 |
| Open | 0 |  |  |

| Criteria in all | 12 |
| --- | --- |
| Changed after the last signing | Mon 28 Sep 2026: C-05, C-06 |

# 4. Cost

| Line | Pays for | Baselined | Final | Difference |
| --- | --- | --- | --- | --- |
| Build and test the engine | D1, D2 | 410,000 | 412,300 | +2,300 |
| Billing history load | D3 | 70,000 | 76,500 | +6,500 |
| Cutover plan, rehearsals and the weekend | D4 | 150,000 | 138,900 | -11,100 |
| Runbook and training | D5 | 40,000 | 38,600 | -1,400 |
| Security and performance testing | D1 | 110,000 | 104,100 | -5,900 |
| Total (typed) |  | 780,000 | 770,400 | -9,600 |

| Owner's limit | 15,600 over the share |
| --- | --- |
| Against the share | 9,600 under, 1.2 percent |

# 5. Dates

| Gate | Original | Decided on | Moved in all | Change | Decides |
| --- | --- | --- | --- | --- | --- |
| Start | Thu 12 Mar 2026 | Thu 12 Mar 2026 | 0 |  | Priya (CTO) |
| Plan baselined | Fri 12 Jun 2026 | Fri 12 Jun 2026 | 0 |  | Anders (Engineering Manager) |
| Build complete | Fri 6 Nov 2026 | Fri 13 Nov 2026 | 5 | CH-5 | Anders (Engineering Manager) |
| Readiness | Thu 19 Nov 2026 | Thu 19 Nov 2026 | 0 |  | Anders (Engineering Manager) |
| Go/no-go | Thu 3 Dec 2026 | Thu 3 Dec 2026 | 0 |  | Priya (CTO) |
| Handover accepted | Fri 28 May 2027 | Fri 28 May 2027 | 0 |  | Rhys (Finance Operations Lead) |

# 6. Changes

| No. | Date | Change | Effect on scope, cost, date | Decided by | Sponsor agreed |
| --- | --- | --- | --- | --- | --- |
| CH-1 | Mon 21 Sep 2026 | Changes beyond the Owner's limit go to the sponsor, not Hugo (RACI decision 2) | None. Since then nobody can approve a change beyond the limit | Anders (Engineering Manager) | No sponsor named |
| CH-2 | Mon 21 Sep 2026 | C-04's test moves from a sample copy of the customer records to a full copy | Scope: more testing. Cost 0, absorbed in item 2. Date 0 | Anders (Engineering Manager) | No sponsor named |
| CH-3 | Mon 28 Sep 2026 | The invoice layout gains the fields Partner Portal Launch needs (RACI decision 11, Noor added as Consulted) | Scope: a few fields. Cost 0, absorbed in item 1.1. Date 0 | Anders (Engineering Manager) | No sponsor named |
| CH-4 | Wed 14 Oct 2026 | Engineering owns how invoices move to the new engine, not Hugo (RACI decision 4) | None | Anders (Engineering Manager) | No sponsor named |
| CH-5 | Fri 6 Nov 2026 | Build complete moves from Fri 6 Nov to Fri 13 Nov 2026 (CR-5) | Date: Build complete, 5 working days. Cost 0. Scope: none | Anders (Engineering Manager) | No sponsor named |
| CH-6 | Thu 19 Nov 2026 | Rhys (Finance Operations Lead) decides Handover accepted, with Noor's acceptance of D5 as a condition (RACI decision 14) | None | Priya (CTO) | No sponsor named |

# 7. Handover

| Takes it over | What | Accepted on |
| --- | --- | --- |
| Rhys (Finance Operations Lead) | The monthly invoice run, the month close, the ledger export and the tax rule list | Fri 28 May 2027 |
| Noor (Support Lead) | The first two lines of billing questions | Fri 28 May 2027 |

| Other routes | Billing defects go to Engineering's normal backlog. Anders (Engineering Manager) is the contact. |
| --- | --- |

# 8. Open items

| Item | Owner | Due | Kept in |
| --- | --- | --- | --- |
| The new engine's running cost, 140,000 a year, is in no budget line | Rhys (Finance Operations Lead) | Date TBD (gated on Finance Operations' FY28 budget request) | RAID log R3 |
| Switch off the old engine's licence and hosting | Rhys (Finance Operations Lead) | Fri 31 Dec 2027 |  |

## Passed to the program

| Item | Owner | First read | Kept in |
| --- | --- | --- | --- |
| Invoices from the new engine | Hugo (Program Manager) | Fri 29 Jan 2027, Taken | Program workbook, Benefits |
| Fewer invoice corrections | Rhys (Finance Operations Lead) | Fri 30 Apr 2027, Taken. No baseline: it was Not yet measured | Program workbook, Benefits |
| Cheaper to run billing | Rhys (Finance Operations Lead) | Fri 30 Jul 2027, Not yet due | Program workbook, Benefits |
| Objective 3's reading on the quarter to 30 Sep 2027 | Hugo (Program Manager) | Thu 30 Sep 2027, Not yet due | Program workbook, Benefits |

# 9. Lessons

| No. | Lesson | Comes from |
| --- | --- | --- |
| 1 | Book the second test environment when a full-copy test is added. | CH-2 |
| 2 | Name the sponsor, or the person standing in, at the start. | Go/no-go |
| 3 | Write a change to a criterion into the log the day it is made. | C-06 |

# 10. Sign-off

| Role | Name | What signing means | Signature | Date | Version signed |
| --- | --- | --- | --- | --- | --- |
| Decides the close, standing in as sponsor | Priya (CTO) | I decide that the project is closed. | Priya | Wed 30 Jun 2027 | v1 |
| Owner | Anders (Engineering Manager) | This is a true record of how the project ended. | Anders | Tue 29 Jun 2027 | v1 |
| Reviewer | Tomasz (PMO Head) | I asked the review questions of this version. | Tomasz | Tue 29 Jun 2027 | v1 |
| Takes it over | Rhys (Finance Operations Lead) | I've read what I took over, and the open items with my name. | Rhys | Tue 29 Jun 2027 | v1 |
| Takes it over | Noor (Support Lead) | I've read what I took over, and the open items with my name. | Noor | Tue 29 Jun 2027 | v1 |
| Program manager | Hugo (Program Manager) | I've read what passes to the program. | Hugo | Tue 29 Jun 2027 | v1 |

| Sponsor | Not yet named |
| --- | --- |

A signature applies to the version beside it. Status is Signed only when every row has a name, a signature, a date and the current version; a Reviewer row that reads None needs no signature. Closed on is the date on the Decides the close row.

## Versions

| Version | Date | What changed | Decided by | Re-signed |
| --- | --- | --- | --- | --- |
| v1 | Tue 29 Jun 2027 | First issued and signed | Anders (Engineering Manager) | Yes |

A change to Closed as, Delivered, Accepted by, an Acceptance count, Final cost, Changes, Handover, an Owner or Sign-off makes the next version, v2, and everyone in Sign-off signs again. A corrected Due, Kept in, First read or typo is v1.1: write it here with Re-signed No. Open items can be kept up that way after close.

# Review questions

Before anyone signs, someone who didn't write this close asks these nine questions, usually the portfolio manager. Ask question 5 again once Close is decided. Until everyone has signed, Who signed reads Not yet. Anything else that isn't a yes goes back to the Owner.

| # | Question | Yes when |
| --- | --- | --- |
| 1 | Same names. Do the names and figures match the files they're copied from? | Name, Sits under, Owner, Planned finish and Forecast spend are the Register's, and Sponsor is the program's row. Purpose, Benefit it serves, Share of the envelope, each Id, Deliverable and Accepted by, and each cost Line are the charter's, letter for letter. Outcome's count and last move are Rollout's. Each Dates row's Original is the plan workbook's, except Start's, which is the gate map's Date, and its Decided on and Decides are the gate map's. |
| 2 | Delivered. Does every deliverable say whether it was delivered, and who accepted it? | Every Id in the charter has a row. Accepted by isn't the Owner, and Accepted on is a weekday on or before Closed on. Delivered opens with As promised, Changed or Not delivered; Changed names a change, and Not delivered says where the work went. A Completed close has no Not delivered, and a Terminated one says why it stopped. |
| 3 | Accepted. Do the acceptance counts add up? | Met, Waived and Open add up to Criteria in all, which is the acceptance file's count. A Completed close has Open 0. Each Waived criterion names its decision log row. |
| 4 | The money adds up. Do the cost lines add up to Final cost? | Each Baselined is the charter's line and they add up to the Share. The Finals add up to the Total row, which is Final cost. Each Difference is Final minus Baselined, and the Differences add up to Against the share. Final cost is within the Owner's limit over the Share, or a change covers the rest. This checks the sums; whether Finance's figures are right is Finance's call. |
| 5 | The Register is updated. Does the Register show how the project ended? | Once Close is decided, the Register's Status is the word in Closed as, and its Forecast spend is Final cost. |
| 6 | Every change counted. Is every change since the baseline in Changes? | Changes runs from CH-1 with no number missing or used twice. Each Dates row with Moved in all above 0 names a change whose effect gives that many working days. Each change in the plan workbook's log or the decision log has a row, and so does each criterion whose wording or limit differs from the copy last signed. |
| 7 | What's left open. Does every open item have one owner, a day and a place? | Each Open items row has one Owner, written Name (Role), a Due that is a weekday or Date TBD (gated on …) naming what it waits for, and a Kept in. Every cost that goes on after cutover, in the charter, the RAID log or the handover, is an item, and every RAID line still open is in Open items or Passed to the program. Each First read gives a day, then Taken, Not taken or Not yet due. |
| 8 | Lessons. Is there a lesson, and can each be traced? | There is at least one lesson, and each Comes from is an id or a gate's name found elsewhere in this close. Whether another project could follow it is for a person. |
| 9 | Who signed. Has everyone signed this version? | The person who decides the close isn't the Owner, and the Reviewer is neither of them, or None. Everyone who takes the work over, in the charter and the handover, has a Handover row and a Sign-off row. With no Sponsor, the first row says standing in as sponsor. Status is Signed only when every row is complete and for the current version. While Status is Draft or Waiting to sign, the answer is Not yet. Once Status is Signed, anything missing is a no. Closed on is the Decides the close row's date, and Told isn't before it. |

# About this Example

Hollins Software is a made-up software company. Everyone in it is made up too.

This is the close of Billing Engine Rewrite on Wed 30 Jun 2027, the day Close is decided. All 1,460 customers are on the new engine, and it cost 9,600 less than its share.

It fails questions 5, 6 and 7 on purpose, and passes 1, 2, 3, 4, 8 and 9.

| 5 The Register is updated | The Register's Status reads Active; Closed as is Completed. The Register's Forecast spend is 780,000; Final cost is 770,400. Tomasz (PMO Head) hasn't typed either into the Register, so the gate map's Close line Final cost is entered on the Register isn't met yet. |
| --- | --- |
| 6 Every change counted | C-06's Pass line differs from the copy signed on Mon 28 Sep 2026, and no change names it. Its limit on severity 2 defects went from 0 to 3 or fewer on Thu 15 Oct 2026, and nobody logged it. C-05's Pass line differs from that copy too. Rhys (Finance Operations Lead) set it on Thu 5 Nov 2026, in place of Fast enough for month end, and no change names it. |
| 7 What's left open | Open items row 2, Switch off the old engine's licence and hosting, has no Kept in. |

Open items row 1 has no date yet. Its Due, Date TBD (gated on Finance Operations' FY28 budget request), passes question 7.

No sponsor was ever named. Priya (CTO) decides the close standing in, as she did at Go/no-go.

The people in Sign-off signed this version as it stands, with the three failures in it.

## Before you start

A project close records how the project ended and what it leaves behind: what was delivered and accepted, the final cost and dates, who took the work over and what is still open. It's signed on the day Close is decided, by the person who decides it, the Owner, a reviewer, each person who took the work over and the program manager.

Name, Sits under, Owner, Planned finish and Forecast spend are copied from the project's row on the Register, letter for letter, and the Sponsor from the program's row. Purpose, Benefit it serves, Share of the envelope, the deliverables and the cost lines are copied from the project charter. Dates come from the plan workbook and the gate map, Outcome from the cutover workbook's Rollout, and each Final from Finance's export by cost line.

Write every person as Name (Role), one person to a cell. A team never owns anything: name the one person who answers for it.

With no acceptance file, write under Acceptance what was agreed and who accepted it. With no gate map, Dates can be one line: the Planned finish beside Closed on.

Before anyone signs, someone who didn't write the close asks the nine review questions after Sign-off. Ask question 5 again once Close is decided and the portfolio manager has updated the Register.

Once it's signed, keep this file as it was signed. Open items and Passed to the program stay open after close, and Versions says which changes need signing again.

An assistant can check it for you. The brief is in frqz-project-close-agent-brief.txt, beside this file.

To use your own logo, right-click the FRQZ logo at the top right and choose Change Picture. In Google Docs, choose Replace image.