## Read me
Gate map workbook (Example)
One gate map per project: each gate in order, what has to be true before it's passed, who decides, who is asked first, and the review before it. Three tabs: Read me, Gates and Criteria.
Filling it in
1 | At the top of Gates, copy the project's Name, Sits under, Owner and Latest forecast from the Register.
2 | List the project's gates in order, one per row, each with its Kind and the Date it's due. A small project can use two gates, Start and Go/no-go.
3 | For each gate, name the one person who decides it and the people consulted. Pick the review before it, and type its reviewer and date. Type None if a gate has no review.
4 | On Criteria, write what must be true at each gate, one line each, with the person who says it's met and a Status. When a line is Met, say in Evidence where to see it.
5 | Read the five checks at the top of Gates, then the Check column on both tabs. Fix every line that shows △.
6 | When a gate is decided, type Decided on and Outcome together.
YOUR LOGO
The FRQZ logo is in cell A1 on every tab. To use your own, delete it and insert your logo in A1, on each tab.
KIND
Phase gate | The end of a stage of the work, such as Build complete or Readiness.
Go/no-go | The call on whether to go live.
Decision point | Any other decision, such as Start or Close.
OUTCOME
Go | Go ahead.
Revise | Do more work and bring the gate back.
Defer | Decide later.
Stop | End the work.
OPEN, MET AND WAIVED
Open | Not yet true. A blank Status counts as Open, and Check flags it.
Met | True, and Evidence says where to see it, with the date.
Waived | The person who decides lets the gate go ahead without it. Reason says who waived it and why.
STATE
No criteria yet | The gate has no lines on Criteria. It fails check 1 only once it's decided or due soon.
Ready to decide | Every line for the gate is Met or Waived.
3 of 4 open | How many of the gate's lines are still Open.
Decided: Go | The gate's Outcome.
REVIEWS
Each gate's review comes before its decision. Book it once the gate is due within the days set at the top of Gates (30 to start).
The reviewer should be someone other than the Owner or the person who decides the gate. If they aren't, Check shows △. You can keep it: in a small company they may be the only senior person.
If the result is Passed with actions, write the actions in Evidence or in the minutes. The file has no column for them.
TIMING
A gate that is decided, or due within the days set at the top of Gates (60 to start), needs at least one criterion. Gates further off read No criteria yet and pass, so you can list every gate on day one.
The checks count days from As of. Leave As of blank and they count from today, so a result can change overnight when a date passes.
DECIDED GATES
If a criterion goes back to Open after its gate was decided Go, check 4 fails again until the criterion is Met or waived with a reason.
Each gate has one row, so a gate decided a second time replaces the first decision. Note the earlier one in Evidence or in the minutes.
For a gate decided before you started the file, write its criteria as Met with the evidence you have, or leave the failure showing.
UPKEEP
Clear a row to remove it. Don't delete rows.
If you rename a gate, change the Gate cell on each of its lines on Criteria.
Decides takes one name. A comma or the word and in it fails check 2.
NAMES
Type each person the way the Register does: Anders (Engineering Manager). Check 3 compares first names, so Anders and Anders (Engineering Manager) count as the same person.
READING THE MARKS
△ | A check found something, and the words say what. Filter the Check column on △ to list the rows.
○ Clear | The check found nothing.
GREY CELLS
Grey cells are worked out from what you type. Don't type over them: a typed value replaces the formula.
CHECKS
Gates runs five checks, at the top of the tab. Each says what's wrong and names the first gate it found. Check, on each row of both tabs, says what's wrong with that gate or line.
OTHER FILES
Acceptance criteria stay in their own file. Add one line here at each gate where some are due: Every acceptance criterion due at this gate is Met or waived.
The project charter keeps each gate's date as it was signed, and this file keeps the date as it stands now. The assistant's brief compares the two.
Anyone who opens this file sees every row. To share it with someone outside the company, send them their lines, not the file.
An assistant can check the gate map for you. The brief is in frqz-gate-map-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results.
ABOUT THIS EXAMPLE
Hollins Software is a made-up software company. Everyone in it is made up too.
This is the gate map for Billing Engine Rewrite, as of 22 Oct 2026. Start and Plan baselined are decided. Build complete is 15 days away.
It fails four checks on purpose. Check 5 is clear.
Check 1 | Start was decided Go on 12 Mar 2026 with no criteria written down. One line on Criteria also names a gate called Go-live. Go-live is a milestone, never a gate.
Check 2 | Handover accepted has no one in Decides. Rhys (Finance Operations Lead) takes the engine over, but nobody has agreed that he decides the gate.
Check 3 | Plan baselined was reviewed by Anders, who owns the project and decides that gate. Readiness has its review on 24 Nov 2026, five days after the gate on 19 Nov.
Check 4 | Plan baselined was decided Go on 12 Jun 2026 with Hugo's line on cost and date tolerances still Open, and the line on dependencies Met with no evidence.
As of is set to 22 Oct 2026, so the results stay as they are. Clear it and the checks count from today.

## Gates
Gate map (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 22 Oct 2026. Clear the white cells to start your own.
PROJECT AND SETTINGS
Name | Billing Engine Rewrite
Sits under | Billing and Payments Program
Owner | Anders (Engineering Manager)
Latest forecast | 2027-06-30
As of | 2026-10-22
Book reviews this many days ahead | 30
Write criteria this many days ahead | 60
CHECKS
1 A gate with no criteria, or criteria with no gate
2 A gate without one person to decide it, or no one consulted
3 A gate review that's missing, late or not independent
4 A gate passed without its evidence
5 Gate dates that don't hold together
All checks
GATES
# | Gate | Kind | Date | Decides | Consulted | Review before it | Reviewer | Review date | Review result | Decided on | Outcome | Criteria | Met | Open | Waived | State | Check | Check 1: decided or due soon, no criteria (1 or 0) | Name used twice (1 or 0) | Check 2 (1 or 0) | Check 3: the reason | Waived lines with no reason | Met lines with no evidence | Check 4: the reason | Check 5: the reason
| Start | Decision point | 2026-03-12 | Priya (CTO) | Tomasz (PMO Head), Hugo (Program Manager) | Business case review | Tomasz (PMO Head) | 2026-03-09 | Passed | 2026-03-12 | Go
| Plan baselined | Phase gate | 2026-06-12 | Anders (Engineering Manager) | Hugo (Program Manager), Imani (Security Lead) | Plan and estimate review | Anders (Engineering Manager) | 2026-06-09 | Passed | 2026-06-12 | Go
| Build complete | Phase gate | 2026-11-06 | Anders (Engineering Manager) | Hugo (Program Manager), Kofi (Delivery Lead) | Security and code review | Imani (Security Lead) | 2026-11-03
| Readiness | Phase gate | 2026-11-19 | Anders (Engineering Manager) | Hugo (Program Manager), Imani (Security Lead), Noor (Support Lead) | Rehearsal review | Kofi (Delivery Lead) | 2026-11-24
| Go/no-go | Go/no-go | 2026-12-03 | Priya (CTO) | Hugo (Program Manager), Anders (Engineering Manager), Imani (Security Lead), Noor (Support Lead) | Independent readiness review | Tomasz (PMO Head) | 2026-12-01
| Handover accepted | Phase gate | 2027-05-28 |  | Hugo (Program Manager), Anders (Engineering Manager), Noor (Support Lead), Rhys (Finance Operations Lead) | Handover review
| Close | Decision point | 2027-06-30 | Priya (CTO) | Hugo (Program Manager), Tomasz (PMO Head) | Closure report review | Tomasz (PMO Head)
Note on C10: Worked out: the date the checks count from. It's As of, or today when As of is blank.
Note on A22: Worked out: the gate's place in the list.
Note on M22: Worked out: how many lines on Criteria name this gate.
Note on N22: Worked out: how many of them are Met.
Note on O22: Worked out: how many are Open. A blank Status counts as Open.
Note on P22: Worked out: how many are Waived.
Note on Q22: Worked out: decided, ready to decide, or how many criteria are still open.
Note on R22: The first thing wrong with this gate. Filter on △ to list them.

## Criteria
Criteria (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 22 Oct 2026. Clear the white cells to start your own.
CRITERIA
Gate | Criterion | Owner (says it's met) | Status | Reason | Evidence | Check | Names no gate on Gates (1 or 0) | Waived with no reason (1 or 0) | Met with no evidence (1 or 0)
Plan baselined | Every item has an owner and an estimate | Anders (Engineering Manager) | Met |  | Work breakdown v1, 12 Jun 2026
Plan baselined | Dependencies on other teams are recorded, each with a date from that team | Anders (Engineering Manager) | Met
Plan baselined | Cost and date tolerances are agreed with the program manager | Hugo (Program Manager) | Open
Plan baselined | The test approach is agreed with the Security Lead | Imani (Security Lead) | Met |  | Test approach v1, 10 Jun 2026
Build complete | Every item is done, or moved by a recorded decision | Anders (Engineering Manager) | Open
Build complete | Every acceptance criterion due at this gate is Met or waived | Anders (Engineering Manager) | Open
Build complete | No security finding rated high or critical is open | Imani (Security Lead) | Open
Build complete | Every change since the plan was baselined is decided | Hugo (Program Manager) | Met |  | Change log, 20 Oct 2026
Build complete | Every open risk has an owner and a response | Anders (Engineering Manager) | Open
Readiness | The cutover rehearsal has passed | Anders (Engineering Manager) | Open
Readiness | Rollback has been tested | Anders (Engineering Manager) | Open
Readiness | Every cutover step has a named owner | Anders (Engineering Manager) | Open
Readiness | Support is trained on the new invoice screens | Noor (Support Lead) | Open
Go/no-go | The Readiness gate is decided | Hugo (Program Manager) | Open
Go/no-go | Every Readiness criterion is Met, or waived with a reason | Hugo (Program Manager) | Open
Go/no-go | The rollback owner and the fallback are named | Anders (Engineering Manager) | Open
Go/no-go | Support is staffed for the cutover weekend, 12 and 13 Dec 2026 | Noor (Support Lead) | Open
Handover accepted | Finance Operations has closed a month on the new engine | Rhys (Finance Operations Lead) | Open
Handover accepted | Support has handled billing tickets for four weeks without the build team | Noor (Support Lead) | Open
Handover accepted | The runbooks are in the support team's wiki | Noor (Support Lead) | Open
Close | Every customer is on the new engine, the last at its renewal | Hugo (Program Manager) | Open
Close | The lessons are written down | Anders (Engineering Manager) | Open
Close | Final cost is entered on the Register | Tomasz (PMO Head) | Open
Go-live | US customers billed monthly are told about the cutover weekend by 1 Dec 2026 | Noor (Support Lead) | Open
Note on G7: The first thing missing from this line. Filter on △ to list them.