## Read me
RAID log
One list of a project's risks, assumptions, issues and dependencies, each with one owner and a date to look at it again. Three tabs: Read me, Summary and Log.
Where to start
Start with the risks and dependencies in the project charter. Copy them onto Log by hand, with their look-again dates, then add the rest as they come up. Log holds 150 lines.
Filling it in
1 | On Summary, type the project's Name, Sits under and Owner as the Register has them, and the day you're reviewing on in As of.
2 | On Log, add a line in the next empty row for each risk, assumption, issue and dependency. Give it the Next Id from Summary, one owner written like Imani (Security Lead), and a date to look at it again.
3 | For a risk or an issue, type what is being done in Response the day you raise it.
4 | Rate Impact on every line, and Likelihood on risks and assumptions.
5 | For a dependency, fill in Provided by, Who answers and Needed by.
6 | Read the seven checks on Summary, and fix every line whose Row check shows △.
7 | When a line is over, set Status to Closed and fill in Closed on and Why closed.
YOUR LOGO
The FRQZ logo is at the top of each tab. To use your own, delete it and insert your logo in the same place.
THE FOUR KINDS
Risk | Might happen, and would hurt if it did.
Assumption | Counted on, not confirmed.
Issue | Has happened and needs fixing.
Dependency | Needed from someone outside the team, by a date.
Ids | Each kind has its own Id letter: R, A, I and X. Dependencies take X because the project charter uses D for its deliverables.
STATUS
Raised | Written down. Nobody is acting on it yet.
Responding | Someone is acting on it, and Response says what.
Closed | Over. Closed on and Why closed say when, and what shows it.
Open | Open, on Summary, means Raised or Responding.
NAMES
Write each owner as one person with their role in brackets, the way the Register writes an Owner: Anders (Engineering Manager). Who answers on a dependency is written the same way. The Stakeholders file matches its names against these, so type each person the same way every time.
LOOK AGAIN ON
Look again on is the next day someone reads the line. It falls between As of on Summary and 60 days after it, and on a dependency, no later than Needed by. Change the 60 in Look again within on Summary. Pick a weekday.
CLOSING A LINE
1 | Closing a line needs a date and a reason. Write what shows it's over, not "done". If a risk happens, close it with the reason "Happened, see I3" and raise the issue.
2 | Don't reopen a closed line: raise a new one with the next Id. A closed line set back to Raised or Responding can't be read until Closed on and Why closed are cleared.
3 | Summary lists every high-impact line closed since Last reviewed, so the project's Owner reads each one.
THE PROGRAM
1 | Set With the program to Yes when the program needs to watch a line. It stays this project's line, with its owner. Clear it to take it back. The project's Owner decides both.
2 | A dependency on another project, in this program or another, is kept on the program workbook's Dependencies tab. Add a line here too, with Kept in set to Program workbook, so you can see it.
3 | Summary counts that line under In the program workbook. The owner, look-again and Needed by checks skip it: the program workbook watches those.
4 | A dependency on anything else stays in this log as a full line: a team, a supplier, or a project that sits under no program. For a project under no program, tell the portfolio manager too, since no program workbook holds it.
READING THE MARKS
△ | A check found something, and the words say what. Filter Row check on Log on △ to list the lines.
○ Clear | The check found nothing. Every check reads clear until a line is typed.
THE CHECKS
Summary runs seven checks on the lines on Log, counting from As of. Each result names the first line that fails, and Row check on Log says what is wrong with each line.
1 | An open line without one named owner: Owner isn't written as Name (Role), or the name holds a comma, a slash, "and" or "&". Engineering managers fails; Imani (Security Lead) passes.
2 | A look-again date missing, passed or too far ahead: Look again on is blank, before As of, more than the Look again within days after As of, or after the line's Needed by.
3 | An open risk or issue with no response: Response is blank. Assumptions and dependencies don't need one.
4 | A line closed without a date or a reason: Status is Closed and Closed on or Why closed is blank.
5 | An open dependency missing who provides it, who answers or when: Provided by or Needed by is blank, or Who answers isn't written as Name (Role).
6 | A dependency past its Needed by date: an open dependency kept in this log whose Needed by is before As of.
7 | A line the log can't read: an Id that is blank, used twice or doesn't start with its Kind's letter; a Kind, Status, Impact or Likelihood not on its list; a date typed as text; or Closed on or Why closed filled in on an open line.
The checks count lines and compare dates. They can't tell whether a response is any good, whether the owner agreed to own it, whether a closing reason is true, or whether a team has been typed as a person, such as The team (Engineering).
Before Build complete, the gate map asks that every open risk has an owner and a response. The owner and response checks here answer it.
THE WORKING
1 | Grey cells are worked out from what you type, and locked so they aren't typed over. There's no password.
2 | The working is in hidden columns: T to AJ on Log, each with a header, and K on Summary, labelled in J. Unhide them to read it.
3 | Rows can't be inserted or deleted, so every line stays counted. Clear a row to remove a line. To sort, unprotect the sheet first and protect it again after.
OTHER FILES
1 | The project charter holds a signed copy of the risks and dependencies that would stop the project. This log is the live list, and starts with those lines.
2 | The Decision log and the Status report cite a line by its Id, so keep each Id for good.
3 | Anyone who opens this file sees every line. To share it with someone outside the company, send them their lines, not the file.
4 | An assistant can check the log for you. The brief is in frqz-raid-log-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results. It never sets an owner, a rating or a status, and never closes a line.
5 | FRQZ keeps a project's risks and issues with the same Owner, Impact, Likelihood, Response and Status words, so a line reads the same in both.

## Summary
Summary | [7 empty] | Lines in use
Open lines
Closed lines
As of, as the checks use it
PROJECT | [7 empty] | Look again within, as the checks use it (days)
NAME | [7 empty] | Last reviewed, as the list uses it (0 if blank)
SITS UNDER | [7 empty] | High-impact lines closed since the last review
OWNER
AS OF
LAST REVIEWED
LOOK AGAIN WITHIN (DAYS)
COUNTS
Kind | Raised | Responding | Closed | In the program workbook | Open | Of those, with the program | Next Id
Risk
Assumption
Issue
Dependency
Total
CHECKS
Checks failing
An open line without one named owner
A look-again date missing, passed or too far ahead
An open risk or issue with no response
A line closed without a date or a reason
An open dependency missing who provides it, who answers or when
A dependency past its Needed by date
A line the log can't read
HIGH-IMPACT LINES CLOSED
Id | What | Closed on | Why closed
Note on B14: Open lines kept in this log that nobody is acting on yet.
Note on C14: Open lines kept in this log that someone is acting on.
Note on D14: Every closed line, including lines that point to the program workbook.
Note on E14: Open lines kept on the program workbook's Dependencies tab. This log only points to them.
Note on F14: Raised, Responding and In the program workbook, added up.
Note on G14: Open lines whose With the program is Yes. The program watches them; they're still this project's lines.
Note on H14: The Id to give the next line of this kind. Never reuse an Id, even when a line has been cleared.
Note on A31: Every line with Impact High closed on or after Last reviewed, for the project's Owner to read. Blank Last reviewed lists every one. A list, not a check.

## Log
Log
Id | Kind | What | Owner | Raised on | Look again on | Impact | Likelihood | Response | Status | Closed on | Why closed | With the program | Provided by | Who answers | Needed by | Kept in | Row check | Line in use (1 or 0) | Open (1 or 0) | Open and kept in this log (1 or 0) | Fails: owner not one named person (1 or 0) | Fails: look-again date (1 or 0) | Fails: no response (1 or 0) | Fails: closed without a date or a reason (1 or 0) | Fails: dependency missing a provider, who answers or a date (1 or 0) | Fails: dependency past Needed by (1 or 0) | Id blank, used twice or not matching Kind (1 or 0) | A word not on its list, or closing text on an open line (1 or 0) | A date cell that isn't a date (1 or 0) | Fails: the log can't read the line (1 or 0) | Helper, worked out | Owner's name, before the bracket | Impact High, closed since Last reviewed (1 or 0) | Its place in the Summary's closed list