## Read me
Cutover workbook (Example)
One workbook for a cutover: the Readiness and Go/no-go criteria and decisions, the runbook, the rollback and the rollout in waves. Ten tabs: Read me, Details, Readiness, Go-no-go, Runbook, Rollback, Rollout, Conditions, Moves and Checks.
Filling it in
1 | On Details, copy the project's Name, Sits under, Owner, Planned finish and Sponsor from the Register. Type the window, the rollback point and limit, and who decides each gate.
2 | On Readiness, copy each Readiness and Go/no-go criterion from the gate map or the acceptance and sign-off file, word for word, with its owner. Mark each one Met, with its evidence, as it comes true.
3 | On Runbook, list every step in time order, each with its Kind, one owner and how to stop or undo it.
4 | On Rollback, list the rollback steps in order, each with one owner. Time a rollback at each rehearsal and type the minutes.
5 | On Rollout, list the waves in the order they open. Type each wave's conditions on Conditions and its months on Moves.
6 | When a gate is decided, type its Decided on and Outcome on Go-no-go together.
7 | Read Checks, then the Check column on each tab. Fix every line that shows △.
YOUR LOGO
The FRQZ logo is at the top of each tab. To use your own, delete it and insert your logo in the same place.
GATES
Readiness | Everything for the window is in place: rehearsed, rollback tested, every step owned, support trained.
Go/no-go | The call on whether to go live.
Go-live | A milestone, never a gate. The Gate column takes Readiness or Go/no-go only.
OPEN, MET AND WAIVED
Open | Not yet true, or no longer true.
Met | True, and Evidence says where to see it, with the date.
Waived | The gate's decider lets it go ahead without it. Waived by, Reason and Met or waived on say who, why and when.
WAIVERS
If a criterion goes back to Open after its gate was decided Go, check 2 fails until it is Met again or waived.
After a Go, only the gate's decider may waive a criterion that went back to Open, with a reason and a date. The assistant's brief checks the name.
OUTCOME
Go | Go ahead.
Revise | Do more work and bring the gate back.
Defer | Decide later.
Stop | End the work.
KIND
Prepare | Gets something ready, and changes nothing customers or the books see. It may come up to a day before the window.
Check | Confirms something is true, such as invoice counts that match.
Change | Alters what customers or the books see. It needs Stop or undo.
Hold | Waits or watches, such as overnight. It may come up to a day after the window.
Decision | A call made in the window, such as carry on or roll back.
TIMES
Every time in the file is in the time zone on Details. Type a date and a time, such as 12 Dec 2026 06:00.
The file doesn't adjust for a clock change. If one falls in the window, say so in the step it touches.
The runbook holds the window and a day either side. The week after the window belongs to the handover.
ROLLBACK
Rollback point is the last time the change can be rolled back. After it, a problem is fixed forward.
Rollback limit is the most hours a rollback may take. Time one at each rehearsal, in minutes, from the call to the old system working again. Check 6 reads the last rehearsal on the list.
WAVES
Wave 1 can be the cutover weekend itself. Each later wave needs a condition on Conditions, due by the day it opens.
Type each wave's conditions on its own rows. A later wave inherits none, so a condition two waves need is typed twice.
Moves plans each wave month by month, by the first day of the month. Once a wave is due to open within 60 days, its Moves must add up to its Customers.
Fill in Moved so far as the rollout runs. Check 9 compares it with Moves for each month that has ended.
NAMES
Type each person the way the Register does: Anders (Engineering Manager). The checks read the name before the bracket, and fail a comma, the word and, or the word team or group.
A numbered post, such as Backend engineer 1, is one person and can own a step.
READING THE MARKS
△ | A check found something, and the words say what. Filter the Check column on △ to list the rows.
○ Clear | The check found nothing.
GREY CELLS
Grey cells are worked out from what you type. Don't type over them: a typed value replaces the formula.
The working is in hidden columns, each with a header: N to U on Readiness, K to N on Runbook, N to R on Rollout and L to O on Conditions.
CHECKS
Checks runs nine checks. Each result names the first row that fails, and Check on each row says what's wrong with it.
Check 3 reads Readiness only once something is typed on it. A project with no Readiness gate leaves Readiness empty, and Readiness decided by blank.
LIMITS
Rollout counts customers, not partners. The partners' notice is kept in the stakeholders file.
Check 2 is the gate map's check 4, A gate passed without its evidence, run on Readiness and Go/no-go only.
The checks can't tell whether the fallback still runs, or whether an undo would work. The assistant's brief asks the owners.
The owner checks can't catch a team written another way, such as Backend engineers. The assistant's brief looks for that.
UPKEEP
Clear a row to remove it. Don't delete rows.
OTHER FILES
The gate map holds the same criteria, word for word, and copies their status at each decision. A criterion taken from the acceptance and sign-off file keeps that file's wording. This file tracks them in the weeks before the call.
The decision log is the record of each decision. Decided by, Decided on and Outcome here are copies.
Window opens has the same start date as Cutover weekend in the plan workbook. The times and the end are kept only here.
Rollback owner is the person the RACI names for rolling back. The test evidence keeps each rehearsal's run, and this file the minutes.
The handover reads Still to move from Rollout.
Anyone who opens this file sees every row. To share it with someone outside the company, send them their lines, not the file.
An assistant can check the cutover workbook for you. The brief is in frqz-cutover-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results.
ABOUT THIS EXAMPLE
Hollins Software is a made-up software company. Everyone in it is made up too.
This is the cutover workbook for Billing Engine Rewrite, as of Fri 11 Dec 2026, the day before the cutover weekend. Readiness was decided Go on 19 Nov 2026 and Go/no-go on 3 Dec 2026. Nothing of the weekend has happened yet.
It fails two checks on purpose. The other seven are clear.
Check 5 | Step 6 loads the open invoices, balances and plans into the new engine, and Stop or undo is blank. Nothing says how to undo it.
Check 8 | The tax rule list, a condition for wave 3, has no Needed by date. Rhys (Finance Operations Lead) owns it, and the Program board's notes of 22 Oct 2026 say no date is set for the sign-off yet.
Every criterion, step and condition has one person as its owner. Where a team helps, as Rhys's team does with the export, it's in With.
Priya (CTO) decides the Go/no-go, standing in as portfolio director, because Billing and Payments Program has no sponsor yet.
G1 to G8 copy the gate map's criteria word for word. G9 is the gate map's Go-live line on the customer notice, read at Go/no-go. G10 to G12 come from the acceptance criteria, read at Go/no-go.
As of on Details is 11 Dec 2026, so the results stay as they are. Clear it and the checks count from today.

## Details
Details (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 11 Dec 2026. Clear the white cells to start your own.
| Name | Billing Engine Rewrite
| Sits under | Billing and Payments Program
| Owner | Anders (Engineering Manager)
| Planned finish | 2027-06-30
| Sponsor | Not yet named
| Kept by | Anders (Engineering Manager)
| As of | 2026-12-11
| Time zone | Hollins's local time
| Window opens | 2026-12-12 06:00
| Window closes | 2026-12-13 18:00
| Rollback point | 2026-12-13 12:00
| Rollback limit (hours) | 4
| Rollback owner | Anders (Engineering Manager)
| Fallback | The old engine, read-only until 12:00 on Sun 13 Dec 2026
| Readiness decided by | Anders (Engineering Manager)
| Go/no-go decided by | Priya (CTO)
| Customers in all | 1460
Checks count from
Note on C22: Worked out: the date the checks count from. It's As of, or today when As of is blank.

## Readiness
Readiness (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 11 Dec 2026. Clear the white cells to start your own.
# | Id | Gate | Criterion | Owner (says it's met) | Status | Met or waived on | Evidence | Waived by | Reason | Note | Check | Owner, before any bracket | In use (1 or 0) | The first fault | Waiver or evidence fault | Its gate decided Go (1 or 0) | Open after a Go | Open, in order | Gate, when Open
| G1 | Readiness | The cutover rehearsal has passed | Anders (Engineering Manager) | Met | 2026-11-14 | Rehearsal 1 report, 14 Nov 2026
| G2 | Readiness | Rollback has been tested | Anders (Engineering Manager) | Met | 2026-11-14 | C-08, rehearsal 1: rollback in 3 hours 10 minutes, 14 Nov 2026
| G3 | Readiness | Every cutover step has a named owner | Anders (Engineering Manager) | Met | 2026-11-12 | Runbook v1, sent to Rhys 12 Nov 2026
| G4 | Readiness | Support is trained on the new invoice screens | Noor (Support Lead) | Met | 2026-11-17 | Training sessions, 16 and 17 Nov 2026
| G5 | Go/no-go | The Readiness gate is decided | Hugo (Program Manager) | Met | 2026-11-19 | Decision log, 19 Nov 2026
| G6 | Go/no-go | Every Readiness criterion is Met, or waived with a reason | Hugo (Program Manager) | Met | 2026-11-19 | G1 to G4 Met, none waived, 19 Nov 2026
| G7 | Go/no-go | The rollback owner and the fallback are named | Anders (Engineering Manager) | Met | 2026-11-19 | Anders owns the rollback; the fallback is the old engine, read-only until 12:00 on Sun 13 Dec 2026
| G8 | Go/no-go | Support is staffed for the cutover weekend, 12 and 13 Dec 2026 | Noor (Support Lead) | Met | 2026-11-26 | The weekend roster: three support staff each day, 26 Nov 2026
| G9 | Go/no-go | US customers billed monthly are told about the cutover weekend by 1 Dec 2026 | Noor (Support Lead) | Met | 2026-12-01 | Hugo's notice, sent 1 Dec 2026 to 910 customers and the partners
| G10 | Go/no-go | The rollback is under 4 hours (C-08) | Priya (CTO) | Met | 2026-11-28 | C-08, rehearsal 2: 2 hours 55 minutes, 28 Nov 2026
| G11 | Go/no-go | Support answers 10 billing questions from the runbook alone (C-10) | Noor (Support Lead) | Met | 2026-12-01 | 10 of 10 answered, 1 Dec 2026
| G12 | Go/no-go | Credit notes and refunds match Finance's figures (C-12) | Rhys (Finance Operations Lead) | Met | 2026-11-18 | 10 of 10 match, 18 Nov 2026
Note on A5: Worked out: the criterion's place in the list.
Note on L5: The first thing wrong with this criterion. Filter on △ to list them.

## Go-no-go
Go/no-go (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 11 Dec 2026. Clear the white cells to start your own.
| Gate | Readiness | Go/no-go
Decided by
| Gate date | 2026-11-19 | 2026-12-03
Criteria
Met
Waived
Open
| Decided on | 2026-11-19 | 2026-12-03
| Outcome | Go | Go
| Note |  | Priya stands in as portfolio director. No sponsor has been named.
State
Check
WINDOW
Window opens
Window closes
Time zone
Rollback point
Rollback limit (hours)
Rollback owner
Fallback
Last rollback timed (minutes)
First wave told on
Steps
Change steps with no undo
OPEN CRITERIA
| Criterion | Owner (says it's met) | Gate
Note on B6: Worked out: Readiness decided by and Go/no-go decided by, from Details.
Note on B8: Worked out: how many criteria on Readiness name this gate.
Note on B9: Worked out: how many of them are Met.
Note on B10: Worked out: how many are Waived.
Note on B11: Worked out: how many are still Open.
Note on B15: Worked out: decided, ready to decide, or how many criteria are still open.
Note on B16: Worked out: what's wrong with a Go. Clear when the gate isn't Go, or nothing is wrong.

## Runbook
Runbook (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 11 Dec 2026. Clear the white cells to start your own.
# | When | Step | Kind | Owner | With | Stop or undo | Done at | Check | In use (1 or 0) | The first fault | Change with no undo (1 or 0) | Owner, before any bracket
| 2026-12-11 23:00 | Back up the old engine | Prepare | Backend engineer 2
| 2026-12-12 06:00 | Open the call; roll call; the Payments processor's contact is on the line | Prepare | Anders (Engineering Manager) | The Payments processor's contact
| 2026-12-12 06:30 | Confirm the backup taken Fri 11 Dec 23:00 restores on the staging copy | Check | Backend engineer 1 |  | If it won't restore, stop; nothing has changed
| 2026-12-12 07:00 | Freeze: the old engine stops issuing invoices and accepting plan changes; the support banner goes up | Change | Anders (Engineering Manager) | Noor (Support Lead) | Unfreeze
| 2026-12-12 08:00 | Export open invoices, balances and plans for the 910 customers | Prepare | Rhys (Finance Operations Lead) | Rhys's team
| 2026-12-12 10:00 | Load the open invoices, balances and plans into the new engine, with the billing history | Change | Backend engineer 1 | Backend engineers 2 and 3
| 2026-12-12 13:00 | Count check: invoice counts match in old and new, 0 missing | Check | Anders (Engineering Manager) |  | Stop point 1: if it fails, stop, unfreeze and tell Hugo
| 2026-12-12 14:00 | Sample check: the 40 sample accounts compared | Check | Anders (Engineering Manager) | Build agent
| 2026-12-12 16:00 | Ledger check: totals agree with the ledger to the cent | Check | Esi (Finance Operations Analyst) | Rhys (Finance Operations Lead) | Stop point 2: if it fails, stop and unfreeze
| 2026-12-12 17:00 | Hold overnight; the freeze stays; Anders on call | Hold | Anders (Engineering Manager)
| 2026-12-13 06:00 | Call reopens; read the overnight job logs | Check | Anders (Engineering Manager)
| 2026-12-13 07:00 | Switch: invoice events from the customer platform go to the new engine; the old engine is set read-only and stays on | Change | Backend engineer 2 |  | Point the events back to the old engine
| 2026-12-13 08:00 | Switch the Payments processor connection; five test payments through the processor's test environment | Change | Backend engineer 1 | The Payments processor's contact | Point the connection back
| 2026-12-13 09:30 | Smoke test on 10 live accounts: a new subscription, a plan change, a credit note, a refund | Check | Esi (Finance Operations Analyst) | Build agent
| 2026-12-13 11:30 | Carry on or roll back; Rhys and Esi say whether the figures stand | Decision | Anders (Engineering Manager) | Rhys (Finance Operations Lead), Esi (Finance Operations Analyst)
| 2026-12-13 12:00 | Rollback point: the new engine takes live payments | Change | Anders (Engineering Manager) |  | Before 12:00, roll back: the old engine is back in at most 4 hours (rehearsed in 3 h 10 and 2 h 55). From 12:00, fixed forward
| 2026-12-13 12:00 | Watch payment failures, support tickets and job logs until 16:00 | Hold | Anders (Engineering Manager) | Noor (Support Lead), Imani (Security Lead)
| 2026-12-13 16:00 | Final check; write the weekend report; tell Hugo and Priya | Check | Anders (Engineering Manager) | Hugo (Program Manager), Priya (CTO)
| 2026-12-13 18:00 | Close the call; name the Monday morning cover | Hold | Anders (Engineering Manager)
Note on A5: Worked out: the step's number.
Note on I5: The first thing wrong with this step. Filter on △ to list them.

## Rollback
Rollback (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 11 Dec 2026. Clear the white cells to start your own.
STEPS
# | Step | Owner | Check
| Call the rollback | Anders (Engineering Manager)
| Point invoice events back to the old engine | Backend engineer 2
| Set the old engine to read-write | Backend engineer 2
| Switch payments back to the old engine | Backend engineer 1
| Replay the invoice events since the freeze (none before 12:00) | Backend engineer 1
| Smoke test on the old engine | Esi (Finance Operations Analyst)
| Tell Noor, Hugo and Priya | Anders (Engineering Manager)
REHEARSALS
# | Rehearsal | Date | Rollback timed (minutes) | Time | Against the limit | Evidence
| Rehearsal 1, on the staging copy | 2026-11-14 | 190 |  |  | Test evidence, C-08, rehearsal 1
| Rehearsal 2, on the staging copy | 2026-11-28 | 175 |  |  | Test evidence, C-08, rehearsal 2
Note on D5: The first thing missing from this step.
Note on E29: Worked out: the minutes as hours and minutes.
Note on F29: Worked out: against the Rollback limit on Details.

## Rollout
Rollout (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 11 Dec 2026. Clear the white cells to start your own.
Wave | Who | Customers | Opens | Why in this order | Told on | Told by | Last move | Moved so far | Scheduled | Still to move | Check | Due to have moved by now | Latest Needed by of its conditions | Check 7: the fault | Check 8: the fault | Check 9: the fault
| US customers billed monthly | 910 | 2026-12-12 | Moves before the January renewals | 2026-12-01 | Hugo (Program Manager) | 2026-12-13
| US customers on annual contracts | 210 | 2027-02-01 | Needs the customer accounts on the new platform (X2) | 2027-01-18 | Hugo (Program Manager) | 2027-06-28
| Customers outside the US | 340 | 2027-02-12 | Waits for the tax rules as well (X1) | 2027-01-18 | Hugo (Program Manager) | 2027-06-28
Note on A5: Worked out: the wave's number. Conditions and Moves find the wave by it.
Note on J5: Worked out: Customers moving for this wave, added up from Moves.
Note on K5: Worked out: Customers minus Moved so far.
Note on L5: The first thing wrong with this wave. Filter on △ to list them.

## Conditions
Conditions (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 11 Dec 2026. Clear the white cells to start your own.
# | Wave | Condition | Owner | Needed by | Status | Evidence or reason | RAID Id | Note | Check | In use (1 or 0) | The first fault | Owner, before any bracket | Needed by, as a number
| 2 | December's month-end is closed | Rhys (Finance Operations Lead) | 2027-01-08 | Open
| 2 | No severity 1 defect is open | Anders (Engineering Manager) | 2027-01-29 | Open
| 2 | The second-wave notice has gone to the 550 customers | Hugo (Program Manager) | 2027-01-18 | Open
| 2 | Their customer accounts are on the new platform | Kofi (Delivery Lead) | 2027-01-29 | Open |  | X2
| 3 | December's month-end is closed | Rhys (Finance Operations Lead) | 2027-01-08 | Open
| 3 | No severity 1 defect is open | Anders (Engineering Manager) | 2027-01-29 | Open
| 3 | The second-wave notice has gone to the 550 customers | Hugo (Program Manager) | 2027-01-18 | Open
| 3 | Their customer accounts are on the new platform | Kofi (Delivery Lead) | 2027-01-29 | Open |  | X2
| 3 | The tax rules for customers outside the US have arrived | Hugo (Program Manager) | 2027-02-01 | Open |  | X1
| 3 | The tax rule list is signed off | Rhys (Finance Operations Lead) |  | Open |  |  | No date yet for the sign-off (Program board notes, 22 Oct 2026, line 9)
Note on A5: Worked out: the condition's place in the list.
Note on J5: The first thing wrong with this condition. Filter on △ to list them.

## Moves
Moves (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 11 Dec 2026. Clear the white cells to start your own.
Wave | Month | Customers moving | Moved | Check
1 | 2026-12-01 | 910
2 | 2027-02-01 | 40
2 | 2027-03-01 | 50
2 | 2027-04-01 | 60
2 | 2027-05-01 | 40
2 | 2027-06-01 | 20
3 | 2027-02-01 | 30
3 | 2027-03-01 | 50
3 | 2027-04-01 | 50
3 | 2027-05-01 | 100
3 | 2027-06-01 | 110
Note on E5: The first thing wrong with this row.

## Checks
Checks (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 11 Dec 2026. Clear the white cells to start your own.
# | Check | Result | Rule
1 | A criterion with no Id, gate, owner or status |  | Each criterion on Readiness has an Id used once, the gate Readiness or Go/no-go, a criterion, one person as owner and a status.
2 | A gate passed without its evidence |  | A gate decided Go has no Open criterion, no waiver missing its name, reason or date, and no Met line without evidence.
3 | A go/no-go missing its decider or fallback, or with dates out of order |  | Each decider is one name, the rollback owner and fallback are filled in, the window and rollback point are in order, and Readiness was Go on or before the Go/no-go.
4 | A step out of place, or with no time, Kind or owner |  | Each runbook step has a time, a Kind and one owner, comes no earlier than the step above, and falls in the window, or within a day of it for a Prepare or a Hold.
5 | A Change step with no way to undo it |  | Each Change step says in Stop or undo how to undo it, or says None, fixed forward.
6 | A rollback not written, owned or timed within the limit |  | Once any rollback detail is typed, a runbook step sits at the Rollback point, each rollback step has one owner, and the last rehearsal is timed within the limit.
7 | A rollout that doesn't add up |  | The waves add up to Customers in all and open in order, each wave opening within 60 days has Moves that add up to its Customers, and no wave has moved more than its Customers.
8 | A wave condition or notice that's incomplete or late |  | Each wave is told before it opens, each wave after the first has a condition due by then, and each condition has one owner, a date and a status.
9 | A wave that runs late |  | Each wave's Last move is on or after Opens and by the Planned finish, and Moved so far keeps up with the Moves plan for months that have ended.
All checks