## Read me
Cutover workbook
One workbook for a cutover: the Readiness and Go/no-go criteria and decisions, the runbook, the rollback and the rollout in waves. Ten tabs: Read me, Details, Readiness, Go-no-go, Runbook, Rollback, Rollout, Conditions, Moves and Checks.
Filling it in
1 | On Details, copy the project's Name, Sits under, Owner, Planned finish and Sponsor from the Register. Type the window, the rollback point and limit, and who decides each gate.
2 | On Readiness, copy each Readiness and Go/no-go criterion from the gate map or the acceptance and sign-off file, word for word, with its owner. Mark each one Met, with its evidence, as it comes true.
3 | On Runbook, list every step in time order, each with its Kind, one owner and how to stop or undo it.
4 | On Rollback, list the rollback steps in order, each with one owner. Time a rollback at each rehearsal and type the minutes.
5 | On Rollout, list the waves in the order they open. Type each wave's conditions on Conditions and its months on Moves.
6 | When a gate is decided, type its Decided on and Outcome on Go-no-go together.
7 | Read Checks, then the Check column on each tab. Fix every line that shows △.
YOUR LOGO
The FRQZ logo is at the top of each tab. To use your own, delete it and insert your logo in the same place.
GATES
Readiness | Everything for the window is in place: rehearsed, rollback tested, every step owned, support trained.
Go/no-go | The call on whether to go live.
Go-live | A milestone, never a gate. The Gate column takes Readiness or Go/no-go only.
OPEN, MET AND WAIVED
Open | Not yet true, or no longer true.
Met | True, and Evidence says where to see it, with the date.
Waived | The gate's decider lets it go ahead without it. Waived by, Reason and Met or waived on say who, why and when.
WAIVERS
If a criterion goes back to Open after its gate was decided Go, check 2 fails until it is Met again or waived.
After a Go, only the gate's decider may waive a criterion that went back to Open, with a reason and a date. The assistant's brief checks the name.
OUTCOME
Go | Go ahead.
Revise | Do more work and bring the gate back.
Defer | Decide later.
Stop | End the work.
KIND
Prepare | Gets something ready, and changes nothing customers or the books see. It may come up to a day before the window.
Check | Confirms something is true, such as invoice counts that match.
Change | Alters what customers or the books see. It needs Stop or undo.
Hold | Waits or watches, such as overnight. It may come up to a day after the window.
Decision | A call made in the window, such as carry on or roll back.
TIMES
Every time in the file is in the time zone on Details. Type a date and a time, such as 12 Dec 2026 06:00.
The file doesn't adjust for a clock change. If one falls in the window, say so in the step it touches.
The runbook holds the window and a day either side. The week after the window belongs to the handover.
ROLLBACK
Rollback point is the last time the change can be rolled back. After it, a problem is fixed forward.
Rollback limit is the most hours a rollback may take. Time one at each rehearsal, in minutes, from the call to the old system working again. Check 6 reads the last rehearsal on the list.
WAVES
Wave 1 can be the cutover weekend itself. Each later wave needs a condition on Conditions, due by the day it opens.
Type each wave's conditions on its own rows. A later wave inherits none, so a condition two waves need is typed twice.
Moves plans each wave month by month, by the first day of the month. Once a wave is due to open within 60 days, its Moves must add up to its Customers.
Fill in Moved so far as the rollout runs. Check 9 compares it with Moves for each month that has ended.
NAMES
Type each person the way the Register does: Anders (Engineering Manager). The checks read the name before the bracket, and fail a comma, the word and, or the word team or group.
A numbered post, such as Backend engineer 1, is one person and can own a step.
READING THE MARKS
△ | A check found something, and the words say what. Filter the Check column on △ to list the rows.
○ Clear | The check found nothing.
GREY CELLS
Grey cells are worked out from what you type. Don't type over them: a typed value replaces the formula.
The working is in hidden columns, each with a header: N to U on Readiness, K to N on Runbook, N to R on Rollout and L to O on Conditions.
CHECKS
Checks runs nine checks. Each result names the first row that fails, and Check on each row says what's wrong with it.
Check 3 reads Readiness only once something is typed on it. A project with no Readiness gate leaves Readiness empty, and Readiness decided by blank.
LIMITS
Rollout counts customers, not partners. The partners' notice is kept in the stakeholders file.
Check 2 is the gate map's check 4, A gate passed without its evidence, run on Readiness and Go/no-go only.
The checks can't tell whether the fallback still runs, or whether an undo would work. The assistant's brief asks the owners.
The owner checks can't catch a team written another way, such as Backend engineers. The assistant's brief looks for that.
UPKEEP
Clear a row to remove it. Don't delete rows.
OTHER FILES
The gate map holds the same criteria, word for word, and copies their status at each decision. A criterion taken from the acceptance and sign-off file keeps that file's wording. This file tracks them in the weeks before the call.
The decision log is the record of each decision. Decided by, Decided on and Outcome here are copies.
Window opens has the same start date as Cutover weekend in the plan workbook. The times and the end are kept only here.
Rollback owner is the person the RACI names for rolling back. The test evidence keeps each rehearsal's run, and this file the minutes.
The handover reads Still to move from Rollout.
Anyone who opens this file sees every row. To share it with someone outside the company, send them their lines, not the file.
An assistant can check the cutover workbook for you. The brief is in frqz-cutover-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results.

## Details
Details
Name
Sits under
Owner
Planned finish
Sponsor
Kept by
As of
Time zone
Window opens
Window closes
Rollback point
| Rollback limit (hours) | 4
Rollback owner
Fallback
Readiness decided by
Go/no-go decided by
Customers in all
Checks count from
Note on C22: Worked out: the date the checks count from. It's As of, or today when As of is blank.

## Readiness
Readiness
# | Id | Gate | Criterion | Owner (says it's met) | Status | Met or waived on | Evidence | Waived by | Reason | Note | Check | Owner, before any bracket | In use (1 or 0) | The first fault | Waiver or evidence fault | Its gate decided Go (1 or 0) | Open after a Go | Open, in order | Gate, when Open
Note on A5: Worked out: the criterion's place in the list.
Note on L5: The first thing wrong with this criterion. Filter on △ to list them.

## Go-no-go
Go/no-go
| Gate | Readiness | Go/no-go
Decided by
Gate date
Criteria
Met
Waived
Open
Decided on
Outcome
Note
State
Check
WINDOW
Window opens
Window closes
Time zone
Rollback point
Rollback limit (hours)
Rollback owner
Fallback
Last rollback timed (minutes)
First wave told on
Steps
Change steps with no undo
OPEN CRITERIA
| Criterion | Owner (says it's met) | Gate
Note on B6: Worked out: Readiness decided by and Go/no-go decided by, from Details.
Note on B8: Worked out: how many criteria on Readiness name this gate.
Note on B9: Worked out: how many of them are Met.
Note on B10: Worked out: how many are Waived.
Note on B11: Worked out: how many are still Open.
Note on B15: Worked out: decided, ready to decide, or how many criteria are still open.
Note on B16: Worked out: what's wrong with a Go. Clear when the gate isn't Go, or nothing is wrong.

## Runbook
Runbook
# | When | Step | Kind | Owner | With | Stop or undo | Done at | Check | In use (1 or 0) | The first fault | Change with no undo (1 or 0) | Owner, before any bracket
Note on A5: Worked out: the step's number.
Note on I5: The first thing wrong with this step. Filter on △ to list them.

## Rollback
Rollback
STEPS
# | Step | Owner | Check
REHEARSALS
# | Rehearsal | Date | Rollback timed (minutes) | Time | Against the limit | Evidence
Note on D5: The first thing missing from this step.
Note on E29: Worked out: the minutes as hours and minutes.
Note on F29: Worked out: against the Rollback limit on Details.

## Rollout
Rollout
Wave | Who | Customers | Opens | Why in this order | Told on | Told by | Last move | Moved so far | Scheduled | Still to move | Check | Due to have moved by now | Latest Needed by of its conditions | Check 7: the fault | Check 8: the fault | Check 9: the fault
Note on A5: Worked out: the wave's number. Conditions and Moves find the wave by it.
Note on J5: Worked out: Customers moving for this wave, added up from Moves.
Note on K5: Worked out: Customers minus Moved so far.
Note on L5: The first thing wrong with this wave. Filter on △ to list them.

## Conditions
Conditions
# | Wave | Condition | Owner | Needed by | Status | Evidence or reason | RAID Id | Note | Check | In use (1 or 0) | The first fault | Owner, before any bracket | Needed by, as a number
Note on A5: Worked out: the condition's place in the list.
Note on J5: The first thing wrong with this condition. Filter on △ to list them.

## Moves
Moves
Wave | Month | Customers moving | Moved | Check
Note on E5: The first thing wrong with this row.

## Checks
Checks
# | Check | Result | Rule
1 | A criterion with no Id, gate, owner or status |  | Each criterion on Readiness has an Id used once, the gate Readiness or Go/no-go, a criterion, one person as owner and a status.
2 | A gate passed without its evidence |  | A gate decided Go has no Open criterion, no waiver missing its name, reason or date, and no Met line without evidence.
3 | A go/no-go missing its decider or fallback, or with dates out of order |  | Each decider is one name, the rollback owner and fallback are filled in, the window and rollback point are in order, and Readiness was Go on or before the Go/no-go.
4 | A step out of place, or with no time, Kind or owner |  | Each runbook step has a time, a Kind and one owner, comes no earlier than the step above, and falls in the window, or within a day of it for a Prepare or a Hold.
5 | A Change step with no way to undo it |  | Each Change step says in Stop or undo how to undo it, or says None, fixed forward.
6 | A rollback not written, owned or timed within the limit |  | Once any rollback detail is typed, a runbook step sits at the Rollback point, each rollback step has one owner, and the last rehearsal is timed within the limit.
7 | A rollout that doesn't add up |  | The waves add up to Customers in all and open in order, each wave opening within 60 days has Moves that add up to its Customers, and no wave has moved more than its Customers.
8 | A wave condition or notice that's incomplete or late |  | Each wave is told before it opens, each wave after the first has a condition due by then, and each condition has one owner, a date and a status.
9 | A wave that runs late |  | Each wave's Last move is on or after Opens and by the Planned finish, and Moved so far keeps up with the Moves plan for months that have ended.
All checks