## Read me
Stakeholders workbook (Example)
Everyone with a stake in one project: what each of them cares about, who on our side talks to them, what we send them and when, and what they've asked us. Five tabs: Read me, Stakeholders, Communication, Asks and Checks.
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 22 Oct 2026. Clear the white cells to start your own.
Before you send it on
Influence and Engagement note on Stakeholders (columns I and J) are yours alone. Before the file goes to anyone outside the project team, clear both columns. Clear them; don't delete them.
Where to start
Start on Stakeholders: copy the project's Name, Sits under and Owner from the Register, then list everyone. Then add what you send on Communication, and log asks on Asks as they come in.
Filling it in
1 | At the top of Stakeholders, copy the project's Name, Sits under and Owner from the portfolio Register, letter for letter. Type Plan baselined on once that gate has passed.
2 | List everyone with a stake, one per row: the people in the project charter, the RACI and the RAID log, and any group the work affects, such as customers.
3 | Give each row a Role, what they care about and an Our contact. The Owner and anyone On the team don't need a contact.
4 | On Communication, add a line for each thing you send or hold: the message, who it goes to, its form, who sends it, how often, and when it starts. To reach everyone in a role, pick Everyone: and the role.
5 | Each week, type Last sent on every line that went out. Next due works out from it.
6 | On Asks, log each question or concern that needs a reply, and who answers it. When you reply, type the date and what you told them.
7 | Read Checks, and fix every row that shows △.
YOUR LOGO
The FRQZ logo is in cell A1 on every tab. To use your own, delete it and insert your logo in A1, on each tab.
ROLES
Sponsor | Can stop the project. In a program, it's the program's sponsor, as the Register has it.
Owner | Answers for the project. The Register's Owner.
Decides at a gate | Decides one or more gates on the gate map.
On the team | Works on the project.
Takes it over | Runs what the project hands over, from handover on.
Affected | Lives with the change without working on it, such as customers.
Advises | Is asked before decisions, such as security or a vendor.
Other | Anyone else the project has to keep in mind.
HOW OFTEN
Next due starts at the planned date. A line that repeats is then due again after each Last sent.
Weekly | Due 7 days after Last sent.
Fortnightly | Due 14 days after Last sent.
Monthly | Due on the same date next month, or the month's last day if it has no such date.
Quarterly | Due on the same date three months on.
At each gate | Add one line for each gate, with the gate's date as its planned date. It's due on that day until it's sent.
On an event | Goes out when something happens, such as an announcement. It has no Next due and is never late.
Once | Due on its planned date. Once it's sent, it's done.
LAST SENT
Last sent is the one cell to update each week. If your email or chat tool keeps a send history, copy the dates from it.
ASKS
Asks is there to show whether anyone replied. Log each question or concern that needs an answer, who answers it, and what you told them.
It catches an empty reply, not a poor one. Whether a reply answers the question is for a person to judge.
If an ask becomes an acceptance criterion, a risk or a dependency, write it there, and say where in What we told them, such as Added to the RAID log.
NAMES
Write each person the way the other project files do: first name, then role in brackets, such as Imani (Security Lead). A group gets one name, such as Customers billed monthly in the US.
A space at the start or end of a pasted name makes it a different name. Check 6 flags it on purpose.
THE SPONSOR
In a program, the project's Sponsor is the program's, as the Register has it. If the Register has none, check 5 fails, and it should.
Outside a program, list as Sponsor whoever can stop the work, such as the founder or the Owner's manager.
Takes it over is needed from the day in Plan baselined on. Before that, the people who'll take it over often aren't known.
THE FILE'S DATE
Every date check uses As of on Stakeholders if you type one, and today's date if you don't. That's the file's date.
TYPING AND CLEARING
Type in the white cells. Grey cells are worked out and locked.
Clear a row to remove it. Rows can't be inserted or deleted. Filter freely. To sort, unprotect the sheet first and protect it again after.
READING THE MARKS
△ | A check found something, and the words say what. Filter Row check or Line check on △ to list the rows.
○ Clear | The check found nothing.
○ Open | On Asks: an ask still inside its days to answer.
○ Answered | On Asks: an ask with a date and a reply.
THE CHECKS
Checks runs six checks, each with its result and what to do. Row check and Line check on each tab say what's wrong with each row.
A message counts for check 2 if it repeats, goes On an event, or has a Next due or Last sent within 90 days of the file's date.
Rows used, under the checks, shows how full each tab is.
OTHER FILES
The roles here are a person's standing on the whole project. The RACI's letters are for one decision at a time, so don't copy one into the other.
Team or organisation is a person's team for staff, as on the RACI's People tab, and their organisation for anyone outside.
An assistant can check the file for you. The brief is in frqz-stakeholders-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results.
ABOUT THIS EXAMPLE
Hollins Software is a made-up software company. Everyone in it is made up too.
This is the stakeholder file for Billing Engine Rewrite, as of 22 Oct 2026. As of is typed, so the results stay as they are.
Influence and Engagement note are Anders's own, as the Owner. In a copy sent outside the team, those two columns would be empty.
It fails five of the six checks on purpose.
Check 1 | Partners billed monthly, the resellers, have no Our contact. Nobody on our side talks to them.
Check 2 | Noor (Support Lead) takes over support after cutover, and no line on Communication goes to her.
Check 3 | The invoice totals for Rhys were due on 9 Oct 2026, a fortnight after they last went. They're 13 days late. The weekly report to Hugo is due today and isn't late.
Check 4 | Rhys asked on 29 Sep whether the new engine exports the same invoice file, and has waited 23 days. Imani's question about card numbers is marked answered on 14 Oct with nothing written. Noor's ask is still inside its 14 days.
Check 5 | No row is Sponsor. Billing and Payments Program has no sponsor, so the project has none, and the check is right to fail. Priya (CTO) decides three gates and stands in at Go/no-go, so her role is Decides at a gate.
Check 6 | Check 6 is clear. To see it fail, paste a name with a space at the end.

## Stakeholders
Stakeholders (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 22 Oct 2026. Clear the white cells to start your own.
PROJECT
NAME | Billing Engine Rewrite |  | PLAN BASELINED ON | 2026-06-12 | [15 empty] | Date used
SITS UNDER | Billing and Payments Program | [18 empty] | Days to answer used
OWNER | Anders (Engineering Manager) | [18 empty] | Sponsor listed
AS OF | 2026-10-22 | [18 empty] | Owner listed
PROJECT CHARTER VERSION | v1 | [18 empty] | Takes it over needed
DAYS TO ANSWER AN ASK | 14 | [18 empty] | Owner matches the Register
STAKEHOLDERS | [7 empty] | PRIVATE | [11 empty] | Takes it over listed
Name | Team or organisation | Role on the project | Cares about | Our contact | Messages to them | Asks open | Row check | Influence (keep private) | Engagement note (keep private) | Row in use (1 or 0) | Name flag (1 or 0) | Our contact: 0 blank, 1 listed, 2 not listed | Role flag (1 or 0) | Helper, worked out | Fails check 2 (1 or 0) | Fails check 1 (1 or 0) | Fails check 6 (1 or 0) | Lines that count for check 2 | Helper, worked out | Roles | Influence | Forms | How often | To list | Everyone prefix
Anders (Engineering Manager) | Engineering | Owner | A cutover weekend that doesn't need the old engine back |  |  |  |  | High | [11 empty] | Sponsor | High | Report | Weekly |  | Everyone:
Hugo (Program Manager) | Program office | Advises | All invoices from the new engine by 30 Sep 2027 | Anders (Engineering Manager) |  |  |  | High | Wants one number, not a plan | [10 empty] | Owner | Medium | Announcement | Fortnightly
Priya (CTO) | Executive | Decides at a gate | Billing moved before the January renewals | Hugo (Program Manager) |  |  |  | High | Reads the monthly roll-up, not the weekly report | [10 empty] | Decides at a gate | Low | Meeting | Monthly
Rhys (Finance Operations Lead) | Finance Operations | Takes it over | Invoice totals that match the old engine, and the first billing run out on time | Anders (Engineering Manager) |  |  |  | Medium | Slow on email; ask at the fortnightly one to one | [10 empty] | On the team |  | One to one | Quarterly
Esi (Finance Operations Analyst) | Finance Operations | On the team | Closing the first month's billing on the new engine before she leaves | Anders (Engineering Manager) |  |  |  | Low | Leaves 18 Dec 2026; Rhys's team picks up her work | [10 empty] | Takes it over |  | Sign-off | At each gate
Noor (Support Lead) | Support | Takes it over | Rollback steps her team can follow when a customer calls about an invoice | Anders (Engineering Manager) |  |  |  | Low | [11 empty] | Affected |  |  | On an event
Imani (Security Lead) | Security | Advises | Card and tax data handled so the audit finds nothing major | Anders (Engineering Manager) |  |  |  | Medium | [11 empty] | Advises |  |  | Once
Backend engineers | Engineering | On the team | Weekend work known weeks ahead | Anders (Engineering Manager) |  |  |  | Low | [11 empty] | Other
Payments processor | Payments vendor | Advises | A test window booked, and a cutover date they can staff | Anders (Engineering Manager) |  |  |  | Medium
Partners billed monthly | Reseller partners | Affected | The charge on the 1st staying the same |  |  |  |  | Low
Customers billed monthly in the US | Customers | Affected | An invoice that looks the same through the cutover weekend | Noor (Support Lead) |  |  |  | Low
Customers outside the US and on annual contracts | Customers | Affected | An invoice that looks the same and arrives before renewal | Noor (Support Lead) |  |  |  | Low
Note on A13: A person as first name and role in brackets, such as Imani (Security Lead), or a group, such as Partners billed monthly. Use each name once.
Note on B13: Their team, for someone inside the company, such as Finance Operations. For anyone outside, their organisation.
Note on C13: Their standing on the project, one per row. Pick from the list; Read me says what each role means.
Note on D13: What they want from the project, in one line.
Note on E13: The person on our side who talks to them. Pick a name from this tab.
Note on F13: Worked out: lines on Communication that go to them by name or to everyone in their role.
Note on G13: Worked out: their asks on Asks with no Answered on date.
Note on H13: The first thing wrong with this row. Filter on △ to list them.
Note on I13: How much pull they have over the outcome: High, Medium or Low. Blank is unrated. Yours alone, and no check reads it.
Note on J13: How to work with them, in a line. Yours alone.

## Communication
Communication (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 22 Oct 2026. Clear the white cells to start your own.
MESSAGES
Message | To | Form | Sent by | How often | First or planned date | Last sent | Next due | Line check | Line in use (1 or 0) | To found (1 or 0) | Sent by: 0 blank, 1 listed, 2 not listed | Form or How often flag (1 or 0) | Date flag (1 or 0) | Counts for check 2 (1 or 0) | Late (1 or 0) | Fails check 6 (1 or 0)
Weekly status report | Hugo (Program Manager) | Report | Anders (Engineering Manager) | Weekly | 2026-10-08 | 2026-10-15
Monthly roll-up | Priya (CTO) | Report | Hugo (Program Manager) | Monthly | 2026-09-30 | 2026-09-30
Invoice totals from the old engine, for matching | Rhys (Finance Operations Lead) | One to one | Anders (Engineering Manager) | Fortnightly | 2026-09-11 | 2026-09-25
Team stand-up | Everyone: On the team | Meeting | Anders (Engineering Manager) | Weekly | 2026-10-26
Readiness evidence | Everyone: Advises | Report | Anders (Engineering Manager) | At each gate | 2026-11-19
Cutover weekend, 12 and 13 Dec: what changes for you (told by 1 Dec 2026) | Customers billed monthly in the US | Announcement | Hugo (Program Manager) | On an event
Runbook and rollback for sign-off | Rhys (Finance Operations Lead) | Sign-off | Anders (Engineering Manager) | Once | 2026-11-12
Cutover weekend, 12 and 13 Dec: what changes for you (told by 1 Dec 2026) | Partners billed monthly | Announcement | Hugo (Program Manager) | On an event
Second wave from 1 Feb 2027: when your invoices move (told before 1 Feb 2027) | Customers outside the US and on annual contracts | Announcement | Hugo (Program Manager) | On an event
Note on A13: What goes out or is held, in a few words, such as Weekly status report.
Note on B13: A name from Stakeholders, or Everyone: and a role to reach everyone in that role.
Note on C13: Report, Announcement, Meeting, One to one or Sign-off.
Note on D13: Who sends it or runs it. Pick a name from Stakeholders.
Note on E13: Pick from the list. An announcement goes On an event, never on a schedule.
Note on F13: The first time it goes out, or the day it's planned for.
Note on G13: The last day it went out or the meeting was held. Update it each week.
Note on H13: Worked out from How often and the dates. Blank when nothing more is due.
Note on I13: The first thing wrong with this line. Filter on △ to list them.

## Asks
Asks (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 22 Oct 2026. Clear the white cells to start your own.
ASKS
Raised on | Who asked | What they asked or said | Who answers | Answer due | Answered on | What we told them, or did | Row check | Row in use (1 or 0) | Who asked listed (1 or 0) | Who answers listed (1 or 0) | Dates readable (1 or 0) | Waiting past due (1 or 0) | Marked answered, nothing written (1 or 0) | Fails check 6 (1 or 0) | Reply with no date (1 or 0)
2026-09-29 | Rhys (Finance Operations Lead) | Will the new engine export the same invoice file we import into the ledger? | Anders (Engineering Manager)
2026-10-01 | Payments processor | Which dates do you want our test environment for? | Anders (Engineering Manager) |  | 2026-10-08 | From 9 Nov to 18 Dec 2026. Booked.
2026-10-06 | Imani (Security Lead) | Which fields hold card numbers, and who can read them in test? | Anders (Engineering Manager) |  | 2026-10-14
2026-10-13 | Noor (Support Lead) | Can my team have the rollback steps two weeks before the cutover weekend? | Anders (Engineering Manager)
Note on A13: The day they asked or said it.
Note on B13: Pick a name from Stakeholders.
Note on C13: Their question or concern, in a line, close to their own words.
Note on D13: Someone who can decide, not only listen. Pick a name from Stakeholders.
Note on E13: Worked out: Raised on plus the days to answer on Stakeholders.
Note on F13: The day the reply went to them. Leave it blank until it has.
Note on G13: The reply itself, or what was done. If it became a risk or a criterion, say where, such as Added to the RAID log.
Note on H13: The first thing wrong with this row. Filter on △ to list them.

## Checks
Checks (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 22 Oct 2026. Clear the white cells to start your own.
# | Check | Result | What to do
1 | A stakeholder nobody on our side talks to |  | Name the person on our side who talks to each of them in Our contact. The Owner and anyone On the team don't need one.
2 | A stakeholder with no message within 90 days |  | Add a line on Communication to them by name, or to Everyone: and their role.
3 | A late message |  | Send it, then type the day in Last sent.
4 | An ask left without a reply |  | Reply, then type Answered on and what you told them. Write the reply itself, not only the date.
5 | A role the project needs that nobody holds |  | Add a row for each missing role. The Sponsor is the program's, as the Register has it; outside a program, whoever can stop the work. If the program has none, raise it there.
6 | A row the file can't read |  | On each tab, filter Row check or Line check on △ and fix what it says.
ROWS USED
Stakeholders
Communication
Asks