Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, week ending Thu 22 Oct 2026. About this Example, at the back, says which review questions it fails on purpose.

# Status report

Billing Engine Rewrite

| Name | Billing Engine Rewrite |
| --- | --- |
| Sits under | Billing and Payments Program |
| Owner | Anders (Engineering Manager) |
| Sponsor | Not yet named |
| Reader | Hugo (Program Manager) |
| Week ending | Thu 22 Oct 2026 |
| Report | 3 |
| Planned finish | Wed 30 Jun 2027 |

# 1. Status

| Line | This week | Last week | Why |
| --- | --- | --- | --- |
| Overall | Amber | Amber | Date sets it. Anders (Engineering Manager) decides CR-5 by Fri 6 Nov 2026. |
| Date | Amber | Amber | Build complete is forecast for Fri 13 Nov 2026, 5 working days after Fri 6 Nov. The only staging environment is booked by Data Migration Wave 2 until Fri 20 Nov, so the full-copy test for C-04 can't start before Mon 9 Nov. |
| Cost | Green | Green | Forecast at completion is the Baselined cost. |
| Scope | Green | Green | No change to scope is waiting. CR-5 moves a date only. |

# 2. Progress

| Measure | This week | Last week |
| --- | --- | --- |
| Acceptance criteria | 3 Met, 1 Waived, 8 Open | 3 Met, 1 Waived, 8 Open |
| Gates decided | 2 of 7: Start, Plan baselined | 2 of 7: Start, Plan baselined |

## Done this week

| What | Evidence | By |
| --- | --- | --- |
| Project charter v1 signed by the Owner. The other signatures are waiting. | Decision log, DL-11 | Anders (Engineering Manager) |
| Program board decision: customers outside the US and on annual contracts get the second-wave notice before Mon 1 Feb 2027. | Decision log, DL-12 | Hugo (Program Manager) |

# 3. Money

| Line | This week | Last week |
| --- | --- | --- |
| Share | 780,000 | 780,000 |
| Baselined cost | 780,000 | 780,000 |
| Owner's limit | 15,600 | 15,600 |
| Spent to date | 463,000 | 447,000 |
| Share spent | 59 percent | 57 percent |
| Forecast at completion | 780,000 | 780,000 |
| Over the share | 0 | 0 |

| Forecast given by | Anders (Engineering Manager), Thu 22 Oct 2026 |
| --- | --- |
| Spent given by | Rhys (Finance Operations Lead), Thu 22 Oct 2026 |

# 4. Dates

| Milestone | Baselined | Forecast | Working days late | Reading |
| --- | --- | --- | --- | --- |
| Build complete | Fri 6 Nov 2026 | Fri 13 Nov 2026 | 5 | Amber |
| Readiness | Thu 19 Nov 2026 | Thu 19 Nov 2026 | 0 | Green |
| Go/no-go | Thu 3 Dec 2026 | Thu 3 Dec 2026 | 0 | Green |
| Handover accepted | Fri 28 May 2027 | Fri 28 May 2027 | 0 | Green |
| Close | Wed 30 Jun 2027 | Wed 30 Jun 2027 | 0 | Green |

# 5. Changes

| No. | Change | Scope | Cost | Date | Status |
| --- | --- | --- | --- | --- | --- |
| CR-5 | Build complete moves from Fri 6 Nov to Fri 13 Nov 2026, so the full-copy test for C-04 can run once the second environment arrives on Mon 9 Nov. | None | 0 | +5 working days | Raised Thu 22 Oct 2026. Anders (Engineering Manager) decides by Fri 6 Nov 2026. |

# 6. Risks and issues

| Id | What | Owner | Response |
| --- | --- | --- | --- |
| R1 | The tax rules arrive late and hold up the second wave | Hugo (Program Manager) | Build the invoice match against the draft rules. Hugo reports the rules' date at each program meeting. |
| R3 | The new engine's running cost (140,000 a year) is in no budget line | Rhys (Finance Operations Lead) | None yet |
| R4 | The three backend engineers can't all stay to 18 Jan 2027 | Engineering managers | Anders asks each engineer's manager to confirm leave dates by 6 Nov 2026. |
| A2 | The test set of invoices covers every current plan and price list | Anders (Engineering Manager) | Anders compares the set with the price-list export. |
| I1 | The staging environment is booked by Data Migration Wave 2 until 20 Nov 2026 | Anders (Engineering Manager) | Anders has asked Kofi for a second environment from 9 Nov 2026. |
| X3 | Last year's invoices exported from the old engine | Anders (Engineering Manager) | Rhys's team exports them once the staging environment is free. |

# 7. Decisions needed

| Decision needed | From | By |
| --- | --- | --- |
| Chase Invoice Tax Rules so the tax rules for customers outside the US arrive by Mon 1 Feb 2027 (R1) | Hugo (Program Manager) | Mon 2 Nov 2026 |
| Name who signs the old engine's hosting renewal, which renews on Sun 31 Jan 2027 | Not yet named | Before 31 Jan |
| Confirm the second staging environment from Mon 9 Nov 2026 (I1) | Kofi (Delivery Lead) | Fri 6 Nov 2026 |

# 8. Coming up

| What | On | Who |
| --- | --- | --- |
| Three backend engineers start | Mon 26 Oct 2026 | Anders (Engineering Manager) |
| Invoice Tax Rules starts | Mon 2 Nov 2026 | Hugo (Program Manager) |
| Security and code review before Build complete | Tue 3 Nov 2026 | Imani (Security Lead) |
| Program board | Thu 5 Nov 2026 | Hugo (Program Manager) |

# 9. Approval

| Step | Name | Day |
| --- | --- | --- |
| Prepared by | Anders (Engineering Manager) | Thu 22 Oct 2026 |
| Approved by | Anders (Engineering Manager) | Thu 22 Oct 2026 |
| Sent to | Hugo (Program Manager) | Thu 22 Oct 2026 |

# Review questions

The Owner asks these eight questions before approving, and a reviewer asks them before a gate. Anything that isn't a yes is fixed before the report goes.

| # | Question | Yes when |
| --- | --- | --- |
| 1 | Same names. Do the names match the Register, the stakeholders file and the gate map? | Name, Sits under and Owner are the Register's, letter for letter, and Planned finish is the Register's date. Sponsor is the program row's, or Not yet named when that's blank. Reader is the stakeholders file's reader for this report. Every gate in Progress and Dates is one of the gate map's seven, and every other Dates row has the plan's name for it, letter for letter. |
| 2 | The readings follow the rules. Is each reading what the rules give? | Date, Cost and Scope are what the rules in Before you start give from Money, Dates and Changes, read against Baselined as it stands. Each Reading in Dates follows the same rule. Overall is the worst of the three. Each Last week is what last week's report has under This week. |
| 3 | The numbers add up. Do the figures and the day counts work out? | Share spent is Spent to date over the Share, as a whole percent, in both columns. Over the share is Forecast at completion minus the Share. Spent to date isn't below Last week, and each Last week figure is last week's report's. Each Working days late counts Monday to Friday from Baselined to Forecast. Every printed weekday matches its date. |
| 4 | Nothing is left out. Is every late date, open change and picked RAID line in the report? | Every row of the plan whose Forecast is later than its Baselined date is in Dates with the same two dates, and every gate still ahead has a row. A late gate has a change in Changes. Every change raised or decided since last week, and every one still raised, is in Changes. Every open RAID line the rule in Before you start picks is in Risks and issues. |
| 5 | Money stays with the share. Do the money figures count this project's cost lines only? | Spent to date, Forecast at completion and the Share count the charter's cost lines only, with nothing after cutover. Forecast given by and Spent given by each name one person and a day. Spent to date isn't above Forecast at completion. |
| 6 | A person behind each colour. Does every Amber or Red line name the person who acts? | Every Amber or Red line of Date, Cost and Scope has a Why that names one person. Overall's Why names the line that sets it and the person who acts. When Forecast at completion is over the Share by more than the owner's limit, Cost's Why names who decides. Whether each Why is true is for a person to judge. |
| 7 | Someone can decide. Does every decision needed have one person and a day? | Every Decisions needed row has one named person in From and a weekday in By. Every Risks and issues row is an open line in the RAID log, with the same Id, What and Owner. |
| 8 | On the beat. Did this report go on time, to the right person? | Week ending is a Thursday, 7 days after the last numbered report's. Report is the last number plus 1, or Early, Red. Sent to is the Reader, and its Day is the Week ending or the next working day. An Early, Red report has a line reading Red and falls inside its own Thursday's week. |

# About this Example

Hollins Software is a made-up software company. Everyone in it is made up too.

This is report 3 for Billing Engine Rewrite, for the week ending Thu 22 Oct 2026. Report 1 went to Hugo (Program Manager) on Thu 8 Oct 2026.

It fails questions 4, 6 and 7 on purpose, and passes 1, 2, 3, 5 and 8.

| 4 Nothing is left out | The plan has Tax rules for outside the US moving from Mon 1 Feb 2027 to Fri 12 Feb 2027, and Dates doesn't show it. |
| --- | --- |
| 6 A person behind each colour | Date's Why names nobody. It gives the cause, the staging environment Data Migration Wave 2 has booked, and Data Migration Wave 2 is a project. |
| 7 Someone can decide | Decisions needed row 2, the hosting renewal, has no person or day: From reads Not yet named, By reads Before 31 Jan. |

R4's Owner reads Engineering managers, a team. That's the RAID log's planted failure, copied as the log has it, and it's why Risks and issues shows R4. Question 7 compares the Owner with the log, so it passes.

Risks and issues shows the six open lines the rule picks: R1, which Decisions needed names; R3, with no response; R4; A2, with no look-again date; I1, whose look-again date passed on Fri 16 Oct 2026; and X3, with nobody named to answer for it.

Cost is Green. Forecast at completion, 780,000, is the Baselined cost. The new engine's running cost, 140,000 a year, is in no budget line, so it stays out of Money and sits in Risks and issues as R3.

Sponsor reads Not yet named, as on every Hollins file: Billing and Payments Program has no sponsor.

# Before you start

A status report says where one project stands at the end of one week, for one reader. Each report covers the week to a Thursday, and goes out that day or the next working day.

Name, Sits under and Owner are copied from the project's row on the Register, letter for letter, and Planned finish is the Register's date with its weekday. Sponsor is copied from the program's row, and Reader from the stakeholders file. Gate names are the gate map's seven, letter for letter.

Start from last week's report. Report goes up by 1 and Week ending by 7 days, and this week's readings and figures move to Last week.

Money is numbers only, in the charter's currency. The Share and the owner's limit come from the charter; Baselined cost and Forecast at completion from the plan. Spent to date comes from the finance export, for the charter's cost lines only, with nothing after cutover.

Dates has a row for each gate still ahead, and for any other row of the plan whose Forecast is later than its Baselined date, under the plan's name for it.

Changes lists each change raised or decided since last week's report, and every one still raised. A decided change shows once more under its CH number, with the dates it moved, then drops off.

Risks and issues copies Id, What, Owner and Response from the RAID log for each open line that has no response, no single named owner, a look-again date missing or passed, or nobody named to answer a dependency, and for each line Dates, Changes or Decisions needed names. Lines the log keeps on the program workbook aren't copied.

Decisions needed lists what someone else has to decide, or has to do before a decision can be made, with one person in From and a weekday in By. Coming up covers the next two weeks.

Write every person as Name (Role), one to a cell. A team, a board or a project never owns a line. A table with nothing in it reads None this week.

Before approving, check the report against the eight review questions after Approval.

Approval covers the report as sent. One person may prepare it and approve it. Once Sent to has a day, the report isn't changed: anything wrong is corrected in the next one.

The report ends at Approval. The pages after it are guidance: leave them out of the copy you send.

An assistant can check it for you. The brief is in frqz-status-report-agent-brief.txt, beside this file.

To use your own logo, right-click the FRQZ logo at the top right and choose Change Picture. In Google Docs, choose Replace image.

## Readings

Each reading is taken against the Baselined dates and cost as they stand, after approved changes. It is written as a word in its shaded cell: Green, Amber, Red, or Not read.

Date. Green when no gate or milestone of this project is forecast later than its Baselined date. Amber when one is, by up to 5 working days. Red when one is later by more, or its Baselined date is before Week ending and it isn't done. A date another project provides is shown in Dates and doesn't colour Date.

Cost. Green when Forecast at completion is the Baselined cost or less. Amber when it's over by up to 10 percent. Red when it's over by more.

Scope. Green while no change to scope is waiting for a decision. Amber while one is. Red when something was added or removed with no decision.

Overall is the worst of Date, Cost and Scope.

The owner's limit is how far the Owner may move a date, 5 working days, or spend over the Share, 15,600, without asking anyone. Money prints it, and it colours nothing. When Forecast at completion is over the Share by more than it, Cost's Why names who decides.

Once a change is approved, Baselined becomes the approved date or cost, so a reading goes back to Green when the forecast meets it. Changes shows the change once under its CH number.

An Amber or Red line of Date, Cost or Scope has a Why that names the person who acts. Overall's Why names the line that sets it and that person.

A line that turns Red goes to the Reader that day, in a report marked Early, Red. It keeps its week's Thursday as Week ending and takes no number, and the next weekly report takes the number it would have had.

In FRQZ, Green reads On track.