## Read me
Test evidence workbook (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 22 Oct 2026. Clear the white cells to start your own.
Test evidence for one project: each run of a test against an acceptance criterion, with its date, who ran it, who checked it, the result and the file it's kept in. Four tabs: Read me, Summary, Criteria and Runs.
Where to start
Start on Summary with the project's details from the Register and the builders from acceptance and sign-off. Then copy the criteria onto Criteria, and plan a run for each one on Runs.
Filling it in
1 | On Summary, copy Name, Sits under and Owner from the Register, and the Version of acceptance and sign-off into Criteria version. Copy its builders under Who builds it.
2 | Under Gate map dates, type each gate's Date from the gate map. It's optional.
3 | On Criteria, copy five columns from acceptance and sign-off: ID, Criterion, Pass line, Owner (says it's met) and Status. Gate and Needed by are optional.
4 | On Runs, plan a run for each criterion before its gate: its number, the criterion's ID, the day, what it's tested on, who runs it, who checks it, and the Pass line copied into Pass line used.
5 | On the day, the checker sets the Outcome. Type the Result and the File. For Failed or Not run, say why in Reason.
6 | In the week before each gate, read the seven checks on Summary and fix every row whose Row check shows △.
7 | When a criterion's Status changes on acceptance and sign-off, copy it here. Only its Owner marks it Met, and does it there.
YOUR LOGO
The FRQZ logo is at the top of every tab. To use your own, delete it and insert your logo in the same cell.
TYPED AND WORKED OUT
Type in the white cells. Grey cells are worked out, so don't type over them. They're locked, with no password. The hidden columns on Criteria and Runs hold the checks' working, each with a header.
READING THE MARKS
△ | A check found something, and the words say what. Filter Row check on △ to list the rows.
○ Clear | The check found nothing. Every check reads clear until a row is typed.
◇ | A prompt to look again. It isn't counted as a failure.
READING
Passed | The latest run with a result passed.
Failed | The latest run with a result failed.
Not run | The latest run was set down as Not run, with a Reason, such as for a waived criterion.
Planned | A run is booked and nothing has been run yet.
No run | Nothing is booked.
The latest run is the one with a result and the latest Date. On the same day, the row further down counts. A planned re-run never hides an earlier pass.
RUNS
1 | A result with no file is a claim, so name the file each result is kept in.
2 | The checker reads the result and sets the Outcome. A checker who confirms by message puts the message's date in Result. The checker can't be a builder or the person who ran the test.
3 | One person runs each test. The Build agent counts as one; a team doesn't.
4 | Date is the day the result is read. For a planned run, it's the day it's planned for.
5 | Copy the Pass line into Pass line used when you plan the run, and never update it. A Pass line changed after the run was planned is a different test: plan a new run against the new line, even when the old run passed.
6 | After a failure, plan a new row with a new number. A criterion tested twice, such as in two rehearsals, needs both runs planned.
7 | Clear a row, never delete it. Put its story in the Reason of the run that replaced it.
8 | A run can answer a RAID log line instead of a criterion: type its Id, such as R5, in For. A risk closed on a test needs a run with a Result and a File.
NEEDED BY
Needed by is the day the criterion's gate is decided: the gate's Forecast on the plan's Schedule if that is a date, or else its Date on the gate map. When a gate moves, whoever decides the change retypes Needed by that day.
NAMES
Write each person the way the Register writes an Owner: Rhys (Finance Operations Lead). Check 2 compares the name before the bracket, whole, so Ana and Diana are two people.
THE CHECKS
Summary runs seven checks, counting from Date the checks use. Row check on Criteria and on Runs says what's wrong with each row.
1 | A run or criterion not fully written down: a run with no number or a repeated one, a For that isn't a criterion ID or a RAID Id, or no Date; unless it's Not run, no Tested on or Run by, or Pass line used blank on a run for a criterion; a criterion ID used twice; or a run planned for a criterion with no Pass line.
2 | A run checked by a builder, its runner or nobody: any run, Planned included, whose Checked by names someone under Who builds it or the person in Run by, or a Passed or Failed run with Checked by blank. It also fails when Who builds it is empty and a run is typed.
3 | A result with no figure, file or reason: a Passed or Failed run without a Result, a File, or a Date on or before the date the checks use; a run Failed or Not run without a Reason; or a planned run with a Result or File.
4 | A criterion marked Met without a passing run: Status is Met and Reading isn't Passed.
5 | An open criterion needed soon with no run booked: an Open criterion whose Needed by is within Look ahead of the date the checks use, or already past, with no run Planned, Passed or Failed, or whose latest result failed with no planned re-run. Not run books nothing.
6 | A planned run past its day: a Planned run dated before the date the checks use.
7 | A run planned against a Pass line that has since changed: Pass line used differs from the criterion's Pass line on Criteria, Passed runs included.
LIMITS
1 | The checks see that a file is named, not that it holds the figure.
2 | They see a changed Pass line only if you copied it when you planned the run.
3 | Check 2 compares names, not whether the checker looked. It misses a builder written another way, such as Backend engineer 1 for Backend engineers.
4 | Check 1 sees that a Pass line is there, not that anything could fail it. Acceptance and sign-off checks the wording.
5 | They can't see a test nobody planned.
OTHER FILES
1 | Name, Sits under and Owner come from the Register, and the criteria from acceptance and sign-off. Files connect by these names, never by formulas.
2 | Acceptance and sign-off keeps each criterion's Status. Its Evidence can name the run, such as T-03, Comparison run report, 14 Oct 2026.
3 | The status report reads Met, Waived and Open under Acceptance and sign-off on Summary.
4 | Anyone who opens this file sees every cell. To share it with someone outside the company, send them their rows, not the file.
5 | An assistant can check the sheet for you and draft planned runs. The brief is in frqz-test-evidence-agent-brief.txt, beside this file. Open and save the workbook once in your spreadsheet first, so the assistant can read the results. It never sets an Outcome or a Result, or names who checked.
ABOUT THIS EXAMPLE
Hollins Software is a made-up software company. Everyone in it is made up too.
This is the test evidence for Billing Engine Rewrite, as of Thu 22 Oct 2026. Tests have run to 15 Oct, and every later run is planned.
It fails checks 2, 3, 5 and 7 on purpose, and passes 1, 4 and 6.
Check 2 | T-04, Finance's 12 invoice cases for C-07, is checked by Anders (Engineering Manager), and Anders is on the builders list. T-05 is marked Passed with nobody in Checked by.
Check 3 | T-05 was typed on 15 Oct 2026, the day RAID line R5 closed, for the comparison of 200 invoices. It's marked Passed, and no result or file was kept.
Check 5 | C-12, credit notes and refunds, is needed by 3 Dec 2026 for Go/no-go and has no run booked. Acceptance and sign-off already says how to test it, so what's missing is the booking.
Check 7 | T-08, the defect count for C-06, was planned against the Pass line signed on 28 Sep 2026, which allowed 0 severity 2 defects. On 15 Oct the line became 3 or fewer, so T-08 tests a line that has changed.
Check 1 | C-05's Pass line still reads Fast enough for month end, as acceptance and sign-off has it. Check 1 sees that a Pass line is there, not whether anything could fail it.
◇ | Build complete is forecast for Fri 13 Nov, a week after its gate map Date of Fri 6 Nov, so C-04, C-05 and C-06 show a ◇. C-05's month-end run, T-07, is planned for Tue 17 Nov, after it, which is the second ◇ on C-05.
Run by gives a numbered role, such as Backend engineer 1, where Hollins hasn't named the person. Each is one person, never a team.
As of on Summary is 22 Oct 2026, so the results stay as they are. Clear it and the checks count from today.
Note on A1: To use your own logo, delete this one and insert yours here.

## Summary
Test evidence (Example) |  |  |  | Criteria in use
Runs in use
ABOUT |  | WHO BUILDS IT
NAME | Billing Engine Rewrite | Anders
SITS UNDER | Billing and Payments Program | Backend engineers
OWNER | Anders (Engineering Manager) | Build agent
CRITERIA VERSION | v2
AS OF | 2026-10-22
LOOK AHEAD (DAYS) | 60
DATE THE CHECKS USE
CHECKS
A run or criterion not fully written down |  | READINGS
A run checked by a builder, its runner or nobody |  | Passed
A result with no figure, file or reason |  | Failed
A criterion marked Met without a passing run |  | Planned
An open criterion needed soon with no run booked |  | Not run
A planned run past its day |  | No run
A run planned against a Pass line that has since changed
ACCEPTANCE AND SIGN-OFF
Met
Waived
Open
GATE MAP DATES
|  | Start | 2026-03-12
|  | Plan baselined | 2026-06-12
|  | Build complete | 2026-11-06
|  | Readiness | 2026-11-19
|  | Go/no-go | 2026-12-03
|  | Handover accepted | 2027-05-28
|  | Close | 2027-06-30
Note on H1: To use your own logo, delete this one and insert yours here.

## Criteria
Criteria (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 22 Oct 2026. Clear the white cells to start your own.
CRITERIA
ID | Gate | Criterion | Pass line | Owner (says it's met) | Status | Needed by | Runs | Latest run | Reading | Row check | Row in use (1 or 0) | Runs for this criterion | Row of the latest result on Runs (0 if none) | Fails check 1 (1 or 0) | Fails check 4 (1 or 0) | Fails check 5 (1 or 0) | Hint: passed, still Open (1 or 0) | Hint: a run planned after Needed by (1 or 0) | Hint: no Needed by (1 or 0) | Runs booked, Not run left out | Runs planned | Hint: Needed by isn't the gate map's Date (1 or 0)
C-01 | Plan baselined | Every plan item has an owner and a due date | 0 items missing either | Tomasz (PMO Head) | Met | 2026-06-12
C-02 | Plan baselined | Every report that reads the old engine's tax export works from the new engine | Every report Finance names runs | Hugo (Program Manager) | Waived | 2026-06-12
C-03 | Build complete | For each of 40 sample accounts, the new engine's invoice matches the old engine's | 40 of 40 match to the cent | Rhys (Finance Operations Lead) | Met | 2026-11-13
C-04 | Build complete | The new engine connects to the customer records Data Migration Wave 2 fills, with no invoice lost | Counts match, with 0 invoices missing | Rhys (Finance Operations Lead) | Open | 2026-11-13
C-05 | Build complete | The month-end invoice run is fast enough | Fast enough for month end | Rhys (Finance Operations Lead) | Open | 2026-11-13
C-06 | Build complete | Open defects at the gate are within the limit | 0 severity 1, 3 or fewer severity 2, 5 or fewer severity 3 | Noor (Support Lead) | Open | 2026-11-13
C-07 | Build complete | All 12 invoice cases Finance listed pass on the new engine | 12 of 12 pass | Anders (Engineering Manager) | Met | 2026-11-13
C-12 | Go/no-go | Credit notes and refunds from the new engine match Finance's figures | 10 of 10 match to the cent | Rhys (Finance Operations Lead) | Open | 2026-12-03
C-08 | Go/no-go | Billing can be rolled back to the old engine after cutover | Rollback finishes in 4 hours or less | Priya (CTO) | Open | 2026-12-03
C-09 | Handover accepted | Every invoice in the first live run matches the finance ledger | Totals match to the cent, with 0 unexplained differences | Rhys (Finance Operations Lead) | Open | 2027-05-28
C-10 | Go/no-go | Support can answer billing questions from the runbook alone | 10 of 10 answered without escalation | Noor (Support Lead) | Open | 2026-12-03
C-11 | Go-live | Finance Operations runs a month-end invoice run on the new engine alone | The run finishes with no engineering help | Rhys (Finance Operations Lead) | Open
Note on K1: To use your own logo, delete this one and insert yours here.

## Runs
Runs (Example)
Example. Hollins Software and everyone in it are made up. Billing Engine Rewrite, as of 22 Oct 2026. Clear the white cells to start your own.
RUNS
Run | For | Date | Run by | Checked by | Outcome | Result | File | Reason | Row check | Tested on | Pass line used | Row in use (1 or 0) | Outcome as read (blank reads Planned) | For is a criterion ID (1 or 0) | For is shaped like a RAID Id (1 or 0) | Latest result for its For (1 or 0) | For, on the latest result's row | Fails check 1 (1 or 0) | Fails check 2 (1 or 0) | Fails check 3 (1 or 0) | Fails check 6 (1 or 0) | Fails check 7 (1 or 0) | Fails check 1, Pass line (1 or 0)
T-01 | C-01 | 2026-06-12 | Anders (Engineering Manager) | Tomasz (PMO Head) | Passed | 0 items missing either | Tracker export, 12 Jun 2026 |  |  | The plan items in the tracker | 0 items missing either
T-02 | C-02 | 2026-06-12 |  |  | Not run |  |  | Waived. See DL-04.
T-03 | C-03 | 2026-10-14 | Build agent | Rhys (Finance Operations Lead) | Passed | 40 of 40 match to the cent | Comparison run report, 14 Oct 2026 |  |  | Both engines, 40 sample accounts | 40 of 40 match to the cent
T-04 | C-07 | 2026-10-15 | Build agent | Anders (Engineering Manager) | Passed | 12 of 12 pass | Case run results, 15 Oct 2026 |  |  | Finance's 12 invoice cases | 12 of 12 pass
T-05 | R5 | 2026-10-15 | Anders (Engineering Manager) |  | Passed |  |  | Typed on 15 Oct 2026, when R5 was closed. No result was kept. |  | 200 invoices, tax rounded both ways
T-06 | C-04 | 2026-11-12 | Backend engineer 1 | Rhys (Finance Operations Lead) | Planned |  |  | Runs 10 to 12 Nov, once the second environment arrives. |  | Full copy of the customer records | Counts match, with 0 invoices missing
T-07 | C-05 | 2026-11-17 | Backend engineer 1 | Rhys (Finance Operations Lead) | Planned |  |  |  |  | The month-end invoice run | Fast enough for month end
T-08 | C-06 | 2026-11-13 | Backend engineer 1 | Noor (Support Lead) | Planned |  |  |  |  | Open defects, counted by severity | 0 severity 1, 0 severity 2, 5 or fewer severity 3
T-09 | C-08 | 2026-11-14 | Backend engineer 1 | Priya (CTO) | Planned |  |  |  |  | Rehearsal 1, rollback on the staging copy | Rollback finishes in 4 hours or less
T-10 | C-08 | 2026-11-28 | Backend engineer 1 | Priya (CTO) | Planned |  |  |  |  | Rehearsal 2, rollback on the staging copy | Rollback finishes in 4 hours or less
T-11 | C-10 | 2026-11-26 | Support staff 1 | Noor (Support Lead) | Planned |  |  |  |  | 10 sample billing questions | 10 of 10 answered without escalation
T-12 | C-09 | 2027-01-08 | Finance Operations analyst 1 | Rhys (Finance Operations Lead) | Planned |  |  |  |  | December's first live run | Totals match to the cent, with 0 unexplained differences
T-13 | C-11 | 2027-01-29 | Finance Operations analyst 1 | Rhys (Finance Operations Lead) | Planned |  |  |  |  | The January month-end run | The run finishes with no engineering help
Note on J1: To use your own logo, delete this one and insert yours here.